## 시트1
| SCT SHIP NO. | MR# | INVOICE Date | VENDOR | CATEGORY | MAIN DESCRIPTION (PO) | SUB DESCRIPTION | SHU | DAS | MIR | AGI | INCOTERMS | COE | POL | POD | SHIPPING LINE | FORWARDER | SHIP MODE | PKG | 20DC | 40DC | LCL | G Bulk | O Bulk | H Bulk | GWT (KG) | CBM | R/T (GRAND- TOTAL) | ETD | ATD | ETA | ATA | Attestation Date | DO Collection | Customs Start | SHU | MIR | DAS | AGI | DSV Indoor | DSV Outdoor | DSV MZD | JDN MZD | JDN Waterfront | MOSB | AAA Storage | ZENER (WH) | Hauler DG Storage | Vijay Tanks
1 | HVDC-ADOPT-PPL-0001 | E02 | 2023-11-10 | Prysmian | Elec | 320kV HVDC Cable System | ±320kV Land Cable |  |  | O | O | CIF | FRANCE | Le Havre | Mina Zayed | BBC | Allied Seafreight Line | B | 19 | 0 | 0 | - |  | 1290.9 |  | 659580 | 1290.89 | 1290.89 | 2023-11-12 | 2023-11-12 | 2023-11-30 | 2023-12-01 | 2023-11-29 | 2023-11-30 | 2023-11-29 | [7 empty] | 2023-12-05
2 | HVDC-ADOPT-PPL-0002 | E02 | 2023-11-12 | Prysmian | Elec | 320kV HVDC Cable System | Onshore Optical Fibre Cable |  |  | O | O | CIF | FRANCE | Le Havre | Mina Zayed | BBC | Allied Seafreight Line | B | 12 | 0 | 1 | - | 75 |  |  | 23664.18 | 75 | 75 | 2023-11-12 | 2023-11-12 | 2023-11-30 | 2023-12-01 | 2023-11-29 | 2023-11-30 | 2023-11-29 | [7 empty] | 2023-12-06
3 | HVDC-ADOPT-HS-0001 | M02 | 2023-11-26 | SCT Trade | Mech | Tank Plate & Accessories | Tank Plate & Accessories | O | O | O | O | CIF | KOREA | Dangjin | Jebel Ali |  | Mariso Shipping | B | 66 | 0 | 0 | - | 60.1 |  |  | 471966 | 60.13 | 471.97 | 2023-11-26 | 2023-12-03 | 2024-01-07 | 2024-01-12 | 2023-12-08 | 2024-01-12 | 2024-01-12 | [13 empty] | 2024-01-20
4 | HVDC-ADOPT-PPL-0003 | E02 | 2023-12-17 | Prysmian | Elec | 320kV HVDC Cable System | DTS and DAS Monitoritng System |  |  | O | O | CIF | ITALY | La Spezia | Khalifa | MSC | Allied Seafreight Line | C | 6 | 0 | 1 | - |  |  |  | 1074 | 12.67 | 12.67 | 2023-12-15 | 2023-12-17 | 2024-02-12 | 2024-02-14 | 2023-12-20 | 2024-02-13 | 2024-02-14 |  |  |  |  | 2024-02-26
5 | HVDC-ADOPT-PPL-0004 | E02 | 2023-12-17 | Prysmian | Elec | 320kV HVDC Cable System | Cable Accessories |  |  | O | O | CIF | ITALY | La Spezia | Khalifa | MSC | Allied Seafreight Line | C | 88 | 1 | 6 | - |  |  |  | 27151 | 160.3 | 160.3 | 2023-12-15 | 2023-12-17 | 2024-01-30 | 2024-01-31 | 2023-12-20 | 2024-01-31 | 2024-01-31 | [7 empty] | 2024-02-05
6 | HVDC-ADOPT-PPL-0005 | E02 | 2023-12-21 | Prysmian | Elec | 320kV HVDC Cable System | Subsea Repair Joint |  |  | O | O | CIF | ITALY | Port of Pozzuoli | Mina Zayed |  |  | B | 18 | 0 | 0 | - | 26.9 |  |  | 7645 | 26.9 | 26.9 | 2023-12-21 | 2023-12-21 | 2024-01-07 | 2024-01-07 | 2024-01-02 | 2024-01-13 | 2024-01-16 | [7 empty] | 2024-01-07
7 | HVDC-ADOPT-PPL-0006 | E02 | 2023-12-21 | Prysmian | Elec | 320kV HVDC Cable System | Pulling Stocks |  |  | O | O | CIF | ITALY | Port of Pozzuoli | Mina Zayed |  |  | B | 1 | 0 | 0 | - | 1.2 |  |  | 975 | 1.2 | 1.2 | 2023-12-21 | 2023-12-21 | 2024-01-07 | 2024-01-07 | 2024-01-02 | 2024-01-13 | 2024-01-15 | [7 empty] | 2024-01-07
8 | HVDC-ADOPT-PPL-0007 | E02 | 2023-12-21 | Prysmian | Elec | 320kV HVDC Cable System | Repair Joint for FO Unit |  |  | O | O | CIF | ITALY | Port of Pozzuoli | Mina Zayed |  |  | B | 4 | 0 | 0 | - | 1.4 |  |  | 150 | 1.4 | 1.4 | 2023-12-21 | 2023-12-21 | 2024-01-07 | 2024-01-07 | 2024-01-02 | 2024-01-13 | 2024-01-13 | [7 empty] | 2024-01-07
9 | HVDC-ADOPT-PPL-0008 | E02 | 2023-12-21 | Prysmian | Elec | 320kV HVDC Cable System | Yale Grips |  |  | O | O | CIF | ITALY | Port of Pozzuoli | Mina Zayed |  |  | B | 2 | 0 | 0 | - | 0.2 |  |  | 597 | 0.2 | 0.6 | 2023-12-21 | 2023-12-21 | 2024-01-07 | 2024-01-07 | 2024-01-03 | 2024-01-13 | 2024-01-15 | [7 empty] | 2024-01-07
10 | HVDC-ADOPT-PPL-0009 | E02 | 2023-12-22 | Prysmian | Elec | 320kV HVDC Cable System | Minisub FOC Subsea Fiber Optic Cable |  |  |  |  | CIF | GERMANY | Nordenham | Mina Zayed |  |  | B | 6 | 0 | 0 | - | 2.6 |  |  | 560 | 2.62 | 2.62 | 2023-12-22 | 2023-12-22 | 2024-03-02 | 2024-03-02 | 2024-01-10 | 2024-03-01 | 2024-03-02 | [7 empty] | 2024-03-03
11 | HVDC-ADOPT-HE-0001 | E01 | 2023-12-01 | Hitachi | Elec | Main Converter | Bottom Schields |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 14 | 0 | 7 | - |  |  |  | 16016 | 351.3 | 351.3 | 2023-12-01 | 2023-12-01 | 2024-01-11 | 2024-01-11 | 2023-12-30 | 2024-01-13 | 2024-01-15 | [5 empty] | 2024-01-19
12 | HVDC-ADOPT-HE-0002 | E01 | 2023-12-04 | Hitachi | Elec | Main Converter | Part of valve |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 10 | 0 | 2 | - |  |  |  | 7456 | 70.8 | 70.8 | 2023-12-07 | 2023-12-07 | 2024-01-21 | 2024-01-21 | 2024-01-09 | 2024-01-19 | 2024-01-23 |  |  | 2024-07-14 |  |  | 2024-01-25 |  |  |  | 2024-05-08
13 | HVDC-ADOPT-HE-0003 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Serpentine, Side Shields, Bottom Shields (part of valve) |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 59 | 0 | 10 | - |  |  |  | 35148 | 371.02 | 371.02 | 2023-12-14 | 2023-12-14 | 2024-01-21 | 2024-01-21 | 2024-01-22 | 2024-01-19 | 2024-01-23 |  |  | 2024-07-14 |  | 2024-01-29 | 2024-01-29
14 | HVDC-ADOPT-HE-0004 | E01 | 2023-12-21 | Hitachi | Elec | Main Converter | Top Part Installation (Part of valve) |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 36 | 0 | 9 | - |  |  |  | 37440 | 469.24 | 469.24 | 2024-01-03 | 2024-01-03 | 2024-02-18 | 2024-02-18 | 2024-02-20 | 2024-02-19 | 2024-02-19 | [5 empty] | 2024-02-23
15 | HVDC-ADOPT-HE-0005 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Part of valve |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 82 | 0 | 10 | - |  |  |  | 62538 | 391.3 | 391.3 | 2023-12-21 | 2023-12-21 | 2024-02-10 | 2024-02-10 | 2024-02-12 | 2024-02-12 | 2024-02-12 |  |  | 2024-08-26 |  | 2024-02-15 | 2024-02-15 |  |  |  | 2025-03-27
16 | HVDC-ADOPT-HE-0007 | E01 | 2023-12-05 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 30 | 0 | 10 | - |  |  |  | 150000 | 438.83 | 438.83 | 2023-12-19 | 2023-12-19 | 2024-01-25 | 2024-01-20 | 2024-01-08 | 2024-01-19 | 2024-01-21 |  |  |  |  | 2024-02-02
17 | HVDC-ADOPT-HE-0008 | E01 | 2023-12-05 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 15 | 0 | 8 | - |  |  |  | 75000 | 219.41 | 219.41 | 2023-12-14 | 2023-12-14 | 2024-01-25 | 2024-01-21 | 2024-01-08 | 2024-01-19 | 2024-01-21 |  |  |  |  | 2024-01-30
18 | HVDC-ADOPT-HE-0009 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 24 | 0 | 8 | - |  |  |  | 120000 | 351.06 | 351.06 | 2023-12-14 | 2023-12-14 | 2024-01-25 | 2024-01-21 | 2024-01-08 | 2024-01-19 | 2024-01-21 |  |  |  |  | 2024-02-03
19 | HVDC-ADOPT-HE-0010 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 27 | 0 | 8 | - |  |  |  | 135000 | 394.94 | 394.94 | 2023-12-14 | 2023-12-14 | 2024-01-25 | 2024-01-21 | 2024-01-08 | 2024-01-19 | 2024-01-21 |  |  |  |  | 2024-02-05
20 | HVDC-ADOPT-HE-0011 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 24 | 0 | 8 | - |  |  |  | 120000 | 351.1 | 351.1 | 2023-12-14 | 2023-12-14 | 2024-01-25 | 2024-01-21 | 2024-01-08 | 2024-01-19 | 2024-01-21 |  |  |  |  | 2024-02-07
21 | HVDC-ADOPT-HE-0020 | E01 | 2023-12-10 | Hitachi | Elec | Main Converter | Layers |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 24 | 0 | 6 | - |  |  |  | 120000 | 351.06 | 351.06 | 2023-12-14 | 2023-12-14 | 2024-01-25 | 2024-01-21 | 2024-01-08 | 2024-01-19 | 2024-01-21 | [5 empty] | 2024-02-08
22 | HVDC-ADOPT-HE-0012 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 11600 | 41.2 | 41.2 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | [5 empty] | 2024-01-23
23 | HVDC-ADOPT-HE-0013 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 5800 | 20.6 | 20.6 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | [5 empty] | 2024-01-23
24 | HVDC-ADOPT-HE-0014 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  |  | O |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 1 | 1 | - |  |  |  | 28800 | 118.09 | 118.09 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-04 | 2024-01-10 | 2024-01-17 |  | 2024-01-26
25 | HVDC-ADOPT-HE-0015 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  |  | O |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 7200 | 29.52 | 29.52 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 |  | 2024-01-26
26 | HVDC-ADOPT-HE-0016 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor | O |  |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 11600 | 41.2 | 41.2 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | 2024-01-24
27 | HVDC-ADOPT-HE-0017 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor | O |  |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 5800 | 20.6 | 20.6 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | 2024-01-24
28 | HVDC-ADOPT-HE-0018 | E01 | 2003-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  |  |  | O | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 1 | 1 | - |  |  |  | 28800 | 118.09 | 118.09 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | [5 empty] | 2024-01-24
29 | HVDC-ADOPT-HE-0019 | E01 | 2023-12-08 | Hitachi | Elec | Main Converter | Smoothing reactor |  |  |  | O | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 7200 | 29.5 | 29.5 | 2023-12-10 | 2023-12-10 | 2024-01-13 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2024-01-17 | [5 empty] | 2024-01-24
30 | HVDC-ADOPT-HE-0021 | E01 | 2023-12-19 | Hitachi | Elec | Main Converter | Converter Reactors | O |  |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 25300 | 139.38 | 139.38 | 2023-12-19 | 2023-12-19 | 2024-01-21 | 2024-01-21 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 2024-01-26
31 | HVDC-ADOPT-HE-0022 | E01 | 2023-11-27 | Hitachi | Elec | Main Converter | Converter Reactors |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 17800 | 105.1 | 105.1 | 2023-12-19 | 2023-12-19 | 2024-01-21 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-23 | [5 empty] | 2024-01-26
32 | HVDC-ADOPT-HE-0023 | E01 | 2024-01-16 | Hitachi | Elec | Main Converter | Converter Reactors |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 17800 | 105.2 | 105.2 | 2024-01-16 | 2024-01-16 | 2024-02-18 | 2024-02-18 | 2024-02-13 | 2024-02-19 | 2024-02-19 |  |  | 2024-09-02 | [6 empty] | 2024-02-24
33 | HVDC-ADOPT-HE-0024 | E01 | 2024-01-16 | Hitachi | Elec | Main Converter | Converter Reactors | O |  |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 12650 | 69.6 | 69.6 | 2024-01-16 | 2024-01-16 | 2024-02-18 | 2024-02-18 | 2024-02-12 | 2024-02-19 | 2024-02-20 | 2024-02-27
34 | HVDC-ADOPT-HE-0025 | E01 | 2024-01-16 | Hitachi | Elec | Main Converter | Converter Reactors |  |  | O |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 17700 | 90.6 | 90.6 | 2024-01-16 | 2024-01-16 | 2024-02-18 | 2024-02-18 | 2024-02-12 | 2024-02-19 | 2024-02-20 |  | 2024-02-27
35 | HVDC-ADOPT-HE-0026 | E01 | 2024-01-16 | Hitachi | Elec | Main Converter | Converter Reactors |  | O |  |  | CIF | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 26700 | 157.8 | 157.8 | 2024-01-16 | 2024-01-16 | 2024-02-18 | 2024-02-18 | 2024-02-13 | 2024-02-19 | 2024-02-19 |  |  | 2024-09-02 | [6 empty] | 2024-02-24
36 | HVDC-ADOPT-HE-0027 | E01 | 2023-11-27 | Hitachi | Elec | Main Converter | Serpentine, Side Shields, Bottom Shields (part of valve) |  | O |  |  | CIF | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 54 | 0 | 15 | - |  |  |  | 37659 | 390.4 | 390.4 | 2024-01-03 | 2024-01-03 | 2024-02-29 | 2024-02-29 | 2024-01-19 | 2024-03-01 | 2024-03-01 |  |  | 2024-08-26 |  | 2024-03-08 | 2024-03-08 |  |  |  | 2025-03-27
37 | HVDC-ADOPT-HE-0062 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 |  | O |  |  | CIF | DENMARK | Copenhagen | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 12 | 0 | 0 | - | 12 |  |  | 2875 | 16.52 | 16.52 | 2024-01-23 | 2024-01-26 | 2024-01-28 | 2024-01-28 | 2024-02-01 | 2024-01-29 | 2024-01-30 |  |  |  |  | 2024-02-01 | 2024-02-01
38 | HVDC-ADOPT-HE-0063 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 |  | O |  |  | CIF | NETHERLANDS | Amsterdam | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 1 | 0 | 0 | - | 1 |  |  | 605 | 7.02 | 7.02 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-27 | 2024-02-01 | 2024-02-01 |  |  |  |  | 2024-02-02
39 | HVDC-ADOPT-HE-0064 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 | O |  |  |  | CIF | DENMARK | Copenhagen | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 14 | 0 | 0 | - | 14 |  |  | 3320 | 19.19 | 19.19 | 2024-01-23 | 2024-01-28 | 2024-01-29 | 2024-01-29 | 2024-01-27 | 2024-01-30 | 2024-01-30 |  | 2024-02-01 |  |  | 2024-02-01
40 | HVDC-ADOPT-HE-0065 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 |  |  | O |  | CIF | NETHERLANDS | Amsterdam | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 1 | 0 | 0 | - | 1 |  |  | 650 | 7.02 | 7.02 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 | 2024-02-01 |  |  |  |  | 2024-02-02
41 | HVDC-ADOPT-HE-0066 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 | O |  |  |  | CIF | DENMARK | Copenhagen | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 12 | 0 | 0 | - | 12 |  |  | 2875 | 16.52 | 16.52 | 2024-01-23 | 2024-01-28 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 |  |  |  | 2024-02-01
42 | HVDC-ADOPT-HE-0067 | E01 | 2024-01-23 | Hitachi | Elec | Main Converter | Optical Current Transducer EQ078 |  | O |  |  | CIF | NETHERLANDS | Amsterdam | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 1 | 0 | 0 | - | 1 |  |  | 605 | 7.02 | 7.02 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 2024-01-27 | 2024-02-01 | 2024-02-01 |  |  |  |  | 2024-02-02
43 | HVDC-ADOPT-HE-0028 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Single-phase converter reactor | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 18975 | 104.4 | 104.4 | 2024-01-29 | 2024-01-29 | 2024-02-29 | 2024-02-29 | 2024-02-12 | 2024-03-01 | 2024-03-01 | 2024-03-05
44 | HVDC-ADOPT-HE-0058 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 26550 | 135.9 | 135.9 | 2024-01-29 | 2024-01-29 | 2024-02-29 | 2024-02-29 | 2024-02-13 | 2024-03-01 | 2024-03-02 |  | 2024-03-06
45 | HVDC-ADOPT-HE-0059 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 26550 | 135.9 | 135.9 | 2024-01-29 | 2024-01-29 | 2024-02-29 | 2024-02-29 | 2024-02-13 | 2024-03-01 | 2024-03-02 |  | 2024-03-07
46 | HVDC-ADOPT-HE-0060 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 26700 | 157.8 | 157.8 | 2024-01-29 | 2024-01-29 | 2024-02-29 | 2024-02-29 | 2024-02-09 | 2024-03-01 | 2024-03-02 |  |  | 2024-09-02 | [6 empty] | 2024-03-07
47 | HVDC-ADOPT-PPL-0010 | E02 | 2024-02-14 | Prysmian | Elec | 320kV HVDC Cable System | Single Core Bonding Cable | O |  |  |  | DAP | OMAN | Muscat | UAE |  |  | B | 2 | 0 | 0 | - |  |  |  | 1657 | 3.6 | 3.6 | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-23 | 2024-02-15 | 2024-02-23 | 2024-02-22 | [7 empty] | 2024-02-23
48 | HVDC-ADOPT-PPL-0011 | E02 | 2024-02-15 | Prysmian | Elec | 320kV HVDC Cable System | End Caps for Subsea Cable | O |  |  |  | DAP | FRANCE | CDG | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 1 | 0 | 0 | - |  |  |  | 50 | 1.31 | 1.31 | 2024-02-19 | 2024-02-19 | 2024-02-28 | 2024-02-28 | 2024-02-15 | 2024-03-05 | 2024-03-05 | [7 empty] | 2024-03-06
49 | HVDC-ADOPT-PPL-0012 | E02 | 2024-02-23 | Prysmian | Elec | 320kV HVDC Cable System | Outer Sheath Repair Kit for Subsea Cable - HVDC and Telecom |  |  |  |  | DAP | FRANCE | CDG | Abu Dhabi Airport |  | Aprile Spa - Milano | A | 9 | 0 | 0 | - | 9 |  |  | 690 | 4.64 | 4.64 | 2024-02-29 | 2024-02-29 | 2024-03-01 | 2024-03-01 | 2024-02-28 | 2024-03-05 | 2024-03-05 | [7 empty] | 2024-03-10
50 | HVDC-ADOPT-PPL-0013 | E02 | 2024-02-27 | Prysmian | Elec | 320kV HVDC Cable System | FO Land Termination and Cleats |  |  |  |  | DAP | UK | London | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 502 | 2.97 | 2.97 | 2024-02-28 | 2024-03-01 | 2024-03-02 | 2024-03-02 | 2024-02-29 | 2024-03-05 | 2024-03-05 | [7 empty] | 2024-03-06
51 | HVDC-ADOPT-SCT-0001 | E08 | 2024-02-15 | Dong Yang | Elec | Cathodic Protection | Cathodic Protection Systems (1st) | O |  | O |  | FOB | KOREA | Busan Port | Khalifa port |  |  | C | 10 | 0 | 1 | - |  |  |  | 3408 | 11.24 | 11.24 | 2024-02-15 | 2024-02-15 | 2024-03-22 | 2024-03-22 | 2024-02-16 | 2024-03-19 | 2024-03-21 | 2024-03-28
52 | HVDC-ADOPT-SCT-0002 | M01 | 2024-04-23 | Excellift | Mech | Crane and Hoist | Crane and Hoist (1st) | O | O |  |  | FOB | MALAYSIA | Port Klang | Khalifa port |  |  | C | 16 | 1 | 3 | - |  |  |  | 15149 | 59.3 | 59.3 | 2024-04-25 | 2024-04-25 | 2024-05-11 | 2024-05-11 | 2024-05-03 | 2024-05-13 | 2024-05-13 | 2024-05-16 |  | 2024-05-15
53 | HVDC-ADOPT-SEI-0001 | E03 | 2024-02-20 | Sumitomo | Elec | 400kV HVDC Cable System | MRC Cable with Static tank | O | O |  |  | CIF | JAPAN | Osaka | Mina Zayed | United Heavy Lift GmbH & Co. KG |  | B | 5 | 0 | 0 | - |  | 4242.9 |  | 4465493.4 | 4116.48 | 4465.49 | 2024-02-20 | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-08 | 2024-03-25 | 2024-03-25 | [7 empty] | 2024-03-28
54 | HVDC-ADOPT-SEI-0002 | E03 | 2024-02-20 | Sumitomo | Elec | 400kV HVDC Cable System | Land & Spare Cable | O | O |  |  | CIF | JAPAN | Osaka | Mina Zayed | United Heavy Lift GmbH & Co. KG |  | B | 5 | 0 | 0 | - |  | 404.6 |  | 127772 | 152.54 | 152.54 | 2024-02-20 | 2024-02-20 | 2024-03-19 | 2024-03-19 | 2024-03-07 | 2024-03-25 | 2024-03-25 | [7 empty] | 2024-04-08
55 | HVDC-ADOPT-SIM-0001 | E04-1 | 2024-01-24 | Siemens | Elec | 400kV and 132kV New Converter GIS | LV Cable | O | O | O | O | CIF | BELGIUM | Antwerp | Khalifa port | MAERSK |  | C | 28 | 0 | 2 | - |  |  |  | 26633 | 55.22 | 55.22 | 2024-01-25 | 2024-02-09 | 2024-03-14 | 2024-03-14 | 2024-03-07 | 2024-03-14 | 2024-03-15 | 2024-03-28 | 2024-04-18 |  |  |  | 2024-03-20
56 | HVDC-ADOPT-HE-0053 | E01 | 2024-01-27 | Hitachi | Elec | Main Converter | Layers (Part of valve) | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 24 | 0 | 8 | - |  |  |  | 120000 | 351.1 | 351.1 | 2024-01-27 | 2024-01-27 | 2024-03-22 | 2024-03-22 | 2024-02-16 | 2024-03-23 | 2024-03-24 | 2025-03-19 |  |  |  | 2024-04-01
57 | HVDC-ADOPT-HE-0054 | E01 | 2024-01-27 | Hitachi | Elec | Main Converter | Serpentine, Light guides ( Part of Valve) | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 32 | 0 | 3 | - |  |  |  | 10271 | 121.6 | 121.6 | 2024-01-27 | 2024-01-27 | 2024-03-22 | 2024-03-22 | 2024-02-16 | 2024-03-23 | 2024-03-24 | 2025-04-25 |  |  |  | 2024-03-29
58 | HVDC-ADOPT-HE-0056 | E01 | 2024-01-27 | Hitachi | Elec | Main Converter | Bottom Shield, Side Shield, Corona Ring, Pipes | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 94 | 0 | 14 | - |  |  |  | 61875 | 655 | 655 | 2024-01-27 | 2024-01-27 | 2024-03-22 | 2024-03-22 | 2024-02-16 | 2024-03-25 | 2024-03-25 |  |  |  |  | 2024-04-04 | 2024-04-17
59 | HVDC-ADOPT-HE-0029 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 24000 | 105.2 | 105.2 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-16 | 2024-03-06 | 2024-03-07 | [5 empty] | 2024-03-14
60 | HVDC-ADOPT-HE-0071 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 1 | 0 | - |  |  |  | 12000 | 52.6 | 52.6 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-16 | 2024-03-06 | 2024-03-07 | [5 empty] | 2024-03-14
61 | HVDC-ADOPT-HE-0061 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 17800 | 105.2 | 105.2 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-20 | 2024-03-06 | 2024-03-08 |  |  | 2024-09-02 | [6 empty] | 2024-03-14
62 | HVDC-ADOPT-HE-0074 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 8900 | 52.6 | 52.6 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-22 | 2024-03-06 | 2024-03-08 |  |  | 2024-09-02 | [6 empty] | 2024-03-14
63 | HVDC-ADOPT-HE-0072 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 26550 | 135.9 | 135.9 | 2024-02-04 | 2024-02-04 | 2024-03-13 | 2024-03-13 | 2024-02-16 | 2024-03-06 | 2024-03-07 |  | 2024-03-11
64 | HVDC-ADOPT-HE-0057 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 18975 | 104.4 | 104.4 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-20 | 2024-03-06 | 2024-03-08 | 2024-03-12
65 | HVDC-ADOPT-HE-0075 | E01 | 2024-02-04 | Hitachi | Elec | Main Converter | Single-phase converter reactor | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 6325 | 34.8 | 34.8 | 2024-02-04 | 2024-02-04 | 2024-03-06 | 2024-03-06 | 2024-02-22 | 2024-03-06 | 2024-03-08 | 2024-03-12
66 | HVDC-ADOPT-HE-0069 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Bottom Shield, Side Shield | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 23 | 0 | 5 | - |  |  |  | 26470 | 214.7 | 214.7 | 2024-01-30 | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-15 | 2024-03-14 | 2024-03-15 | 2024-03-23
67 | HVDC-ADOPT-HE-0070 | E01 | 2024-01-29 | Hitachi | Elec | Main Converter | Serpentine, Cooling media | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 10 | 0 | 1 | - |  |  |  | 3170 | 43.3 | 43.3 | 2024-01-30 | 2024-01-30 | 2024-03-13 | 2024-03-13 | 2024-03-15 | 2024-03-14 | 2024-03-15 |  |  |  |  | 2024-03-19
68 | HVDC-ADOPT-HE-0068-1 | E01 | 2024-02-08 | Hitachi | Elec | Main Converter | Layers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 15 | 0 | 5 | - |  |  |  | 75000 | 219.45 | 219.45 | 2024-02-08 | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-23 | 2024-03-20 | 2024-03-22 | 2025-03-19 |  |  |  | 2024-03-28
69 | HVDC-ADOPT-HE-0080-1 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Side Shields, Conductor (Part of Valve) | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 37 | 0 | 15 | - |  |  |  | 39347 | 393 | 393 | 2024-02-08 | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-02-21 | 2024-03-20 | 2024-03-22 | 2024-04-04
70 | HVDC-ADOPT-HE-0081 | E01 | 2024-02-08 | Hitachi | Elec | Main Converter | Layers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 30 | 0 | 10 | - |  |  |  | 150000 | 438.8 | 438.8 | 2024-02-08 | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-22 | 2024-03-20 | 2024-03-22 | 2025-03-19 |  |  |  | 2024-03-28
71 | HVDC-ADOPT-HE-0073 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Converter Reactors |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 8850 | 45.3 | 45.3 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-26 | 2024-03-14 | 2024-03-15 |  | 2024-03-20
72 | HVDC-ADOPT-HE-0078 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Converter Reactors |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 8850 | 45.3 | 45.3 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-26 | 2024-03-14 | 2024-03-15 |  | 2024-03-20
73 | HVDC-ADOPT-HE-0030 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Converter Reactors |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 24000 | 105.2 | 105.2 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-20 | 2024-03-15 | 2024-03-15 | [5 empty] | 2024-03-21
74 | HVDC-ADOPT-HE-0076 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Converter Reactors |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 24000 | 105.2 | 105.2 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-20 | 2024-03-15 | 2024-03-15 | [5 empty] | 2024-03-20
75 | HVDC-ADOPT-HE-0077 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Converter Reactors |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 24000 | 105.2 | 105.2 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-20 | 2024-03-15 | 2024-03-15 | [5 empty] | 2024-03-20
76 | HVDC-ADOPT-HE-0068-2 | E01 | 2024-02-08 | Hitachi | Elec | Main Converter | Layers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 21 | 0 | 7 | - |  |  |  | 105000 | 307.23 | 307.23 | 2024-02-10 | 2024-02-10 | 2024-03-27 | 2024-03-27 | 2024-02-21 | 2024-03-29 | 2024-03-29 | 2025-03-19 |  |  |  | 2024-04-15
77 | HVDC-ADOPT-HE-0080-2 | E01 | 2024-02-10 | Hitachi | Elec | Main Converter | Top Part Installation | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 3927 | 27.1 | 27.1 | 2024-02-10 | 2024-02-10 | 2024-03-27 | 2024-03-27 | 2024-02-21 | 2024-03-29 | 2024-03-30 | 2024-04-17
78 | HVDC-ADOPT-HE-0031 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Converter Reactors |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 24000 | 105.2 | 105.2 | 2024-02-15 | 2024-02-15 | 2024-03-19 | 2024-03-19 | 2024-02-20 | 2024-03-20 | 2024-03-22 | [5 empty] | 2024-03-27
79 | HVDC-ADOPT-HE-0055 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Top Part Installation | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 36 | 0 | 6 | - |  |  |  | 37440 | 469.3 | 469.3 | 2024-02-15 | 2024-02-15 | 2024-03-27 | 2024-03-27 | 2024-04-01 | 2024-03-28 | 2024-03-29 | 2024-04-23
80 | HVDC-ADOPT-HE-0082 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Serpentine, commissioning spare | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 1 | - |  |  |  | 1815 | 26 | 26 | 2024-02-15 | 2024-02-15 | 2024-03-27 | 2024-03-27 | 2024-02-22 | 2024-03-29 | 2024-03-30 |  |  |  |  | 2024-04-02
81 | HVDC-ADOPT-HE-0083 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Side Shields, Insulator | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 15 | 0 | 4 | - |  |  |  | 12110 | 117 | 117 | 2024-02-15 | 2024-02-15 | 2024-03-27 | 2024-03-27 | 2024-02-23 | 2024-03-28 | 2024-03-30 | 2024-04-17
82 | HVDC-ADOPT-HE-0084-1 | E01 | 2024-02-15 | Hitachi | Elec | Main Converter | Layers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 51 | 0 | 17 | - |  |  |  | 255000 | 746.02 | 746.02 | 2024-02-15 | 2024-02-15 | 2024-03-27 | 2024-03-27 | 2024-02-22 | 2024-03-28 | 2024-03-30 | 2025-03-19 |  |  |  | 2024-04-06
83 | HVDC-ADOPT-HE-0079 | E01 | 2024-02-20 | Hitachi | Elec | Main Converter | Converter Reactors Spare |  |  |  | O | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 12000 | 52.6 | 52.6 | 2024-02-20 | 2024-02-20 | 2024-03-27 | 2024-03-27 | 2024-02-26 | 2024-03-28 | 2024-03-30 | [5 empty] | 2024-04-04
84 | HVDC-ADOPT-HE-0032 | E01 | 2024-02-20 | Hitachi | Elec | Main Converter | Converter Reactors |  |  |  | O | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 12000 | 52.6 | 52.6 | 2024-02-20 | 2024-02-20 | 2024-03-27 | 2024-03-27 | 2024-02-26 | 2024-03-28 | 2024-03-30 | [5 empty] | 2024-04-04
85 | HVDC-ADOPT-HE-0084-2 | E01 | 2024-02-22 | Hitachi | Elec | Main Converter | Layers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 15000 | 43.9 | 43.9 | 2024-02-22 | 2024-02-22 | 2024-04-05 | 2024-04-05 | 2024-02-22 | 2024-04-08 | 2024-04-17 | 2025-03-19 |  |  |  | 2024-04-24
86 | HVDC-ADOPT-HE-0048 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 3316 | 20.12 | 20.12 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-22
87 | HVDC-ADOPT-HE-0050 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 12 | 0 | 1 | - |  |  |  | 10008 | 44.98 | 44.98 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-22
88 | HVDC-ADOPT-HE-0051 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 5310 | 52.44 | 52.44 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-22
89 | HVDC-ADOPT-HE-0049 | E01 | 2024-02-22 | Hitachi | Elec | Main Converter | Support Insulator Spare |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 253 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-22
90 | HVDC-ADOPT-HE-0052 | E01 | 2024-02-22 | Hitachi | Elec | Main Converter | Support Insulator Spare |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 256 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-22
91 | HVDC-ADOPT-HE-0044 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator Spare |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 253 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-15 |  | 2024-04-02
92 | HVDC-ADOPT-HE-0047 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator Spare |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 256 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-15 |  | 2024-04-02
93 | HVDC-ADOPT-HE-0046 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 4860 | 44.1 | 44.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-15 |  | 2024-04-02
94 | HVDC-ADOPT-HE-0043 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Corona Rings |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 3316 | 20.11 | 20.11 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-15 |  | 2024-04-02
95 | HVDC-ADOPT-HE-0045 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 12 | 0 | 1 | - |  |  |  | 10008 | 45 | 45 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-15 |  | 2024-04-02
96 | HVDC-ADOPT-HE-0039 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Spare Support Insulator | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 315 | 1.4 | 1.4 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-14 | 2024-03-15 | 2024-03-23
97 | HVDC-ADOPT-HE-0042 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Spare Support Insulator | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 256 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-14 | 2024-03-15 | 2024-03-23
98 | HVDC-ADOPT-HE-0038 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 2260 | 15.22 | 15.22 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-14 | 2024-03-15 | 2024-03-23
99 | HVDC-ADOPT-HE-0040 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 12 | 0 | 1 | - |  |  |  | 10008 | 44.88 | 44.88 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-14 | 2024-03-15 | 2024-03-26
100 | HVDC-ADOPT-HE-0041 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 4230 | 37.2 | 37.2 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-14 | 2024-03-15 | 2024-03-24
101 | HVDC-ADOPT-HE-0034 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Spare Support Insulator |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 315 | 1.4 | 1.4 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-21 |  |  |  | 2024-05-08
102 | HVDC-ADOPT-HE-0037 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Spare Support Insulator |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 256 | 1.1 | 1.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 |  |  | 2024-07-14 |  |  | 2024-03-21
103 | HVDC-ADOPT-HE-0033 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 2260 | 15.1 | 15.1 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 |  |  | 2024-08-24 |  |  | 2024-03-21 |  |  |  | 2024-05-08
104 | HVDC-ADOPT-HE-0035 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 12 | 0 | 1 | - |  |  |  | 10008 | 44.88 | 44.88 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 |  |  | 2024-11-26 |  |  | 2024-03-21 |  |  |  | 2024-05-14
105 | HVDC-ADOPT-HE-0036 | E01 | 2024-02-09 | Hitachi | Elec | Main Converter | Support Insulator, Corona Rings |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 5250 | 51.3 | 51.3 | 2024-02-09 | 2024-02-09 | 2024-03-13 | 2024-03-13 | 2024-02-29 | 2024-03-15 | 2024-03-18 | [5 empty] | 2024-03-21
106 | HVDC-ADOPT-HE-0085 | E01 | 2024-02-23 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  |  | O |  | DAP | BRAZIL | Itaguai | Mina Zayed | BBC | Scan Global Logistics AB | B | 47 | 0 | 0 | - | 47 |  |  | 543257 | 713.95 | 713.95 | 2024-02-23 | 2024-02-23 | 2024-04-12 | 2024-04-12 | 2024-03-22 | 2024-04-03 | 2024-04-04 |  |  |  |  | 2024-04-19 | 2024-04-19 |  |  |  | 2024-04-26
107 | HVDC-ADOPT-HE-0088 | E01 | 2024-02-20 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  | O |  |  | DAP | SWEDEN | Norrkoping | Mina Zayed | BBC | Scan Global Logistics AB | B | 49 | 0 | 0 | - | 49 |  |  | 412188 | 798.91 | 798.91 | 2024-02-19 | 2024-02-19 | 2024-04-20 | 2024-04-20 | 2024-04-13 | 2024-04-06 | 2024-04-12 |  |  | 2025-02-06 |  |  | 2024-04-21
108 | HVDC-ADOPT-HE-0089 | E01 | 2024-02-20 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  | O |  |  | DAP | SWEDEN | Norrkoping | Mina Zayed | BBC | Scan Global Logistics AB | B | 4 | 0 | 0 | - | 4 |  |  | 4024 | 41.72 | 41.72 | 2024-02-19 | 2024-02-19 | 2024-04-20 | 2024-04-20 | 2024-04-13 | 2024-04-06 | 2024-04-12 |  |  |  |  | 2024-04-26 |  |  |  |  | 2024-04-26
109 | HVDC-ADOPT-HE-0087 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | AC Current Transformer |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 1 | - |  |  |  | 3420 | 11.89 | 11.89 | 2024-02-29 | 2024-02-29 | 2024-04-15 | 2024-04-15 | 2024-03-11 | 2024-04-17 | 2024-04-18 | [5 empty] | 2024-04-20
110 | HVDC-ADOPT-HE-0090 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | AC Current Transformer |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1100 | 3.96 | 3.96 | 2024-02-29 | 2024-02-29 | 2024-04-15 | 2024-04-15 | 2024-03-11 | 2024-04-17 | 2024-04-18 | [5 empty] | 2024-04-20
111 | HVDC-ADOPT-HE-0091 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | AC Current Transformer Spare |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 570 | 1.98 | 1.98 | 2024-02-29 | 2024-02-29 | 2024-04-15 | 2024-04-15 | 2024-03-11 | 2024-04-17 | 2024-04-18 |  |  | 2024-11-26 |  |  | 2024-04-20
112 | HVDC-ADOPT-HE-0092 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | AC Current Transformer Spare |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 750 | 1.98 | 1.98 | 2024-02-29 | 2024-02-29 | 2024-04-15 | 2024-04-15 | 2024-03-11 | 2024-04-17 | 2024-04-18 | [5 empty] | 2024-04-20
113 | HVDC-ADOPT-HE-0103 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | AC Current Transformer |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 2200 | 7.93 | 7.93 | 2024-02-29 | 2024-02-29 | 2024-05-04 | 2024-05-04 | 2024-03-11 | 2024-05-06 | 2024-05-08 | [5 empty] | 2024-06-06
114 | HVDC-ADOPT-HE-0104 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | Converter AC Bus |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 12 | 0 | 0 | - |  |  |  | 4110 | 20.51 | 20.51 | 2024-02-29 | 2024-02-29 | 2024-05-04 | 2024-05-04 | 2024-03-11 | 2024-05-06 | 2024-05-08 | [9 empty] | 2024-06-06
115 | HVDC-ADOPT-HE-0105 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | Converter AC Bus Spare |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 685 | 3.42 | 3.42 | 2024-02-29 | 2024-02-29 | 2024-05-04 | 2024-05-04 | 2024-03-11 | 2024-05-06 | 2024-05-08 | [9 empty] | 2024-06-06
116 | HVDC-ADOPT-HE-0106 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | Converter AC Bus |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 12 | 0 | 1 | - |  |  |  | 4110 | 20.51 | 20.51 | 2024-02-29 | 2024-02-29 | 2024-05-04 | 2024-05-04 | 2024-03-11 | 2024-05-06 | 2024-05-08 | [9 empty] | 2024-06-10
117 | HVDC-ADOPT-HE-0107 | E01 | 2024-02-29 | Hitachi | Elec | Main Converter | Converter AC Bus Spare |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 685 | 3.42 | 3.42 | 2024-02-29 | 2024-02-29 | 2024-05-04 | 2024-05-04 | 2024-03-11 | 2024-05-06 | 2024-05-08 | [9 empty] | 2024-06-10
118 | HVDC-ADOPT-HE-0101 | E01 | 2024-03-14 | Hitachi | Elec | Main Converter | Optical Transducer |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 16 | 0 | 1 | - |  |  |  | 3920 | 25.79 | 25.79 | 2024-03-14 | 2024-03-14 | 2024-05-04 | 2024-05-04 | 2024-03-14 | 2024-05-09 | 2024-05-09 |  |  |  |  | 2024-05-11 | 2024-05-11
119 | HVDC-ADOPT-HE-0102 | E01 | 2024-03-14 | Hitachi | Elec | Main Converter | Optical Transducer (Spare) | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 20 | 0 | 0 | - |  |  |  | 2748 | 18.08 | 18.08 | 2024-03-14 | 2024-03-14 | 2024-05-04 | 2024-05-04 | 2024-03-14 | 2024-05-09 | 2024-05-09 |  |  |  |  | 2024-05-11
120 | HVDC-ADOPT-HE-0108 | E01 | 2024-03-18 | Hitachi | Elec | Main Converter | RC Voltage Divider | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 54 | 0 | 9 | - |  |  |  | 40740 | 323.9 | 323.9 | 2024-03-10 | 2024-03-10 | 2024-04-15 | 2024-04-15 | 2024-03-21 | 2024-04-17 | 2024-04-18 |  |  |  |  | 2024-05-01
121 | HVDC-ADOPT-HE-0109 | E01 | 2024-03-21 | Hitachi | Elec | Main Converter | RC Voltage Divider, Corona Ring Spare | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 9 | 0 | 1 | - |  |  |  | 4670 | 37.1 | 37.1 | 2024-03-10 | 2024-03-10 | 2024-04-15 | 2024-04-15 | 2024-03-21 | 2024-04-17 | 2024-04-18 |  |  |  |  | 2024-04-22
122 | HVDC-ADOPT-PPL-0014 | E02 | 2024-03-14 | Prysmian | Elec | 320kV HVDC Cable System | Minisub FOC Subsea Fiber Optic Cable (up to 96 fibres) |  |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Trans Global | C | 1 | 1 | 0 | - |  |  |  | 8045 | 21.55 | 21.55 | 2024-03-29 | 2024-03-29 | 2024-05-06 | 2024-05-06 | 2024-04-12 | 2024-05-06 | 2024-05-07 | [7 empty] | 2024-05-08
123 | HVDC-ADOPT-HE-0110 | E01 | 2024-03-29 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  |  | O |  | DAP | BRAZIL | Itaguai | Mina Zayed | BBC | Scan Global Logistics AB | B | 48 | 0 | 0 | - |  |  |  | 546212 | 736.03 | 736.03 | 2024-04-01 | 2024-04-01 | 2024-05-09 | 2024-05-09 | 2024-04-13 | 2024-05-07 | 2024-05-08 |  |  |  |  | 2024-05-10 | 2024-06-09
124 | HVDC-ADOPT-HE-0116 | E01 | 2024-04-09 | Hitachi | Elec | Main Converter | Transformer Units & Accessories | O |  |  |  | DAP | SWEDEN | Uddelvalla | Mugharraq | BBC | Scan Global Logistics AB | B | 95 | 0 | 0 | - |  |  |  | 926998 | 1436.98 | 1436.98 | 2024-04-02 | 2024-04-02 | 2024-05-23 | 2024-05-23 | 2024-04-15 | 2024-05-22 | 2024-05-23 | 2025-01-16 |  |  |  | 2024-05-23 | 2024-06-13
125 | HVDC-ADOPT-HE-0093 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Single Phase Current Limiting Reactors, Supprt Insulator | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 17 | 0 | 1 | - |  |  |  | 7306 | 41.88 | 41.88 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-07 | [5 empty] | 2024-05-10
126 | HVDC-ADOPT-HE-0094 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Single Phase Current Limiting Reactors, Supprt Insulator | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 889 | 5.93 | 5.93 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-07 | [5 empty] | 2024-05-10
127 | HVDC-ADOPT-HE-0095 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Single Phase Current Limiting Reactors, Supprt Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 3338 | 18.6 | 18.6 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-08 | 2024-06-15
128 | HVDC-ADOPT-HE-0096 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Single Phase Current Limiting Reactors, Supprt Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 447 | 3.2 | 3.2 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-08 | 2024-06-15
129 | HVDC-ADOPT-HE-0097 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Single Phase Current Limiting Reactors, Supprt Insulator |  |  | O |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 1624 | 18.6 | 18.6 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-08 |  | 2024-06-12
130 | HVDC-ADOPT-HE-0098 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Single Phase Current Limiting Reactors, Supprt Insulator |  |  | O |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 517 | 2.79 | 2.79 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-15 | 2024-05-06 | 2024-05-08 |  | 2024-06-12
131 | HVDC-ADOPT-HE-0115 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Single Phase HVDC Filter Reactors |  |  | O |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 5204 | 56.88 | 56.88 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-07 | 2024-05-08 |  | 2024-06-12
132 | HVDC-ADOPT-HE-0117 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 118 | 0.22 | 0.22 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-07 | 2024-05-08 | 2024-06-15
133 | HVDC-ADOPT-HE-0120 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Insulator |  |  | O |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 3840 | 5.93 | 5.93 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-06 | 2024-05-08 |  | 2024-06-12
134 | HVDC-ADOPT-HE-0121 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Single Phase HVDC Filter Reactors, Insulator |  |  | O |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 789 | 6.58 | 6.58 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-06 | 2024-05-08 |  | 2024-06-12
135 | HVDC-ADOPT-HE-0123 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Spare Single Phase HVDC Filter Reactors, Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 609 | 4.8 | 4.8 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-06 | 2024-05-08 | 2024-06-15
136 | HVDC-ADOPT-HE-0122 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Single Phase HVDC Filter Reactors, Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 8468 | 54.2 | 54.2 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-06 | 2024-05-08 | 2024-06-15
137 | HVDC-ADOPT-HE-0124 | E01 | 2024-03-27 | Hitachi | Elec | Main Converter | Commutating DC Switches, Insulator | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 185 | 1.16 | 1.16 | 2024-03-27 | 2024-03-27 | 2024-05-04 | 2024-05-04 | 2024-04-18 | 2024-05-06 | 2024-05-08 | 2024-06-15
138 | HVDC-ADOPT-HE-0099 | E01 | 2024-04-30 | Hitachi | Elec | Main Converter | DC Cables Discharger Resistor | O |  |  |  | DAP | SWEDEN | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 2760 | 38.9 | 38.9 | 2024-04-30 | 2024-04-30 | 2024-06-07 | 2024-06-07 | 2024-05-20 | 2024-06-08 | 2024-06-11 |  |  |  |  | 2024-06-14
139 | HVDC-ADOPT-HE-0100 | E01 | 2024-04-30 | Hitachi | Elec | Main Converter | Spare DC Cables Discharger Resistor, Composite Insulator | O |  |  |  | DAP | SWEDEN | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1375 | 19.63 | 19.63 | 2024-04-30 | 2024-04-30 | 2024-06-07 | 2024-06-07 | 2024-05-19 | 2024-06-08 | 2024-06-11 |  |  |  |  | 2024-06-14
140 | HVDC-ADOPT-HE-0114 | E01 | 2024-04-30 | Hitachi | Elec | Main Converter | Single Phase Filter Reactor | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 8 | 0 | 2 | - |  |  |  | 13108 | 139.81 | 139.81 | 2024-04-30 | 2024-04-30 | 2024-06-07 | 2024-06-07 | 2024-05-19 | 2024-06-08 | 2024-06-11 | [5 empty] | 2024-06-14
141 | HVDC-ADOPT-HE-0118 | E01 | 2024-04-30 | Hitachi | Elec | Main Converter | Insulator | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 9910 | 13.57 | 13.57 | 2024-04-30 | 2024-04-30 | 2024-06-07 | 2024-06-07 | 2024-05-20 | 2024-06-08 | 2024-06-11 | [5 empty] | 2024-06-13
142 | HVDC-ADOPT-HE-0119 | E01 | 2024-04-30 | Hitachi | Elec | Main Converter | Spare Single Phase HVDC Filter Reactor, Insulator | O | O | O | O | DAP | GERMANY | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 2105 | 20.94 | 20.94 | 2024-04-30 | 2024-04-30 | 2024-06-07 | 2024-06-07 | 2024-05-20 | 2024-06-08 | 2024-06-11 | [5 empty] | 2024-06-13
143 | HVDC-ADOPT-HE-0111 | E01 | 2024-05-02 | Hitachi | Elec | Main Converter | Sheilds, Conductor, Holders, Pipes, Insulator |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 84 | 0 | 19 | - |  |  |  | 76822 | 952.07 | 952.07 | 2024-05-02 | 2024-05-02 | 2024-06-09 | 2024-06-09 | 2024-05-20 | 2024-06-08 | 2024-06-11 |  | 2024-06-28
144 | HVDC-ADOPT-HE-0112 | E01 | 2024-05-02 | Hitachi | Elec | Main Converter | Serpentine, Light Guides, Cooling, Draining |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 56 | 0 | 6 | - |  |  |  | 16234 | 231.43 | 231.43 | 2024-05-02 | 2024-05-02 | 2024-06-09 | 2024-06-09 | 2024-05-20 | 2024-06-08 | 2024-06-11 |  |  |  |  | 2024-06-13
145 | HVDC-ADOPT-HE-0125 | E01 | 2024-05-02 | Hitachi | Elec | Main Converter | Wallbushings | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 38 | 0 | 12 | - |  |  |  | 34920 | 256.77 | 256.77 | 2024-05-02 | 2024-05-02 | 2024-06-09 | 2024-06-09 | 2024-05-20 | 2024-06-08 | 2024-06-11 | 2024-06-25
146 | HVDC-ADOPT-HE-0126 | E01 | 2024-05-02 | Hitachi | Elec | Main Converter | Spare Wallbushings | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 5070 | 37.2 | 37.2 | 2024-05-02 | 2024-05-02 | 2024-06-09 | 2024-06-09 | 2024-05-20 | 2024-06-08 | 2024-06-11 | 2024-06-25
147 | HVDC-ADOPT-SIM-0002 | E04-1 | 2024-03-20 | Siemens | Elec | 400kV and 132kV New Converter GIS | High Voltage Surge Arrestor | O |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | DANMAR LINES | C | 8 | 0 | 1 | - |  |  |  | 6725 | 34.56 | 34.56 | 2024-05-04 | 2024-05-04 | 2024-06-10 | 2024-06-10 | 2024-05-28 | 2024-06-13 | 2024-06-14 | 2024-06-24 | 2024-06-24
148 | HVDC-ADOPT-HE-0113 | E01 | 2024-05-09 | Hitachi | Elec | Main Converter | Top Part Installation |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 48 | 0 | 8 | - |  |  |  | 49920 | 625.66 | 625.66 | 2024-05-09 | 2024-05-09 | 2024-06-18 | 2024-06-18 | 2024-05-20 | 2024-06-19 | 2024-06-20 |  | 2024-07-03
149 | HVDC-ADOPT-HE-0145 | E01 | 2024-05-09 | Hitachi | Elec | Main Converter | Sheilds, Pipes, Connector, Corona Rings |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 78 | 0 | 16 | - |  |  |  | 58101 | 474.45 | 474.45 | 2024-05-09 | 2024-05-09 | 2024-06-18 | 2024-06-18 | 2024-05-20 | 2024-06-20 | 2024-06-21 |  | 2024-07-12
150 | HVDC-ADOPT-HE-0142 | E01 | 2024-05-09 | Hitachi | Elec | Main Converter | Layers |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 30 | 0 | 10 | - |  |  |  | 150000 | 438.83 | 438.83 | 2024-05-09 | 2024-05-09 | 2024-06-18 | 2024-06-18 | 2024-05-20 | 2024-06-20 | 2024-06-21 |  |  |  |  | 2024-06-29
151 | HVDC-ADOPT-HE-0146 | E01 | 2024-05-09 | Hitachi | Elec | Main Converter | Layers |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 72 | 0 | 24 | - |  |  |  | 360000 | 1053.22 | 1053.22 | 2024-05-09 | 2024-05-09 | 2024-06-18 | 2024-06-18 | 2024-06-20 | 2024-06-19 | 2024-06-20 |  |  |  |  | 2024-06-27
152 | HVDC-ADOPT-SEI-0003 | E03 | 2024-05-30 | Sumitomo | Elec | 400kV HVDC Cable System | DAS Land and Spare Cable |  | O |  |  | CIF | JAPAN | Kobe | Khalifa port | K Line |  | B | 7 | 0 | 0 | - |  |  |  | 160605 | 270.72 | 270.72 | 2024-05-06 | 2024-05-06 | 2024-06-20 | 2024-06-20 | 2024-06-18 | 2024-06-20 | 2024-06-22 | [7 empty] | 2024-06-28
153 | HVDC-ADOPT-HE-0128 | E01 | 2024-05-17 | Hitachi | Elec | Main Converter | Wallbushings, Corona Shields Spare |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 2925 | 22 | 22 | 2024-05-17 | 2024-05-17 | 2024-06-25 | 2024-06-25 | 2024-06-13 | 2024-06-24 | 2024-06-25 |  |  | 2024-11-26 |  |  | 2024-07-03
154 | HVDC-ADOPT-HE-0127-1 | E01 | 2024-05-17 | Hitachi | Elec | Main Converter | Wallbushings, Corona Shields |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 41 | 0 | 7 | - |  |  |  | 38750 | 285.31 | 285.31 | 2024-05-17 | 2024-05-17 | 2024-06-25 | 2024-06-25 | 2024-06-13 | 2024-06-24 | 2024-06-25 |  |  | 2024-11-26 |  |  | 2024-07-04
155 | HVDC-ADOPT-HE-0153-1 | E01 | 2024-05-17 | Hitachi | Elec | Main Converter | Layers |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 18 | 0 | 6 | - |  |  |  | 90000 | 263.3 | 263.3 | 2024-05-17 | 2024-05-17 | 2024-06-25 | 2024-06-25 | 2024-06-27 | 2024-06-24 | 2024-06-25 |  |  |  |  | 2024-07-01
156 | HVDC-ADOPT-HE-0154-1 | E01 | 2024-05-17 | Hitachi | Elec | Main Converter | Bus bars, Side shields, Insulators, Pipes |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 43 | 0 | 18 | - |  |  |  | 40905 | 427.96 | 427.96 | 2024-05-17 | 2024-05-17 | 2024-06-25 | 2024-06-25 | 2024-06-13 | 2024-06-24 | 2024-06-25 |  | 2024-07-16
157 | HVDC-ADOPT-HE-0155 | E01 | 2024-05-23 | Hitachi | Elec | Main Converter | Layers |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 63 | 0 | 21 | - |  |  |  | 315000 | 921.56 | 921.56 | 2024-05-23 | 2024-05-23 | 2024-07-03 | 2024-07-03 | 2024-05-28 | 2024-07-03 | 2024-07-05 |  |  |  |  | 2024-07-15
158 | HVDC-ADOPT-HE-0156 | E01 | 2024-05-23 | Hitachi | Elec | Main Converter | Assembly Material, Studs, Poles, Routing |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 28 | 0 | 2 | - |  |  |  | 19068 | 53.3 | 53.3 | 2024-05-23 | 2024-05-23 | 2024-07-03 | 2024-07-03 | 2024-07-08 | 2024-07-03 | 2024-07-05 |  | 2027-07-23
159 | HVDC-ADOPT-HE-0157 | E01 | 2024-05-23 | Hitachi | Elec | Main Converter | Bus Bars, Cooling, Channels |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 1 | - |  |  |  | 3912 | 18.58 | 18.58 | 2024-05-23 | 2024-05-23 | 2024-07-03 | 2024-07-03 | 2024-05-28 | 2024-07-03 | 2024-07-05 |  |  |  |  | 2024-07-10
160 | HVDC-ADOPT-HE-0158 | E01 | 2024-05-23 | Hitachi | Elec | Main Converter | Wallbushings, Corona Shields |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 1 | - |  |  |  | 4160 | 31.3 | 31.3 | 2024-05-23 | 2024-05-23 | 2024-07-03 | 2024-07-03 | 2024-07-08 | 2024-07-04 | 2024-07-06 | [5 empty] | 2024-07-11
161 | HVDC-ADOPT-HE-0159 | E01 | 2024-05-23 | Hitachi | Elec | Main Converter | Wallbushings, Corona Shields Spare |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1930 | 14 | 14 | 2024-05-23 | 2024-05-23 | 2024-07-03 | 2024-07-03 | 2024-05-28 | 2024-07-04 | 2024-07-06 | [5 empty] | 2024-07-11
162 | HVDC-ADOPT-HE-0153-2 | E01 | 2024-05-19 | Hitachi | Elec | Main Converter | Layers |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 33 | 0 | 11 | - |  |  |  | 165000 | 482.72 | 482.72 | 2024-05-19 | 2024-05-19 | 2024-07-03 | 2024-07-03 | 2024-06-14 | 2024-07-03 | 2024-07-05 |  |  |  |  | 2024-07-09
163 | HVDC-ADOPT-HE-0154-2 | E01 | 2024-05-19 | Hitachi | Elec | Main Converter | Side Shields |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 10 | 0 | 5 | - |  |  |  | 10310 | 120.54 | 120.54 | 2024-05-19 | 2024-05-19 | 2024-07-03 | 2024-07-03 | 2024-06-14 | 2024-07-04 | 2024-07-06 |  | 2024-07-17
164 | HVDC-ADOPT-HE-0127-2 | E01 | 2024-05-19 | Hitachi | Elec | Main Converter | Wallbushings, Corona Shields |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 9 | 0 | 2 | - |  |  |  | 10370 | 75.77 | 75.77 | 2024-05-19 | 2024-05-19 | 2024-07-03 | 2024-07-03 | 2024-06-18 | 2024-07-03 | 2024-07-05 |  |  | 2025-05-04 |  |  | 2024-07-08
165 | HVDC-ADOPT-SCT-0003 | E08 | 2024-05-22 | Dong Yang | Elec | Cathodic Protection | Cathodic Protection Systems (2nd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port |  |  | C | 12 | 0 | 1 | - |  |  |  | 4105 | 16.98 | 16.98 | 2024-05-22 | 2024-05-22 | 2024-07-04 | 2024-07-04 | 2024-05-28 | 2024-07-03 | 2024-07-04 | 2024-08-07 |  | 2024-07-14 |  |  | 2024-07-09 |  |  |  | 2024-07-09
166 | HVDC-ADOPT-HE-0143 | E01 | 2024-05-13 | Hitachi | Elec | Main Converter | Transformer Units & Accessories | O |  |  |  | DAP | SWEDEN | Uddelvalla | Mugharraq | BBC | Scan Global Logistics AB | B | 60 | 0 | 0 | - |  |  |  | 684952 | 993.82 | 993.82 | 2024-05-06 | 2024-05-06 | 2024-07-21 | 2024-07-21 | 2024-05-20 | 2024-07-15 | 2024-07-17 |  |  |  |  | 2024-07-21
167 | HVDC-ADOPT-HE-0144 | E01 | 2024-05-13 | Hitachi | Elec | Main Converter | Transformer Units & Accessories | O |  |  |  | DAP | SWEDEN | Uddelvalla | Mugharraq | BBC | Scan Global Logistics AB | B | 7 | 0 | 0 | - |  |  |  | 6071 | 62.83 | 62.83 | 2024-05-06 | 2024-05-06 | 2024-07-21 | 2024-07-21 | 2024-05-20 | 2024-07-15 | 2024-07-17 | 2025-01-03
168 | HVDC-ADOPT-SCT-0004 | M01 | 2024-06-04 | Excellift | Mech | Crane and Hoist | Crane and Hoist (2nd) | O |  |  | O | FOB | MALAYSIA | Port Klang | Khalifa port |  |  | C | 13 | 0 | 2 | - |  |  |  | 7122 | 27.47 | 27.47 | 2024-06-21 | 2024-06-21 | 2024-07-19 | 2024-07-19 | 2024-07-03 | 2024-07-23 | 2024-07-23 | 2024-07-30 |  |  | 2024-08-14
169 | HVDC-ADOPT-SCT-0005 | E08 | 2024-06-01 | TaeHwa | Elec | Cable Tray System | Cable Tray System (1st) |  | O |  | O | FOB | KOREA | Busan Port | Khalifa port |  |  | C | 37 | 0 | 7 | - |  |  |  | 85147 | 392.11 | 392.11 | 2024-06-01 | 2024-06-01 | 2024-07-18 | 2024-07-18 | 2024-06-11 | 2024-07-19 | 2024-07-19 |  |  | 2024-08-28 | [6 empty] | 2024-08-26
170 | HVDC-ADOPT-HE-0160 | E01 | 2024-05-30 | Hitachi | Elec | Main Converter | Layers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 39 | 0 | 13 | - |  |  |  | 195000 | 570.48 | 570.48 | 2024-05-30 | 2024-05-30 | 2024-07-11 | 2024-07-11 | 2024-07-13 | 2024-07-11 | 2024-07-12 |  |  |  |  | 2024-07-17
171 | HVDC-ADOPT-HE-0162 | E01 | 2024-06-06 | Hitachi | Elec | Main Converter | Layers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 51 | 0 | 17 | - |  |  |  | 255000 | 746.03 | 746.03 | 2024-06-06 | 2024-06-06 | 2024-07-17 | 2024-07-17 | 2024-07-21 | 2024-07-18 | 2024-07-19 |  |  |  |  | 2024-07-27
172 | HVDC-ADOPT-HE-0163 | E01 | 2024-06-06 | Hitachi | Elec | Main Converter | Insulators, serpentine, side shields |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 56 | 0 | 8 | - |  |  |  | 26538 | 281.41 | 281.41 | 2024-06-06 | 2024-06-06 | 2024-07-17 | 2024-07-17 | 2024-06-13 | 2024-07-18 | 2024-07-19 |  |  |  |  | 2024-07-27 | 2024-07-27
173 | HVDC-ADOPT-SEI-0005 | E03 | 2024-06-06 | Sumitomo | Elec | 400kV HVDC Cable System | Fiber Optic Subsea Cable |  | O |  |  | CIF | Norway | Rognan | Mina Zayed |  | BIMCO | B | 4 | 0 | 0 | - |  |  |  | 496254 | 575.35 | 575.35 | 2024-06-06 | 2024-06-06 | 2024-07-15 | 2024-07-15 | 2024-06-21 | 2024-07-12 | 2024-07-12 | [7 empty] | 2024-07-25
174 | HVDC-ADOPT-HE-0135 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer Spare | O |  |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 1 | - |  |  |  | 668 | 2.1 | 2.1 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-21 | 2024-07-11 | 2024-07-12 | 2024-07-28
175 | HVDC-ADOPT-HE-0134 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer | O |  |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 1268 | 3.8 | 3.8 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-21 | 2024-07-11 | 2024-07-12 | 2024-07-28
176 | HVDC-ADOPT-HE-0138 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer | O | O | O | O | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 1206 | 2.3 | 2.3 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-21 | 2024-07-11 | 2024-07-12 |  |  | 2025-05-04 |  |  | 2024-07-31
177 | HVDC-ADOPT-HE-0139 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer Spare | O | O | O | O | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 500 | 1.3 | 1.3 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-23 | 2024-07-11 | 2024-07-12 | [5 empty] | 2024-07-31
178 | HVDC-ADOPT-HE-0136 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer |  |  | O |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 653 | 1.11 | 1.11 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-23 | 2024-07-11 | 2024-07-12 |  | 2024-07-23
179 | HVDC-ADOPT-HE-0137 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Outdoor Current Transformer Spare |  |  | O |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 190 | 0.49 | 0.49 | 2024-06-08 | 2024-06-08 | 2024-07-11 | 2024-07-11 | 2024-06-23 | 2024-07-11 | 2024-07-12 |  | 2024-07-23
180 | HVDC-ADOPT-SCT-0007 | M01 | 2024-06-18 | Excellift | Mech | Crane and Hoist | Crane and Hoist (3rd) |  |  | O | O | FOB | MALAYSIA | Port Klang | Khalifa port | Maersk |  | C | 15 | 0 | 2 | - |  |  |  | 9192 | 32.51 | 32.51 | 2024-06-29 | 2024-06-29 | 2024-07-19 | 2024-07-19 | 2024-07-03 | 2024-07-23 | 2024-07-23 |  | 2024-07-30 | [7 empty] | 2024-07-30
181 | HVDC-ADOPT-SCT-0008 | M01 | 2024-06-04 | Excellift | Mech | Crane and Hoist | Crane and Hoist (4th) |  |  | O | O | FOB | MALAYSIA | Port Klang | Khalifa port |  |  | C | 5 | 0 | 2 | - |  |  |  | 9300 | 38.78 | 38.78 | 2024-06-28 | 2024-06-28 | 2024-07-25 | 2024-07-25 | 2024-07-10 | 2024-07-25 | 2024-07-26 |  | 2024-07-30
182 | HVDC-ADOPT-SEI-0004-1 | E03 | 2024-06-19 | Sumitomo | Elec | 400kV HVDC Cable System | DC400kv Subsea Cable |  |  |  |  | CIF | JAPAN | Hitachi | Mina Zayed |  |  | B | 3 | 0 | 0 | - |  |  |  | 5475234 | 4479.9 | 5475.23 | 2024-06-19 | 2024-06-19 | 2024-07-10 | 2024-07-10 | 2024-07-02 | 2024-07-05 | 2024-07-07 | [7 empty] | 2024-08-13
183 | HVDC-ADOPT-SEI-0004-2 | E03 | 2024-06-19 | Sumitomo | Elec | 400kV HVDC Cable System | Frame & Slope of Static Tank |  |  |  |  | CIF | JAPAN | Hitachi | Mina Zayed |  |  | B | 3 | 0 | 0 | - |  |  |  | 88155.2 | 347.3 | 347.3 | 2024-06-19 | 2024-06-19 | 2024-07-10 | 2024-07-10 | 2024-07-02 | 2024-07-05 | 2024-07-07 | [7 empty] | 2024-08-13
184 | HVDC-ADOPT-HE-0161 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  |  | O |  | DAP | BRAZIL | Itaguai | Mina Zayed | BBC | Scan Global Logistics AB | B | 77 | 0 | 0 | - |  |  |  | 822875 | 1136.2 | 1136.2 | 2024-06-13 | 2024-06-13 | 2024-07-30 | 2024-07-30 | 2024-07-23 | 2024-07-22 | 2024-07-23 |  | 2024-09-08
185 | HVDC-ADOPT-HE-0130 | E01 | 2024-06-18 | Hitachi | Elec | Main Converter | DC Neutral Earthing Resistor,Insulators and Terminals | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1515 | 17.08 | 17.08 | 2024-06-18 | 2024-06-18 | 2024-07-23 | 2024-07-23 | 2024-07-12 | 2024-07-23 | 2024-07-24 |  |  |  |  | 2024-07-27
186 | HVDC-ADOPT-HE-0131 | E01 | 2024-06-18 | Hitachi | Elec | Main Converter | Spare DC Neutral Earthing Resistor,Insulators and Terminals | O |  |  |  | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1515 | 17.08 | 17.08 | 2024-06-18 | 2024-06-18 | 2024-07-23 | 2024-07-23 | 2024-07-12 | 2024-07-23 | 2024-07-24 |  |  |  |  | 2024-07-27
187 | HVDC-ADOPT-HE-0132 | E01 | 2024-06-18 | Hitachi | Elec | Main Converter | DC Neutral Earthing Resistor,Insulators and Terminals |  | O |  |  | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 4030 | 48.8 | 48.8 | 2024-06-18 | 2024-06-18 | 2024-07-23 | 2024-07-23 | 2024-07-12 | 2024-07-23 | 2024-07-24 |  |  |  |  | 2024-07-27
188 | HVDC-ADOPT-HE-0133 | E01 | 2024-06-18 | Hitachi | Elec | Main Converter | Spare DC Neutral Earthing Resistor,Insulators and Terminals |  | O |  |  | DAP | GERMANY | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 2015 | 24.4 | 24.4 | 2024-06-18 | 2024-06-18 | 2024-07-23 | 2024-07-23 | 2024-07-12 | 2024-07-23 | 2024-07-24 |  |  |  |  | 2024-07-27
189 | HVDC-ADOPT-SCT-0006 | E08 | 2024-06-19 | TaeHwa | Elec | Cable Tray System | Cable Tray System (2nd) | O |  | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM |  | C | 38 | 1 | 7 | - |  |  |  | 84803 | 369.36 | 369.36 | 2024-06-19 | 2024-06-19 | 2024-07-30 | 2024-07-30 | 2024-06-21 | 2024-07-30 | 2024-07-30 | 2024-08-12 | 2024-08-12
190 | HVDC-ADOPT-SEI-0007 | E03 | 2024-07-31 | Sumitomo | Elec | 400kV HVDC Cable System | Repair Joint (2nd) |  |  |  |  | CIP | JAPAN | Osaka | Abu Dhabi Airport |  |  | A | 9 | 0 | 0 | - |  |  |  | 42 | 0.27 | 0.27 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-08-01 | 2024-08-01 | [8 empty] | 2024-08-03
191 | HVDC-ADOPT-HE-0151 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Spare Mobile Arm & Fixed Contact |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 336 | 1.7 | 1.7 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-14 | 2024-08-04 | 2024-08-05 |  | 2024-08-22
192 | HVDC-ADOPT-HE-0149 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 10 | 0 | 1 | - |  |  |  | 7625 | 25.8 | 25.8 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-14 | 2024-08-04 | 2024-08-05 |  | 2024-08-22
193 | HVDC-ADOPT-HE-0150 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1437 | 7.6 | 7.6 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-13 | 2024-08-04 | 2024-08-05 |  |  |  |  | 2024-08-06
194 | HVDC-ADOPT-HE-0152 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Spare n°1 OP. MECHANISM |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 230 | 1.1 | 1.1 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-14 | 2024-08-04 | 2024-08-05 |  |  |  |  | 2024-08-07
195 | HVDC-ADOPT-HE-0148 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | Spare n° 6 Singlepole DSC STA 145 kV, 1 OP. MECHANISM | O | O | O | O | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 1032 | 4.73 | 4.73 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-14 | 2024-08-04 | 2024-08-05 |  |  |  |  | 2024-08-07 | 2024-08-07
196 | HVDC-ADOPT-HE-0147 | E01 | 2024-06-08 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator | O | O | O | O | DAP | Italy | Venezia | Khalifa port | MAERSK | Scan Global Logistics AB | C | 18 | 0 | 1 | - |  |  |  | 14307 | 45.9 | 45.9 | 2024-06-08 | 2024-06-08 | 2024-08-04 | 2024-08-04 | 2024-06-19 | 2024-08-04 | 2024-08-05 |  |  |  |  | 2024-08-07 | 2024-08-07
197 | HVDC-ADOPT-HE-0141 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Serpentine, insulators, shields, conductors |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 41 | 0 | 7 | - |  |  |  | 28480 | 325.28 | 325.28 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-09-03 | 2024-09-03
198 | HVDC-ADOPT-HE-0140 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Layers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 48 | 0 | 16 | - |  |  |  | 240000 | 702.13 | 702.13 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-08-15
199 | HVDC-ADOPT-HE-0164 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Set of frame, poles & T-breaking unit | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 14 | 0 | 3 | - |  |  |  | 6940 | 36.53 | 36.53 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-16 | 2024-08-07 | 2024-08-07 | 2024-09-01
200 | HVDC-ADOPT-HE-0168 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Frame Parts and Poles | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 12 | 0 | 0 | - |  |  |  | 6340 | 29.7 | 29.7 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-16 | 2024-08-07 | 2024-08-07 | 2024-08-29
201 | HVDC-ADOPT-HE-0172 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Corona Ring | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 28 | 0.34 | 0.34 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-16 | 2024-08-07 | 2024-08-07 | 2024-08-29
202 | HVDC-ADOPT-HE-0167 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Set of frame, poles & T-breaking unit Spare | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 2900 | 14.9 | 14.9 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-12 | 2024-08-07 | 2024-08-07 | 2024-08-30
203 | HVDC-ADOPT-HE-0170 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Support Pole HPL B1 & Set of Poles LTB Spare | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1430 | 8 | 8 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-12 | 2024-08-07 | 2024-08-07 | 2024-08-30
204 | HVDC-ADOPT-HE-0165 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | OPERATING DEVICE BLG | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 1 | - |  |  |  | 2410 | 9.76 | 9.76 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-16 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-09-03
205 | HVDC-ADOPT-HE-0169 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | OPERATING DEVICE BLG | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 3750 | 12.84 | 12.84 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-16 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-09-03
206 | HVDC-ADOPT-HE-0166 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Operating device, Set of tools, Gas filling device Spare | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 1108 | 4.3 | 4.3 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-13 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-09-03
207 | HVDC-ADOPT-HE-0171 | E01 | 2024-06-13 | Hitachi | Elec | Main Converter | Operating device | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1030 | 4 | 4 | 2024-06-13 | 2024-06-13 | 2024-08-07 | 2024-08-07 | 2024-07-13 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-09-03
208 | HVDC-ADOPT-HE-0174 | E01 | 2024-06-20 | Hitachi | Elec | Main Converter | Pipe, Stud, Shields, Conductor, Damper |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 56 | 0 | 10 | - |  |  |  | 50897 | 487.5 | 487.5 | 2024-06-20 | 2024-06-20 | 2024-08-06 | 2024-08-06 | 2024-07-24 | 2024-08-06 | 2024-08-06 | [5 empty] | 2024-08-16
209 | HVDC-ADOPT-HE-0173 | E01 | 2024-06-20 | Hitachi | Elec | Main Converter | Layers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 51 | 0 | 17 | - |  |  |  | 255000 | 746.02 | 746.02 | 2024-06-20 | 2024-06-20 | 2024-08-06 | 2024-08-06 | 2024-07-24 | 2024-08-06 | 2024-08-06 |  |  |  |  | 2024-08-10
210 | HVDC-ADOPT-HE-0179-A | E01 | 2024-07-04 | Hitachi | Elec | Main Converter | Shields, Insulator, Pipes, Dampers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 69 | 0 | 24 | - |  |  |  | 60031 | 686.8 | 686.8 | 2024-06-27 | 2024-06-27 | 2024-08-07 | 2024-08-07 | 2024-07-24 | 2024-08-07 | 2024-08-07 |  |  |  |  | 2024-08-22 | 2024-08-22
211 | HVDC-ADOPT-HE-0179-B | E01 | 2024-07-04 | Hitachi | Elec | Main Converter | Shields, Insulator, Pipes, Dampers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 3 | - |  |  |  | 5484 |  |  | 2024-06-27 | 2024-06-27 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-16 | 2024-08-16 |  |  |  |  | 2024-09-03 | 2024-09-03
212 | HVDC-ADOPT-SCT-0009 | E08 | 2024-07-05 | TaeHwa | Elec | Cable Tray System | Cable Tray System (3rd) |  | O |  |  | FOB | KOREA | Busan Port | Khalifa port | HMM |  | C | 68 | 1 | 13 | - |  |  |  | 168787 | 665.53 | 665.53 | 2024-07-03 | 2024-07-05 | 2024-08-12 | 2024-08-12 | 2024-07-08 | 2024-08-13 | 2024-08-13 |  |  | 2024-12-18 | [6 empty] | 2024-09-16
213 | HVDC-ADOPT-SIM-0005-1 | E04-1 | 2024-06-04 | Siemens | Elec | 400kV and 132kV New Converter GIS | DAS Cluster 132kV" GIS & Accessories PS002 |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 87 | 0 | 11 | - |  |  |  | 72654.05 | 396.5 | 396.5 | 2024-07-03 | 2024-07-03 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 |  |  | 2024-11-16 |  |  | 2024-08-14 |  |  |  | 2024-11-13
214 | HVDC-ADOPT-SCT-0010 | M01 | 2024-07-08 | Excellift | Mech | Crane and Hoist | Crane and Hoist (5th) | O | O |  | O | FOB | MALAYSIA | Port Klang | Khalifa port | MSC | Alpha Maritime | C | 26 | 0 | 4 | - |  |  |  | 20980 | 74.71 | 74.71 | 2024-07-12 | 2024-07-12 | 2024-08-08 | 2024-08-08 | 2024-07-16 | 2024-08-09 | 2024-08-09 | 2025-01-16 |  | 2025-01-12 | 2025-01-15 | [5 empty] | 2025-01-14
215 | HVDC-ADOPT-SIM-0006 | E04-1 | 2024-05-31 | Siemens | Elec | 400kV and 132kV New Converter GIS | DAS Cluster 132kV" GIS Cleaning Material & SF6 Gas PS01 (DG) |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 6 | 0 | 1 | - |  |  |  | 6305.1 | 14.4 | 14.4 | 2024-07-12 | 2024-07-12 | 2024-08-16 | 2024-08-16 | 2024-07-18 | 2024-08-19 | 2024-08-26 | [9 empty] | 2025-01-28 | 2024-08-29
216 | HVDC-ADOPT-SIM-0005-2A | E04-1 | 2024-06-04 | Siemens | Elec | 400kV and 132kV New Converter GIS | DAS Cluster 132kV" GIS & Accessories PS002 |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 8 | 0 | 0 | - |  |  |  | 32040 | 224.32 | 224.32 | 2024-07-12 | 2024-07-12 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-19 | 2024-08-19 |  |  | 2024-12-25 |  |  | 2024-08-25 |  |  |  | 2024-12-26
217 | HVDC-ADOPT-SIM-0005-2B | E04-1 | 2024-06-04 | Siemens | Elec | 400kV and 132kV New Converter GIS | DAS Cluster 132kV" GIS & Accessories PS002 |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 25 | 1 | 11 | - |  |  |  | 62186 | 367.54 | 367.54 | 2024-07-12 | 2024-07-12 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-19 | 2024-08-19 |  |  | 2024-12-25 |  |  | 2024-08-25 |  |  |  | 2024-12-26
218 | HVDC-ADOPT-HE-0178 | E01 | 2024-07-13 | Hitachi | Elec | Main Converter | Transformer Units & Accessories |  | O |  |  | DAP | SWEDEN | Norrkoping | Mina Zayed |  | Scan Global Logistics AB | B | 118 | 0 | 0 | - |  |  |  | 1026302 | 1998.17 | 1998.17 | 2024-07-17 | 2024-07-17 | 2024-09-02 | 2024-09-02 | 2024-07-24 | 2024-08-29 | 2024-08-30 |  |  |  |  | 2024-09-21 | 2024-09-21
219 | HVDC-ADOPT-HE-0176 | E01 | 2024-06-27 | Hitachi | Elec | Main Converter | Layers |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 39 | 0 | 13 | - |  |  |  | 195000 | 570.48 | 570.48 | 2024-06-27 | 2024-06-27 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-14 | 2024-08-15 |  |  |  |  | 2024-08-31
220 | HVDC-ADOPT-HE-0177 | E01 | 2024-06-27 | Hitachi | Elec | Main Converter | Pipe, Stud, Shields, Assembly Material |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 88 | 0 | 16 | - |  |  |  | 57864 | 522.12 | 522.12 | 2024-06-27 | 2024-06-27 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-14 | 2024-08-15 | [5 empty] | 2024-08-29
221 | HVDC-ADOPT-HE-0175 | E01 | 2024-06-27 | Hitachi | Elec | Main Converter | Top Part Installation |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 48 | 0 | 8 | - |  |  |  | 49920 | 625.66 | 625.66 | 2024-06-27 | 2024-06-27 | 2024-08-16 | 2024-08-16 | 2024-07-24 | 2024-08-14 | 2024-08-15 | [5 empty] | 2024-08-27
222 | HVDC-ADOPT-HE-0129 | E01 | 2024-07-11 | Hitachi | Elec | Main Converter | Wallbushing & Corona Shields | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 94 | 0 | 11 | - |  |  |  | 61933 | 338.94 | 338.94 | 2024-07-11 | 2024-07-11 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-12 | [5 empty] | 2024-09-17
223 | HVDC-ADOPT-HE-0181 | E01 | 2024-07-11 | Hitachi | Elec | Main Converter | Wallbushing & Corona Shields | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 14 | 0 | 0 | - |  |  |  | 8610 | 53.27 | 53.27 | 2024-07-11 | 2024-07-11 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-12 | [5 empty] | 2024-09-16
224 | HVDC-ADOPT-HE-0180 | E01 | 2024-07-11 | Hitachi | Elec | Main Converter | Spare Wallbushing & Corona Shields | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 1947 | 10.33 | 10.33 | 2024-07-24 | 2024-07-11 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-12 | [5 empty] | 2024-09-16
225 | HVDC-ADOPT-SIM-0009-1A | E04-1 | 2024-06-19 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHU 400 kV" GIS & Accessories SHDC001 PS04 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 38 | 0 | 13 | - |  |  |  | 62247 | 588.95 | 588.95 | 2024-07-18 | 2024-07-18 | 2024-08-26 | 2024-08-26 | 2024-08-07 | 2024-08-26 | 2024-08-27 | 2024-09-05
226 | HVDC-ADOPT-SIM-0009-1B | E04-1 | 2024-06-19 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHU 400 kV" GIS & Accessories SHDC001 PS04 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 64 | 0 | 8 | - |  |  |  | 67821 | 506.55 | 506.55 | 2024-07-18 | 2024-07-18 | 2024-08-26 | 2024-08-26 | 2024-08-07 | 2024-08-26 | 2024-08-27 | 2024-09-05
227 | HVDC-ADOPT-SCT-0013 | E08 | 2024-07-19 | TaeHwa | Elec | Cable Tray System | Cable Tray System (4th) | O |  | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 78 | 0 | 16 | - |  |  |  | 219962 | 867.79 | 867.79 | 2024-07-19 | 2024-07-19 | 2024-08-28 | 2024-08-28 | 2024-07-26 | 2024-08-26 | 2024-08-27 | 2024-09-14 | 2024-09-06
228 | HVDC-ADOPT-HE-0182 | E01 | 2024-08-01 | Hitachi | Elec | Main Converter | Transformer Unit and Accessories |  |  |  | O | DAP | Brazil | Itagui | Mina Zayed | BBC | Scan Global Logistics AB | C | 46 | 0 | 0 | - |  |  |  | 488336 | 692.31 | 692.31 | 2024-08-01 | 2024-08-01 | 2024-09-01 | 2024-09-01 | 2024-08-09 | 2024-08-27 | 2024-08-28 |  |  |  |  | 2024-09-01 | 2024-09-20
229 | HVDC-ADOPT-SCT-0014 | E08 | 2024-08-05 | TaeHwa | Elec | Cable Tray System | Cable Tray System (5th) | O |  | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 82 | 0 | 15 | - |  |  |  | 187023 | 630.17 | 630.17 | 2024-08-05 | 2024-08-05 | 2024-09-10 | 2024-09-10 |  | 2024-09-10 | 2024-09-10 | 2024-09-27 | 2024-11-04 | [7 empty] | 2025-01-09
230 | HVDC-ADOPT-SIM-0009-2A | E04-1 | 2024-06-20 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHU 400 kV" GIS & Accessories SHDC001 PS04 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 34 | 0 | 13 | - |  |  |  | 55434 | 543.26 | 543.26 | 2024-08-16 | 2024-08-16 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-11 | 2024-10-04
231 | HVDC-ADOPT-SIM-0009-2B | E04-1 | 2024-06-20 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHU 400 kV" GIS & Accessories SHDC001 PS04 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 53 | 0 | 6 | - |  |  |  | 53562 | 385.1 | 385.1 | 2024-08-16 | 2024-08-16 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-11 | 2024-10-04
232 | HVDC-ADOPT-SIM-0010 | E04-1 | 2024-06-20 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHU 400 kV" GIS & Accessories DG Cargo PS03 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 30 | 0 | 2 | - |  |  |  | 15840.7 | 42.55 | 42.55 | 2024-08-16 | 2024-08-16 | 2024-09-10 | 2024-09-10 | 2024-09-20 | 2024-09-11 | 2024-09-11 | 2025-01-31 | [9 empty] | 2024-09-18
233 | HVDC-ADOPT-SIM-0016 | E04-1 | 2024-06-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRPS - 400 kv GIS - Mirfa Modification - PS05 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 11 | 0 | 1 | - |  |  |  | 6140 | 25.77 | 25.77 | 2024-08-16 | 2024-08-16 | 2024-09-10 | 2024-09-10 | 2024-09-19 | 2024-09-11 | 2024-09-11 |  | 2024-09-16
234 | HVDC-ADOPT-HE-0183 | E01 | 2024-07-19 | Hitachi | Elec | Main Converter | Aluminum Plates | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 6 | 0 | 1 | - |  |  |  | 3365 | 5.24 | 5.24 | 2024-07-19 | 2024-07-19 | 2024-09-10 | 2024-09-10 | 2024-09-20 | 2024-09-11 | 2024-09-12 |  | 2024-10-16
235 | HVDC-ADOPT-HE-0184 | E01 | 2024-07-19 | Hitachi | Elec | Main Converter | Aluminum Plates | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 3304 | 5.1 | 5.1 | 2024-07-19 | 2024-07-19 | 2024-09-10 | 2024-09-10 | 2024-09-20 | 2024-09-11 | 2024-09-12 |  | 2024-10-16 | 2025-05-04
236 | HVDC-ADOPT-SIM-0017-A | E04-1 | 2024-06-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | Shuweihat 400 kV" GIS & Accessories PS07 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 52 | 1 | 17 | - |  |  |  | 35096 | 249.57 | 249.57 | 2024-08-13 | 2024-08-13 | 2024-09-16 | 2024-09-16 | 2024-09-20 | 2024-09-11 | 2024-09-11 | 2024-10-05
237 | HVDC-ADOPT-SIM-0017-B | E04-1 | 2024-06-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | Shuweihat 400 kV" GIS & Accessories PS07 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 27 | 0 | 0 | - |  |  |  | 34623 | 352.51 | 352.51 | 2024-08-13 | 2024-08-13 | 2024-09-16 | 2024-09-16 | 2024-09-20 | 2024-09-11 | 2024-09-11 | 2024-10-05
238 | HVDC-ADOPT-ZEN-0001 |  | 2024-08-24 | Fluid Pumps | Mech |  | Grooved Fittings |  |  |  |  | CIF | India | Tuticorin | Khalifa port |  | Sky Shipping Line | C | 13 | 1 | 0 | - |  |  |  | 8069.43 | 12.32 | 12.32 | 2024-08-31 | 2024-08-31 | 2024-09-16 | 2024-09-16 |  | 2024-09-27 | 2024-09-28 | [11 empty] | 2024-10-02
239 | HVDC-ADOPT-SEI-0006 | E03 | 2024-08-13 | Sumitomo | Elec | 400kV HVDC Cable System | Repair Joint (1st) |  |  |  |  | CIF | JAPAN | Kobe | Khalifa port | Evergreen | Deugro | C | 20 | 2 | 0 | - |  |  |  | 15040 | 59.25 | 59.25 | 2024-08-13 | 2024-08-13 | 2024-09-22 | 2024-09-22 | 2024-08-18 | 2024-09-30 | 2024-09-30 | [7 empty] | 2024-10-11
240 | HVDC-ADOPT-SEI-0012 | E03 | 2024-08-13 | Sumitomo | Elec | 400kV HVDC Cable System | Armour Clamp |  |  |  |  | CIF | NETHERLANDS | Rotterdam | Khalifa port | MAERSK | Deugro | C | 8 | 1 | 0 | - |  |  |  | 1420 | 5.12 | 5.12 | 2024-08-13 | 2024-08-13 | 2024-09-25 | 2024-09-25 | 2024-08-18 | 2024-09-30 | 2024-10-01 | [7 empty] | 2024-10-08
241 | HVDC-ADOPT-ZEN-0002 |  | 2024-09-09 | SCHRACK SECONET | Elec |  | Parts of Aspiration System |  |  |  |  | CIP | Great Britain | Viena | Abu Dhabi Airport |  | Emirates | A | 3 | 0 | 0 | - |  |  |  | 1444 | 8.18 | 8.18 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 |  | 2024-09-25 | 2024-09-25 | [11 empty] | 2024-09-27
242 | HVDC-ADOPT-PPL-0015 | E02 | 2024-08-01 | Prysmian | Elec | 320kV HVDC Cable System | Spare Subsea Cable and Reel |  |  |  |  | CIF | Italy | Salermo | Khalifa port |  |  | B | 3 | 0 | 0 | - |  |  |  | 110630 | 216.9 | 216.9 | 2024-08-13 | 2024-08-13 | 2024-09-26 | 2024-09-26 |  | 2024-09-26 | 2024-09-26 | [7 empty] | 2024-10-04
243 | HVDC-ADOPT-HE-0187 | E01 | 2024-08-27 | Hitachi | Elec | Main Converter | Air Blast Coolers & Handrails |  | O |  |  | DAP | GERMANY | Bremerhaven | Khalifa port |  | Scan Global Logistics AB | B | 12 | 0 | 0 | - |  |  |  | 88213 | 642.56 | 642.56 | 2024-08-27 | 2024-08-27 | 2024-10-03 | 2024-10-03 |  | 2024-10-01 | 2024-10-03 | [5 empty] | 2024-10-08
244 | HVDC-ADOPT-HE-0185 | E01 | 2024-08-27 | Hitachi | Elec | Main Converter | Air Blast Coolers & Handrails | O |  |  |  | DAP | GERMANY | Bremerhaven | Khalifa port |  | Scan Global Logistics AB | B | 7 | 0 | 0 | - |  |  |  | 68665 | 505.33 | 505.33 | 2024-08-27 | 2024-08-27 | 2024-10-03 | 2024-10-03 |  | 2024-10-01 | 2024-10-03 | 2024-10-06
245 | HVDC-ADOPT-SCT-0016 | E08 | 2024-08-30 | TaeHwa | Elec | Cable Tray System | Cable Tray System (6th) |  |  | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 80 | 0 | 14 | - |  |  |  | 195066 | 623.03 | 623.03 | 2024-08-30 | 2024-08-30 | 2024-10-04 | 2024-10-04 |  | 2024-10-03 | 2024-10-04 |  | 2024-11-04 |  | 2025-04-06 |  | 2024-10-06 |  |  |  | 2025-01-15
246 | HVDC-ADOPT-HE-0188 | E01 | 2024-08-18 | Hitachi | Elec | Main Converter | Structure, Shaft, Support, Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 10 | 1 | 2 | - |  |  |  | 10375 | 54.05 | 54.05 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  | 2024-10-24
247 | HVDC-ADOPT-HE-0190 | E01 | 2024-08-18 | Hitachi | Elec | Main Converter | Spare Singlepole, Shaft, Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 2415 | 13.62 | 13.62 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  | 2024-10-24
248 | HVDC-ADOPT-HE-0191 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | Spare OP Mechanism |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 410 | 2 | 2 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  |  |  |  | 2024-10-12
249 | HVDC-ADOPT-HE-0193 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | Spare Insulator, Stacks, Shaft, Structure | O | O | O | O | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 35 | 0 | 5 | - |  |  |  | 9628 | 48.69 | 48.69 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  |  | 2025-02-06 |  | 2024-10-12 | 2024-10-12
250 | HVDC-ADOPT-HE-0197 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | Spare OP Mechanism | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 9 | 0 | 0 | - |  |  |  | 1364 | 6.24 | 6.24 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  |  |  |  | 2024-10-12
251 | HVDC-ADOPT-HE-0189 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | OP Mechanism for Singlepole |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1374 | 6.76 | 6.76 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  |  |  |  | 2024-10-12
252 | HVDC-ADOPT-HE-0192 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | Insulator, Stacks, Shaft, Structure | O | O | O | O | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 62 | 0 | 5 | - |  |  |  | 44425 | 225.66 | 225.66 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 |  |  | 2025-02-06 |  | 2024-10-12 | 2024-10-12
253 | HVDC-ADOPT-HE-0195 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | OP Mechanism for Singlepole | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 11 | 0 | 0 | - |  |  |  | 4411 | 23.13 | 23.13 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 | 2025-04-03 |  |  |  | 2024-10-12
254 | HVDC-ADOPT-HE-0194 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | Insulator, Stacks, Shaft, Structure, Support, Single DSC | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 40 | 0 | 5 | - |  |  |  | 28240 | 144.46 | 144.46 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 | 2024-10-17
255 | HVDC-ADOPT-HE-0196 | E01 | 2024-08-21 | Hitachi | Elec | Main Converter | SPARE SINGLEPOLE, SHAFT, INSULATOR | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 17 | 0 | 0 | - |  |  |  | 5280 | 26.73 | 26.73 | 2024-08-21 | 2024-08-21 | 2024-10-08 | 2024-10-08 |  | 2024-10-08 | 2024-10-08 | 2024-10-19
256 | HVDC-ADOPT-SEI-0011 | E03 | 2024-08-28 | Sumitomo | Elec | 400kV HVDC Cable System | DC400kv Subsea Cable |  |  |  |  | CIF | JAPAN | Hitachi | Mina Zayed | UHL | Deugro | B | 4 | 0 | 0 | - |  |  |  | 5635154 | 4747.3 | 5635.15 | 2024-09-18 | 2024-09-18 | 2024-10-07 | 2024-10-07 |  | 2024-10-05 | 2024-10-07 | [7 empty] | 2024-10-10
257 | HVDC-ADOPT-SIM-0014-A | E04-1 | 2024-06-26 | Siemens | Elec | 400kV and 132kV New Converter GIS | Earthing Materials (Existing Work) | O |  |  |  | CIF | United Kingdom | Southampton | Khalifa port |  | FedEx Logistics | C | 6 | 1 | 0 | - |  |  |  | 2848.4 | 2.57 | 2.85 | 2024-08-21 | 2024-08-21 | 2024-10-03 | 2024-10-03 |  | 2024-10-03 | 2024-10-05 | 2024-10-15
258 | HVDC-ADOPT-SIM-0014-B | E04-1 | 2024-06-26 | Siemens | Elec | 400kV and 132kV New Converter GIS | Earthing Materials (Existing Work) |  |  | O |  | CIF | United Kingdom | Southampton | Khalifa port |  | FedEx Logistics | C | 5 | 0 | 0 | - |  |  |  | 2021.65 | 2.07 | 2.07 | 2024-08-21 | 2024-08-21 | 2024-10-03 | 2024-10-03 |  | 2024-10-03 | 2024-10-05 |  | 2024-10-15
259 | HVDC-ADOPT-SIM-0012-A | E04-1 | 2024-07-22 | Siemens | Elec | 400kV and 132kV New Converter GIS | MIRFA 400 kV" GIS & Accessories PS09 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 20 | 0 | 19 | - |  |  |  | 47074 | 412.57 | 412.57 | 2024-09-03 | 2024-09-03 | 2024-10-11 | 2024-10-11 |  | 2024-10-10 | 2024-10-11 |  | 2024-10-17
260 | HVDC-ADOPT-SIM-0012-B | E04-1 | 2024-07-22 | Siemens | Elec | 400kV and 132kV New Converter GIS | MIRFA 400 kV" GIS & Accessories PS09 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 14 | 0 | 0 | - |  |  |  | 57048 | 535.89 | 535.89 | 2024-09-03 | 2024-09-03 | 2024-10-11 | 2024-10-11 |  | 2024-10-10 | 2024-10-11 |  | 2024-10-17
261 | HVDC-ADOPT-SIM-0012-C | E04-1 | 2024-07-22 | Siemens | Elec | 400kV and 132kV New Converter GIS | MIRFA 400 kV" GIS & Accessories PS09 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 71 | 0 | 0 | - |  |  |  | 46758.3 | 210.99 | 210.99 | 2024-09-03 | 2024-09-03 | 2024-10-11 | 2024-10-11 |  | 2024-10-10 | 2024-10-11 |  | 2024-10-17
262 | HVDC-ADOPT-SIM-0015 | E04-1 | 2024-07-22 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv_GIS_MRDC_PS08_DG Shipment |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 24 | 1 | 0 | - |  |  |  | 693.6 | 2.01 | 2.01 | 2024-09-03 | 2024-09-03 | 2024-10-11 | 2024-10-11 |  | 2024-10-16 | 2024-10-24 |  | 2024-12-16 | [8 empty] | 2024-10-31
263 | HVDC-ADOPT-HE-0198 | E01 | 2024-09-09 | Hitachi | Elec | Main Converter | Outdoor-MV-DC-Electronic-System OMVDC-E 24,OMVDC-E 36 | O |  |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 2830 | 28.07 | 28.07 | 2024-09-10 | 2024-09-10 | 2024-10-11 | 2024-10-11 |  | 2024-10-11 | 2024-10-14 | 2024-10-26
264 | HVDC-ADOPT-HE-0199 | E01 | 2024-09-09 | Hitachi | Elec | Main Converter | Outdoor-MV-DC-Electronic-System OMVDC- E 36 Spare | O |  |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 558 | 3.39 | 3.39 | 2024-09-10 | 2024-09-10 | 2024-10-11 | 2024-10-11 |  | 2024-10-11 | 2024-10-14 | 2024-10-26
265 | HVDC-ADOPT-HE-0200 | E01 | 2024-09-09 | Hitachi | Elec | Main Converter | Outdoor-MV-DC-Electronic-System OMVDC-E 24,OMVDC-E 36 |  | O |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 3340 | 28.07 | 28.07 | 2024-09-10 | 2024-09-10 | 2024-10-11 | 2024-10-11 |  | 2024-10-11 | 2024-10-14 | [5 empty] | 2024-10-18
266 | HVDC-ADOPT-HE-0201 | E01 | 2024-09-09 | Hitachi | Elec | Main Converter | Outdoor-MV-DC-Electronic-System OMVDC-E 24, E 36 Spare |  | O |  |  | DAP | Austria | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 553 | 3.39 | 3.39 | 2024-09-10 | 2024-09-10 | 2024-10-11 | 2024-10-11 |  | 2024-10-11 | 2024-10-14 | [5 empty] | 2024-10-18
267 | HVDC-ADOPT-SCT-0017 | M01 | 2024-09-21 | Excellift | Mech | Crane and Hoist | Crane and Hoist (6th) |  | O | O | O | FOB | MALAYSIA | Port Klang | Khalifa port | MSC | Alpha Maritime | C | 9 | 0 | 1 | - |  |  |  | 4500 | 17.65 | 17.65 | 2024-09-21 | 2024-09-21 | 2024-10-15 | 2024-10-15 |  | 2024-10-18 | 2024-10-18 |  | 2024-10-28 | [7 empty] | 2024-10-28
268 | HVDC-ADOPT-HE-0207 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Wallbushing & Corona rings |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 10 | 0 | 1 | - |  |  |  | 8300 | 42.75 | 42.75 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 |  | 2024-11-07
269 | HVDC-ADOPT-HE-0211 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Cell Replacement Tool |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1912 | 4.84 | 4.84 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 |  | 2024-11-07
270 | HVDC-ADOPT-HE-0206 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Wallbushing | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 8 | 1 | 1 | - |  |  |  | 4521 | 21.31 | 21.31 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 | [5 empty] | 2024-10-26
271 | HVDC-ADOPT-HE-0209 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Oil Flow Indicator |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 9 | 0.06 | 0.06 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 |  |  |  |  | 2024-10-26
272 | HVDC-ADOPT-HE-0210 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Cell Replacement Tool |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1530 | 4.74 | 4.74 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 | [5 empty] | 2024-10-26
273 | HVDC-ADOPT-HE-0212 | E01 | 2024-09-12 | Hitachi | Elec | Main Converter | Wallbushing & Corona Shields |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 3660 | 22.28 | 22.28 | 2024-09-12 | 2024-09-12 | 2024-10-20 | 2024-10-20 |  | 2024-10-21 | 2024-10-22 | [5 empty] | 2024-10-26
274 | HVDC-ADOPT-SIM-0013 | E04-1 | 2024-06-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRPS-400 kV" Existing GIS Modification PS06 DG cargo |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 1 | 1 | 0 | - |  |  |  | 2475 | 6.57 | 6.57 | 2024-09-09 | 2024-09-09 | 2024-10-21 | 2024-10-21 |  | 2024-10-21 | 2024-10-22 |  | 2024-10-30
275 | HVDC-ADOPT-HE-0186 | E01 | 2024-09-07 | Hitachi | Elec | Main Converter | Pump, Threatment, UMD Cabinet, Comm. Supplies, Special Tools | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | B | 18 | 0 | 0 | - |  |  |  | 33690 | 186.24 | 186.24 | 2024-09-07 | 2024-09-07 | 2024-10-30 | 2024-10-30 |  | 2024-10-29 | 2024-10-30 |  |  |  |  | 2024-11-06
276 | HVDC-ADOPT-HE-0202 | E01 | 2024-09-07 | Hitachi | Elec | Main Converter | Pump, Threatment, UMD Cabinet, Comm. Supplies, Special Tools |  | O | O |  | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | B | 18 | 0 | 0 | - |  |  |  | 33690 | 184.55 | 184.55 | 2024-09-07 | 2024-09-07 | 2024-10-30 | 2024-10-30 |  | 2024-10-29 | 2024-10-30 |  |  |  |  | 2024-11-06
277 | HVDC-ADOPT-HE-0203 | E01 | 2024-09-22 | Hitachi | Elec | Main Converter | Air Blast coolers |  |  | O |  | DAP | GERMANY | Bremerhaven | Khalifa port |  | Scan Global Logistics AB | B | 14 | 0 | 0 | - |  |  |  | 113281 | 794.99 | 794.99 | 2024-09-23 | 2024-09-23 | 2024-10-30 | 2024-10-30 |  | 2024-10-28 | 2024-10-28 |  | 2024-11-03
278 | HVDC-ADOPT-HE-0204 | E01 | 2024-09-22 | Hitachi | Elec | Main Converter | Air Blast coolers |  |  |  | O | DAP | GERMANY | Bremerhaven | Khalifa port |  | Scan Global Logistics AB | B | 15 | 0 | 0 | - |  |  |  | 124596 | 854.48 | 854.48 | 2024-09-23 | 2024-09-23 | 2024-10-30 | 2024-10-30 |  | 2024-10-28 | 2024-10-28 | [5 empty] | 2024-11-05
279 | HVDC-ADOPT-SIM-0024 | E04-1 | 2024-08-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv_GIS_DSDC_PS012_DG Shipment |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 5 | 1 | 0 | - |  |  |  | 2457.9 | 7.95 | 7.95 | 2024-09-20 | 2024-09-20 | 2024-10-29 | 2024-10-29 |  | 2024-10-30 | 2024-11-22 |  |  | 2025-02-13 | [6 empty] | 2025-05-01 | 2024-12-27
280 | HVDC-ADOPT-HE-0205 | E01 | 2024-09-17 | Hitachi | Elec | Main Converter | Transformer Units and Accessories |  |  |  | O | DAP | BRAZIL | Itagui | Mina Zayed |  | Scan Global Logistics AB | B | 69 | 0 | 0 | - |  |  |  | 725786 | 971.59 | 971.59 | 2024-09-30 | 2024-09-30 | 2024-10-31 | 2024-10-31 |  | 2024-10-24 | 2024-10-24 | [5 empty] | 2024-11-19 | 2024-11-19
281 | HVDC-ADOPT-HE-0213 | E01 | 2024-09-30 | Hitachi | Elec | Main Converter | Pumps |  |  | O |  | DAP | BRAZIL | Itagui | Mina Zayed |  | Scan Global Logistics AB | B | 1 | 0 | 0 | - |  |  |  | 1600 | 3.27 | 3.27 | 2024-09-30 | 2024-09-30 | 2024-10-31 | 2024-10-31 |  | 2024-10-24 | 2024-10-24 |  | 2024-11-13
282 | HVDC-ADOPT-SCT-0018 | E08 | 2024-09-25 | Sangdong | Elec | Steel Conduit | Steel Conduit (1st) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 19 | 0 | 5 | - |  |  |  | 70920 | 115.73 | 115.73 | 2024-09-26 | 2024-09-26 | 2024-11-04 | 2024-11-04 |  | 2024-11-06 | 2024-11-06 | 2024-11-13 | 2024-11-18 | 2024-12-11 | 2024-12-11
283 | HVDC-ADOPT-SCT-0015 | E08 | 2024-09-26 | LS Cable | Elec | 400kv Power Cable | 400kv Power Cable (1st) |  |  | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 9 | 9 | 0 | - |  |  |  | 254971 | 438.57 | 438.57 | 2024-09-26 | 2024-09-26 | 2024-11-04 | 2024-11-04 |  | 2024-11-04 | 2024-11-05 |  | 2024-11-26
284 | HVDC-ADOPT-SEI-0008 | E03 | 2024-09-15 | Sumitomo | Elec | 400kV HVDC Cable System | Transition joint, Link Box and Repair Joints |  |  |  |  | CIF | JAPAN | Kobe | Khalifa port | Evergreen | Deugro | C | 62 | 0 | 5 | - |  |  |  | 28266 | 120.57 | 120.57 | 2024-09-16 | 2024-09-16 | 2024-11-04 | 2024-11-04 |  | 2024-11-08 | 2024-11-08 | [5 empty] | 2024-11-18
285 | HVDC-ADOPT-ZEN-0003 |  | 2024-10-01 | SCHRACK SECONET | Elec |  | Fire Alarm System & Aspiration System & Accessories |  |  |  |  | CIP | Austria | Viena | Abu Dhabi Airport |  | European Air Transpor | A | 3 | 0 | 0 | - |  |  |  | 349 | 4.16 | 4.16 | 2024-10-31 | 2024-10-31 | 2024-11-06 | 2024-11-06 |  | 2024-11-06 | 2024-11-06 | [11 empty] | 2024-11-07
286 | HVDC-ADOPT-ZEN-0003 |  | 2024-10-01 | SCHRACK SECONET | Elec |  | Fire Alarm System & Aspiration System & Accessories |  |  |  |  | CIP | Austria | Viena | Abu Dhabi Airport |  | European Air Transpor | A | 4 | 0 | 0 | - |  |  |  | 467 |  |  | 2024-10-31 | 2024-10-31 | 2024-11-07 | 2024-11-07 |  | 2024-11-07 | 2024-11-07 | [11 empty] | 2024-11-07
287 | HVDC-ADOPT-SCT-0021 | E08 | 2024-10-04 | Sangdong | Elec | Steel Conduit | Steel Conduit (2nd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | ESL | Deugro | C | 12 | 1 | 1 | - |  |  |  | 12890 | 28.25 | 28.25 | 2024-10-04 | 2024-10-04 | 2024-11-10 | 2024-11-10 |  | 2024-11-14 | 2024-11-14 | 2024-11-24 | 2024-11-17 | [7 empty] | 2024-11-21
288 | HVDC-ADOPT-SCT-0019 | E08 | 2024-10-01 | TaeHwa | Elec | Cable Tray System | Cable Tray System (7th) |  |  | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 47 | 0 | 10 | - |  |  |  | 129578 | 406.72 | 406.72 | 2024-10-01 | 2024-10-01 | 2024-11-11 | 2024-11-11 |  | 2024-11-12 | 2024-11-12 |  | 2025-01-02 |  | 2025-04-21
289 | HVDC-ADOPT-SCT-0020 | E08 | 2024-10-01 | LS Cable | Elec | 400kv Power Cable | 400kv Power Cable (2nd) |  |  | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 9 | 9 | 0 | - |  |  |  | 253128 | 438.57 | 438.57 | 2024-10-01 | 2024-10-01 | 2024-11-11 | 2024-11-11 |  | 2024-11-12 | 2024-11-12 |  | 2024-12-01
290 | HVDC-ADOPT-SCT-0027 | E08 | 2024-10-09 | Bansuk | Elec | Lighting and Small Power Sysytem | Flood Light |  | O | O |  | FOB | CHINA | Shenzhen | Abu Dhabi Airport |  | Deugro | A | 10 | 0 | 0 | - |  |  |  | 51 | 0.83 | 0.83 | 2024-11-10 | 2024-11-10 | 2024-11-11 | 2024-11-11 |  | 2024-11-12 | 2024-11-12 |  | 2024-11-14 | 2024-11-14
291 | HVDC-ADOPT-ZEN-0007 |  | 2024-10-30 | SCHRACK SECONET | Elec |  | Fire Alarm and Aspiration Sytem |  |  |  |  | CIP | Austria | Viena | Abu Dhabi Airport |  | Etihad | A | 3 | 0 | 0 | - |  |  |  | 550 | 3.87 | 3.87 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2024-11-12 |  | 2024-11-14 | 2024-11-14 | [11 empty] | 2024-11-15
292 | HVDC-ADOPT-SEI-0015 | E03 | 2024-10-31 | Sumitomo | Elec | 400kV HVDC Cable System | DANGEROUS GOODS for CABLE ACCESSORIES | O | O |  |  | CIP | JAPAN | Osaka | Abu Dhabi Airport |  | UCI Airfreight | A | 13 | 0 | 0 | - |  |  |  | 36 | 0.39 | 0.39 | 2024-11-11 | 2024-11-11 | 2024-11-12 | 2024-11-12 |  | 2024-11-12 | 2024-11-12 | [8 empty] | 2024-11-14
293 | HVDC-ADOPT-SIM-0021 | E04-1 | 2024-08-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv_GIS_MRDC_PS010_DG Shipment |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MSC | Alpha Maritime | C | 6 | 1 | 1 | - |  |  |  | 14855 | 39.54 | 39.54 | 2024-09-30 | 2024-09-30 | 2024-11-13 | 2024-11-13 |  | 2024-11-14 | 2024-11-14 |  | 2025-01-02
294 | HVDC-ADOPT-SIM-0025 | E04-1 | 2024-08-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | 132kV_DSDC_PS013 GIB equipment - connection module, Air Bushing, accessories |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MSC | Alpha Maritime | C | 35 | 0 | 10 | - |  |  |  | 30266 | 249.7 | 249.7 | 2024-09-30 | 2024-09-30 | 2024-11-13 | 2024-11-13 |  | 2024-11-14 | 2024-11-15 |  |  | 2025-01-25 |  |  | 2024-11-20 |  |  |  | 2024-12-26
295 | HVDC-ADOPT-SIM-0018 | E04-1 | 2024-09-16 | Siemens | Elec | 400kV and 132kV New Converter GIS | Earthing and Lighting Materials | O | O | O | O | CIF | United Kingdom | Nottingham | Khalifa port |  | FedEx Logistics | C | 12 | 1 | 0 | - |  |  |  | 7059.45 | 6.22 | 7.06 | 2024-10-10 | 2024-10-10 | 2024-11-13 | 2024-11-13 |  | 2024-11-18 | 2024-11-18 | 2025-04-19 | 2025-02-05 | 2025-02-13 |  |  | 2024-12-23 |  |  |  | 2024-12-29
296 | HVDC-ADOPT-SIM-0030 | E04-1 | 2024-09-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv Existing GIS modification LCC panels SHPS | O |  |  |  | CIP | GERMANY | Frankfurt | Abu Dhabi Airport |  | FedEx Logistics | A | 2 | 0 | 0 | - |  |  |  | 1840 | 8.8 | 8.8 | 2024-11-11 | 2024-11-11 | 2024-11-13 | 2024-11-13 |  | 2024-11-13 | 2024-11-13 | 2024-11-14
297 | HVDC-ADOPT-HE-0214 | E01 | 2024-09-26 | Hitachi | Elec | Main Converter | Capacitors | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 74 | 0 | 2 | - |  |  |  | 36885 | 71.04 | 71.04 | 2024-09-26 | 2024-09-26 | 2024-11-16 | 2024-11-16 |  | 2024-11-15 | 2024-11-15
298 | HVDC-ADOPT-SIM-0019-A | E04-1 | 2024-08-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | GIS equipment viz. Connection module, Voltage Transformer and Accessories_MRDC_PS011 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 32 | 1 | 38 | - |  |  |  | 44005 | 483.5 | 483.5 | 2024-10-11 | 2024-10-11 | 2024-11-16 | 2024-11-16 |  | 2024-11-19 | 2024-11-20 |  | 2025-02-21
299 | HVDC-ADOPT-SIM-0019-B | E04-1 | 2024-08-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | GIS equipment viz. Connection module, Voltage Transformer and Accessories_MRDC_PS011 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 24 | 0 | 0 | - |  |  |  | 36915 | 392.91 | 392.91 | 2024-10-11 | 2024-10-11 | 2024-11-16 | 2024-11-16 |  | 2024-11-19 | 2024-11-20 |  | 2025-02-21
300 | HVDC-ADOPT-SIM-0019-C | E04-1 | 2024-08-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | GIS equipment viz. Connection module, Voltage Transformer and Accessories_MRDC_PS011 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 44 | 0 | 0 | - |  |  |  | 45200 | 359.72 | 359.72 | 2024-10-11 | 2024-10-11 | 2024-11-16 | 2024-11-16 |  | 2024-11-19 | 2024-11-20 |  | 2025-02-21
301 | HVDC-ADOPT-SIM-0019-D | E04-1 | 2024-08-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | GIS equipment viz. Connection module, Voltage Transformer and Accessories_MRDC_PS011 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 46 | 0 | 0 | - |  |  |  | 30179.05 | 229.5 | 229.5 | 2024-10-11 | 2024-10-11 | 2024-11-16 | 2024-11-16 |  | 2024-11-19 | 2024-11-20 |  | 2025-02-21
302 | HVDC-ADOPT-SEI-0009 | E03 | 2024-10-16 | Sumitomo | Elec | 400kV HVDC Cable System | DANGEROUS GOODS for CABLE ACCESSORIES |  |  |  |  | CIF | JAPAN | Kobe | Khalifa port | Evergreen |  | C | 70 | 1 | 0 | - |  |  |  | 678 | 4.75 | 4.75 | 2024-10-22 | 2024-10-22 | 2024-11-19 | 2024-11-19 |  | 2024-11-22 | 2024-11-24 | [8 empty] | 2024-12-07
303 | HVDC-ADOPT-SIM-0020 | E04-1 | 2024-08-15 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kv Existing Modification GIB_SHPS_PS014 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 6 | 0 | 2 | - |  |  |  | 6439 | 36.76 | 36.76 | 2024-10-11 | 2024-10-11 | 2024-11-16 | 2024-11-16 |  | 2024-11-15 | 2024-11-16 | 2024-11-20
304 | HVDC-ADOPT-SIM-0028-A | E04-1 | 2024-09-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kv Modification Voltage Transformer, Conn Module etc_SHPS_PS016 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 24 | 1 | 2 | - |  |  |  | 13944.7 | 77.04 | 77.04 | 2024-10-15 | 2024-10-15 | 2024-11-20 | 2024-11-20 |  | 2024-11-21 | 2024-11-22 | 2024-11-28
305 | HVDC-ADOPT-SIM-0028-B | E04-1 | 2024-09-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kv Modification Voltage Transformer, Conn Module etc_SHPS_PS016 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 15 | 0 | 3 | - |  |  |  | 18925 | 185.04 | 185.04 | 2024-10-22 | 2024-10-22 | 2024-11-27 | 2024-11-27 |  | 2024-11-26 | 2024-11-27 | 2024-12-06
306 | HVDC-ADOPT-SCT-0033 | E08 | 2024-11-21 | Bansuk | Elec | Lighting and Small Power Sysytem | Ondo G3 LW20000-840 ET |  |  | O |  | FOB | Spain | Vitoria-Gasteiz | Abu Dhabi Airport |  | Deugro | A | 1 | 0 | 0 | - |  |  |  | 82 | 0.72 | 0.72 | 2024-11-21 | 2024-11-21 | 2024-11-23 | 2024-11-23 |  | 2024-11-25 | 2024-11-25 |  | 2024-11-26
307 | HVDC-ADOPT-SIM-0032 | E04-1 | 2024-09-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kv MRPS Modification GIB Preassembled acces&cable mesh tray_PS018 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 19 | 1 | 4 | - |  |  |  | 19492 | 161.99 | 161.99 | 2024-10-22 | 2024-10-22 | 2024-11-27 | 2024-11-27 |  | 2024-11-26 | 2024-11-27 |  | 2024-12-05
308 | HVDC-ADOPT-SIM-0033 | E04-1 | 2024-09-25 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kv MRPS Modification GIB DG_PS017 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 3 | 1 | 0 | - |  |  |  | 395.5 | 1.69 | 1.69 | 2024-10-22 | 2024-10-22 | 2024-11-27 | 2024-11-27 |  | 2024-11-26 | 2024-12-05 |  | 2024-12-11
309 | HVDC-ADOPT-HE-0244 | E01 | 2024-11-27 | Hitachi | Elec | Main Converter | Hilti Stud Bolt & Adaptor | O |  |  |  | DAP | SWEDEN | Malmoe | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 46 | 0.11 | 0.11 | 2024-11-27 | 2024-11-27 | 2024-11-29 | 2024-11-29 |  | 2024-12-04 | 2024-12-04 | 2024-12-06
310 | HVDC-ADOPT-HE-0237 | E01 | 2024-11-27 | Hitachi | Elec | Main Converter | Optical Fibre Cables for Valve |  | O |  |  | DAP | Estonia | Talinn | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 755 | 2.81 | 2.81 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 |  | 2024-12-05 | 2024-12-05 |  |  | 2024-12-16 | [6 empty] | 2024-12-09
311 | HVDC-ADOPT-ZEN-0009 |  | 2024-11-05 | Fluid Pumps | Mech |  | Gate Valves |  |  |  |  | CIF | India | Tuticorin | Khalifa port |  | Freightbridge Logistics | C | 2 | 0 | 0 | 1 |  |  |  | 1045.7 | 3.23 | 3.23 | 2024-11-08 | 2024-11-08 | 2024-12-01 | 2024-12-01 |  | 2024-12-07 | 2024-12-09 | [11 empty] | 2024-12-10
312 | HVDC-ADOPT-SIM-0039 | E04-1 | 2024-10-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv PS019 SHPS Existing Modification GIB | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 18 | 2 | 4 | - |  |  |  | 19310 | 165.2 | 165.2 | 2024-11-01 | 2024-11-01 | 2024-12-05 | 2024-12-05 |  | 2024-12-05 | 2024-12-07 | 2024-12-17
313 | HVDC-ADOPT-HE-0208 | E01 | 2024-11-27 | Hitachi | Elec | Main Converter | Optical Fibre Cables for Valve | O |  |  |  | DAP | Estonia | Talinn | Abu Dhabi Airport |  |  | A | 5 | 0 | 0 | - |  |  |  | 1180 | 6.9 | 6.9 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 |  | 2024-12-08 | 2024-12-08 | 2024-12-11
314 | HVDC-ADOPT-HE-0208 | E01 | 2024-11-27 | Hitachi | Elec | Main Converter | Optical Fibre Cables for Valve | O |  |  |  | DAP | Estonia | Talinn | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 655 |  | 0.66 | 2024-11-28 | 2024-11-28 | 2024-12-03 | 2024-12-03 |  | 2024-12-09 | 2024-12-09 | 2024-12-11
315 | HVDC-ADOPT-HE-0251 | E01 | 2024-12-05 | Hitachi | Elec | Main Converter | Optical Fibre Cables for Valve |  | O |  |  | DAP | Estonia | Talinn | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 981 | 3.2 | 3.2 | 2024-12-05 | 2024-12-05 | 2024-12-09 | 2024-12-09 |  | 2024-12-10 | 2024-12-10 |  |  | 2024-12-16 | [6 empty] | 2024-12-11
316 | HVDC-ADOPT-HE-0252 | E01 | 2024-12-05 | Hitachi | Elec | Main Converter | Capacitors | O |  |  |  | DAP | SWEDEN | Copenhagen | Abu Dhabi Airport |  |  | A | 28 | 0 | 0 | - |  |  |  | 13323 | 26.88 | 26.88 | 2024-12-06 | 2024-12-06 | 2024-12-09 | 2024-12-09 |  | 2024-12-10 | 2024-12-10 | 2024-12-11
317 | HVDC-ADOPT-HE-0223 | E01 | 2024-12-07 | Hitachi | Elec | Main Converter | Pipes Valve Hall | O |  |  |  | DAP | SWEDEN | Copenhagen | Abu Dhabi Airport |  |  | A | 5 | 0 | 0 | - |  |  |  | 9020 | 55.63 | 55.63 | 2024-12-07 | 2024-12-07 | 2024-12-09 | 2024-12-09 |  | 2024-12-10 | 2024-12-10 | 2024-12-11
318 | HVDC-ADOPT-SIM-0038 | E04-1 | 2024-10-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv MRDC GIB DG PS020 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 18 | 0 | 1 | - |  |  |  | 7128.45 | 29.85 | 29.85 | 2024-11-06 | 2024-11-06 | 2024-12-09 | 2024-12-09 |  | 2024-12-13 | 2024-12-26 |  | 2025-01-10 | [7 empty] | 2025-01-18
319 | HVDC-ADOPT-SCT-0022 | E08 | 2024-11-05 | TaeHwa | Elec | Cable Tray System | Cable Tray System (8th) |  | O | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 69 | 0 | 11 | - |  |  |  | 136324 | 456.09 | 456.09 | 2024-11-05 | 2024-11-05 | 2024-12-12 | 2024-12-12 |  | 2024-12-12 | 2024-12-12 |  | 2025-01-08 | 2025-02-14 | [6 empty] | 2025-01-03
320 | HVDC-ADOPT-HE-0215 | E01 | 2024-10-25 | Hitachi | Elec | Main Converter | Transformer Unit and Accessories |  |  |  | O | DAP | BRAZIL | Itagui | Mina Zayed |  | Scan Global Logistics AB | B | 44 | 0 | 0 | - |  |  |  | 484276 | 653.41 | 653.41 | 2024-10-25 | 2024-10-25 | 2024-12-12 | 2024-12-12 |  | 2024-12-11 | 2024-12-12 | [6 empty] | 2024-12-14
321 | HVDC-ADOPT-HE-0232 | E01 | 2024-10-25 | Hitachi | Elec | Main Converter | Transformer Accessories |  |  | O |  | DAP | BRAZIL | Itagui | Mina Zayed |  | Scan Global Logistics AB | B | 1 | 0 | 0 | - |  |  |  | 2955 | 22.08 | 22.08 | 2024-10-25 | 2024-10-25 | 2024-12-12 | 2024-12-12 |  | 2024-12-11 | 2024-12-12 |  | 2024-12-18
322 | HVDC-ADOPT-SEI-0014 | E03 | 2024-11-13 | Sumitomo | Elec | 400kV HVDC Cable System | Cable Accessories | O | O |  |  | CIF | JAPAN | Kobe | Khalifa port |  | Deugro | C | 18 | 0 | 1 | - |  |  |  | 3221 | 21.14 | 21.14 | 2024-11-13 | 2024-11-13 | 2024-12-11 | 2024-12-11 |  | 2024-12-17 | 2024-12-17 | [7 empty] | 2024-12-26
323 | HVDC-ADOPT-ZEN-0010 |  | 2024-11-13 | Fluid Pumps | Mech |  | Gate Valves |  |  |  |  | CIF | India | Tuticorin | Khalifa port |  | CCL | C | 2 | 0 | 0 | 1 |  |  |  | 1751.25 | 3.18 | 3.18 | 2024-11-23 | 2024-11-23 | 2024-12-12 | 2024-12-12 |  | 2024-12-14 | 2024-12-16 | [11 empty] | 2024-12-17
324 | HVDC-ADOPT-SCT-0025 | E08 | 2024-11-07 | TaeHwa | Elec | Cable Tray System | Cable Tray System (9th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port |  | Deugro | C | 67 | 0 | 10 | - |  |  |  | 96114 | 273.18 | 273.18 | 2024-11-07 | 2024-11-07 | 2024-12-14 | 2024-12-14 |  | 2024-12-20 | 2024-12-20 | 2025-01-08 | 2025-01-02 | 2025-04-28 | [6 empty] | 2025-01-02
325 | HVDC-ADOPT-SCT-0023 | E08 | 2024-11-09 | LS Cable | Elec | 400kv Power Cable | 400kv Power Cable (3rd) | O |  | O |  | FOB | KOREA | Masan | Khalifa port |  | Deugro | B | 56 | 0 | 0 | - |  |  |  | 1287821 | 2376.01 | 2376.01 | 2024-11-09 | 2024-11-09 | 2024-12-15 | 2024-12-15 |  | 2024-12-06 | 2024-12-07 | 2024-12-31 | 2025-01-02
326 | HVDC-ADOPT-ZEN-0011 |  | 2024-11-12 | JINDAL | Elec |  | Pipe Fittings |  |  |  |  | CIF | India | Nhava Sheva | Khalifa port |  |  | C | 11 | 0 | 0 | 1 |  |  |  | 7846 | 6.65 | 7.85 | 2024-12-04 | 2024-12-04 | 2024-12-15 | 2024-12-15 |  | 2024-12-16 | 2025-01-02 | [11 empty] | 2025-01-03
327 | HVDC-ADOPT-ZEN-0005 |  | 2024-10-10 | MASTICO | Elec |  | Alarm Check Valves |  |  |  |  | CIF | KOREA | Busan Port | Khalifa port |  | Nauri Logistics | C | 5 | 0 | 0 | 1 |  |  |  | 484 | 4.26 | 4.26 | 2024-11-02 | 2024-11-02 | 2024-12-18 | 2024-12-18 |  | 2024-12-20 | 2024-12-23 | [11 empty] | 2024-12-24
328 | HVDC-ADOPT-SCT-0011 | E08 | 2024-11-16 | LS Cable | Elec | MV, LV & Control Cable | MV, LV & Control Cable (1st) |  | O |  |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 37 | 7 | 0 | - |  |  |  | 106087 | 135.48 | 135.48 | 2024-11-16 | 2024-11-16 | 2024-12-19 | 2024-12-19 |  | 2024-12-17 | 2024-12-17 |  |  | 2025-01-25 | [6 empty] | 2024-12-26
329 | HVDC-ADOPT-SCT-0012 | E08 | 2024-11-16 | LS Cable | Elec | MV, LV & Control Cable | MV, LV & Control Cable (2nd) | O |  |  |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 34 | 7 | 0 | - |  |  |  | 97780 | 132.65 | 132.65 | 2024-11-16 | 2024-11-16 | 2024-12-19 | 2024-12-19 |  | 2024-12-17 | 2024-12-17 | 2025-01-07
330 | HVDC-ADOPT-SCT-0024 | E08 | 2024-11-16 | Gastron | Elec | Gas Detection System | Gas Detection System | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1990 | 13.33 | 13.33 | 2024-11-16 | 2024-11-16 | 2024-12-19 | 2024-12-19 |  | 2024-12-20 | 2024-12-20 | 2025-01-29 | 2025-02-05 | 2025-02-19 |  |  | 2024-12-26 |  |  |  | 2025-02-01
331 | HVDC-ADOPT-SCT-0026 | E08 | 2024-11-16 | Sangdong | Elec | Steel Conduit | Steel Conduit (3rd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 46 | 1 | 6 | - |  |  |  | 123460 | 190.29 | 190.29 | 2024-11-16 | 2024-11-16 | 2024-12-19 | 2024-12-19 |  | 2024-12-20 | 2024-12-20 | 2025-01-09 | 2025-01-07 | 2025-01-25 | 2025-01-15 |  | 2025-01-03 |  |  |  | 2025-01-15
332 | HVDC-ADOPT-SCT-0040 | E08 | 2024-12-10 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O |  |  | FOB | CHINA | Shanghai | Abu Dhabi Airport |  |  | A | 7 | 0 | 0 | - |  |  |  | 2768 | 6.09 | 6.09 | 2024-12-19 | 2024-12-19 | 2024-12-19 | 2024-12-19 |  | 2024-12-20 | 2024-12-20 | 2025-01-03 |  | 2025-01-09 | [6 empty] | 2024-12-25
333 | HVDC-ADOPT-SCT-0041 | E08 | 2024-10-04 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O |  |  | FOB | SWEDEN | Malmoe | Abu Dhabi Airport |  |  | A | 5 | 0 | 0 | - |  |  |  | 1675 | 3.97 | 3.97 | 2024-12-17 | 2024-12-17 | 2024-12-20 | 2024-12-20 |  | 2024-12-24 | 2024-12-24 | 2025-01-03 |  | 2025-01-09 | [6 empty] | 2024-12-25
334 | HVDC-ADOPT-HE-0234 | E01 | 2024-11-16 | Hitachi | Elec | Main Converter | Wall Bushings-GSCL1300 & Corona shields |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 14 | 0 | 2 | - |  |  |  | 11830 | 59.81 | 59.81 | 2024-10-16 | 2024-10-16 | 2024-12-22 | 2024-12-22 |  | 2024-12-23 | 2024-12-24 |  | 2025-01-11
335 | HVDC-ADOPT-SIM-0027 | E04-1 | 2024-10-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv SHPS Existing Modification GIS DG_PS015 Shipment | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 19 | 0 | 2 | - |  |  |  | 12593.6 | 82.06 | 82.06 | 2024-11-18 | 2024-11-18 | 2024-12-22 | 2024-12-22 |  | 2024-12-20 | 2024-12-26 | 2024-12-28
336 | HVDC-ADOPT-HE-0264 | E01 | 2024-12-22 | Hitachi | Elec | Main Converter | Pipe Valve Hall (Cooling Pipe) | O |  |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 5 | 0 | 0 | - |  |  |  | 8730 | 59.2 | 59.2 | 2024-12-22 | 2024-12-22 | 2024-12-23 | 2024-12-23 |  | 2024-12-24 | 2024-12-24 | 2024-12-27
337 | HVDC-ADOPT-ZEN-0004 |  | 2024-09-04 | YANGZHOU | Mech |  | Carbon Steel Seamless Pipe |  |  |  |  | CIF | Shanghai | China | Khalifa port |  | World Calss Freight | C | 113 | 0 | 7 | - |  |  |  | 171896 | 98.69 | 171.9 | 2024-11-23 | 2024-11-23 | 2024-12-24 | 2024-12-24 |  | 2025-01-14 | 2025-01-15 | [11 empty] | 2025-01-16
338 | HVDC-ADOPT-SEI-0013 | E03 | 2024-11-29 | Sumitomo | Elec | 400kV HVDC Cable System | Bend Restrictor |  |  |  |  | CIF | United Kingdom | London | Khalifa port |  | Deugro | C | 40 | 0 | 2 | - |  |  |  | 25036 | 69.1 | 69.1 | 2024-11-29 | 2024-11-29 | 2024-12-28 | 2024-12-28 |  | 2024-12-31 | 2025-01-03 | [7 empty] | 2025-01-14
339 | HVDC-ADOPT-SCT-0030 | E08 | 2024-11-24 | LS Cable | Elec | MV, LV & Control Cable | MV, LV & Control Cable (3rd) | O | O | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 171 | 14 | 8 | - |  |  |  | 367431 | 450.76 | 450.76 | 2024-11-23 | 2024-11-23 | 2024-12-31 | 2024-12-31 |  | 2024-12-31 | 2025-01-03 | 2025-01-16 | 2025-02-01 | 2025-01-23 | [6 empty] | 2025-01-17
340 | HVDC-ADOPT-HE-0258 | E01 | 2024-12-11 | Hitachi | Elec | Main Converter | Ac Filter Reactor | O |  |  |  | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 8 | 1 | 1 | - |  |  |  | 5349 | 69.57 | 69.57 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 | 2025-01-26
341 | HVDC-ADOPT-HE-0259 | E01 | 2024-12-29 | Hitachi | Elec | Main Converter | Ac Filter Reactor Spare | O |  |  |  | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 840 | 11.5 | 11.5 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 | 2025-01-26
342 | HVDC-ADOPT-HE-0260 | E01 | 2024-12-29 | Hitachi | Elec | Main Converter | Ac Filter Reactor |  |  | O |  | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 5349 | 69.57 | 69.57 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 |  | 2025-01-26
343 | HVDC-ADOPT-HE-0261 | E01 | 2024-12-29 | Hitachi | Elec | Main Converter | Ac Filter Reactor Spare |  |  | O |  | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 840 | 11.47 | 11.47 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 |  | 2025-01-26
344 | HVDC-ADOPT-HE-0262 | E01 | 2024-12-29 | Hitachi | Elec | Main Converter | Ac Filter Reactor |  | O |  | O | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 17 | 0 | 2 | - |  |  |  | 7134 | 45.29 | 45.29 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 |  |  | 2025-05-04 |  |  | 2025-01-17
345 | HVDC-ADOPT-HE-0263 | E01 | 2024-12-29 | Hitachi | Elec | Main Converter | Ac Filter Reactor Spare |  | O |  | O | DAP | India | Nhava Sheva | Khalifa port |  | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1050 | 7.17 | 7.17 | 2024-12-29 | 2024-12-29 | 2025-01-02 | 2025-01-02 |  | 2025-01-13 | 2025-01-15 | [5 empty] | 2025-01-17
346 | HVDC-ADOPT-SIM-0035 | E04-1 | 2024-10-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRDC-PS021 GIB High Voltage Surge Arrester, connection module and parts |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 24 | 1 | 7 | - |  |  |  | 24667.7 | 230.25 | 230.25 | 2024-11-24 | 2024-11-24 | 2025-01-03 | 2025-01-03 |  | 2025-01-07 | 2025-01-07 | [5 empty] | 2025-01-20
347 | HVDC-ADOPT-SIM-0043 | E04-1 | 2024-10-23 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHDC- PS022 GIB - connection module, pipe module long | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 1 | 0 | 1 | - |  |  |  | 3303 | 40.58 | 40.58 | 2024-11-19 | 2024-11-19 | 2025-01-03 | 2025-01-03 |  | 2025-01-13 | 2025-01-13 | 2024-01-29
348 | HVDC-ADOPT-SIM-0045 | E04-1 | 2024-11-01 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kV SHDC GIB PS023 GIB | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 20 | 0 | 5 | - |  |  |  | 19449.8 | 158.43 | 158.43 | 2024-11-25 | 2024-11-25 | 2025-01-03 | 2025-01-03 |  | 2025-01-07 | 2025-01-07 | 2025-01-31
349 | HVDC-ADOPT-SIM-0041 | E04-1 | 2024-11-01 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC - GIS - DG shipment PS025 |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 33 | 0 | 1 | - |  |  |  | 10120.9 | 25.11 | 25.11 | 2024-11-25 | 2024-11-25 | 2025-01-03 | 2025-01-03 |  | 2025-01-08 | 2025-01-21 | [10 empty] | 2025-02-07
350 | HVDC-ADOPT-SIM-0029 | E04-1 | 2024-10-02 | Siemens | Elec | 400kV and 132kV New Converter GIS | Eupen Cables - SHDC GHDC and MRDC | O |  | O | O | CIF | BELGIUM | Antwerp | Khalifa port |  | SSC | C | 7 | 1 | 0 | - |  |  |  | 6146 |  |  | 2024-12-01 | 2024-12-01 | 2025-01-04 | 2025-01-04 |  | 2025-01-07 | 2025-01-14 | 2025-01-29 | 2025-02-05 | [7 empty] | 2025-02-01
351 | HVDC-ADOPT-SIM-0034 | E04-1 | 2024-10-02 | Siemens | Elec | 400kV and 132kV New Converter GIS | Eupen Cables - SHPS for Existing GIS Modification | O |  |  |  | CIF | BELGIUM | Antwerp | Khalifa port |  | SSC | C | 1 | 0 | 0 | - |  |  |  | 376 |  |  | 2024-12-01 | 2024-12-01 | 2025-01-04 | 2025-01-04 |  | 2025-01-07 | 2025-01-14 | 2025-01-21
352 | HVDC-ADOPT-ZEN-0012 |  | 2024-12-06 | Fluid Pumps | Mech |  | Pipe Fittings & Nozzle |  |  |  |  | CIF | India | Tuticorin | Khalifa port |  | Global Vission Shipping | C | 3 | 0 | 0 | 1 |  |  |  | 1766.55 | 3.12 | 3.12 | 2024-12-15 | 2024-12-15 | 2025-01-07 | 2025-01-07 |  | 2025-01-10 | 2025-01-10 | [11 empty] | 2025-01-13
353 | HVDC-ADOPT-SCT-0031 | E08 | 2024-12-03 | TaeHwa | Elec | Cable Tray System | Cable Tray System (10th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 68 | 1 | 9 | - |  |  |  | 87281 | 315.07 | 315.07 | 2024-12-03 | 2024-12-03 | 2025-01-09 | 2025-01-09 |  | 2025-01-15 | 2025-01-15 | 2025-01-27 | 2025-02-01 | 2025-04-28 | 2025-04-21 | [5 empty] | 2025-01-31
354 | HVDC-ADOPT-SCT-0032 | E08 | 2024-12-03 | Sangdong | Elec | Earthing & Lightning Protection Material | Earthing & Lightning Protection Material (1st) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 26 | 1 | 4 | - |  |  |  | 89430 | 97.86 | 97.86 | 2024-12-03 | 2024-12-03 | 2025-01-09 | 2025-01-09 |  | 2025-01-15 | 2025-01-15 | 2025-01-27 | 2025-02-01 | 2025-02-05 | 1900-07-23 | 2025-03-19 |  |  |  |  | 2025-01-31
355 | HVDC-ADOPT-SCT-0036 | I01 | 2024-12-03 | ESAK CO., Ltd | Inst. | Field Instrument | Field Instrument (1st) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1080 | 8.93 | 8.93 | 2024-12-03 | 2024-12-03 | 2025-01-09 | 2025-01-09 |  | 2025-01-15 | 2025-01-17 | 2025-02-05 | 2025-02-05 | 2025-02-10 | [6 empty] | 2025-01-28
356 | HVDC-ADOPT-SEI-0018 | E03 | 2024-12-13 | Sumitomo | Elec | 400kV HVDC Cable System | Cable Accessories(DG) |  |  |  |  | CIF | JAPAN | Osaka | Khalifa port |  |  | A | 19 | 0 | 0 | - |  |  |  | 55 | 0.57 | 0.57 | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-01-13 | 2025-01-13 | [8 empty] | 2025-01-27
357 | HVDC-ADOPT-ZEN-0015 |  | 2024-12-23 | Fluid Pumps | Mech |  | Pipe Fittings & Warning Sign |  |  |  |  | CIF | India | Cochin | Khalifa port |  | CSL | C | 18 | 1 | 0 | - |  |  |  | 9503.12 | 17.15 | 17.15 | 2024-12-26 | 2024-12-26 | 2025-01-10 | 2025-01-10 |  | 2025-01-14 | 2025-01-15 | [11 empty] | 2025-01-16
358 | HVDC-ADOPT-SCT-0044 | E08 | 2025-01-07 | TaeHwa | Elec | Cable Tray System | Set of Anchor Bolt for Cable Tray | O | O | O | O | FOB | KOREA | Incheon | Abu Dhabi Airport |  | Deugro | A | 4 | 0 | 0 | - |  |  |  | 5797 | 5.51 | 5.8 | 2025-01-12 | 2025-01-12 | 2025-01-12 | 2025-01-12 |  | 2025-01-16 | 2025-01-16 | 2025-01-29 | 2024-02-18 | 2025-02-14 |  |  | 2025-01-16 |  |  |  | 2025-01-17
359 | HVDC-ADOPT-SCT-0035 | E08 | 2024-12-08 | Sangdong | Elec | Steel Conduit | Steel Conduit (4th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 11 | 1 | 1 | - |  |  |  | 16745 | 35.41 | 35.41 | 2024-12-08 | 2024-12-08 | 2025-01-18 | 2025-01-18 |  | 2025-01-17 | 2025-01-23 | 2025-02-05 | 2025-02-05 | 2025-02-12 | 2025-03-11 | [5 empty] | 2025-01-31
360 | HVDC-ADOPT-SCT-0034 | E08 | 2024-12-13 | LS Cable | Elec | MV, LV & Control Cable | MV,LV & CONTROL CABLE (4th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port |  | Deugro | C | 22 | 1 | 2 | - |  |  |  | 47722 | 106.89 | 106.89 | 2024-12-13 | 2024-12-13 | 2025-01-19 | 2025-01-19 |  | 2025-01-23 | 2025-01-23 | 2025-01-30 | 2025-01-30 | 2025-02-13 | [6 empty] | 2025-01-29
361 | HVDC-ADOPT-SCT-0028 | E08 | 2024-12-13 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System |  | O | O |  | FOB | Spain | Barcelona | Khalifa port |  | Deugro | C | 2 | 0 | 0 | 1 |  |  |  | 314 | 3.29 | 3.29 | 2024-12-13 | 2024-12-13 | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-01-24 |  | 2025-02-16 | 2025-02-19 | [6 empty] | 2025-01-29
362 | HVDC-ADOPT-SIM-0036-A | E04-1 | 2024-11-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC-PS026 GIS CB Bay, connection module, Accessories Surge Arrester, Voltage Transformer, Monitor |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 20 | 1 | 0 | - |  |  |  | 94202 | 649.11 | 649.11 | 2024-12-15 | 2024-12-15 | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-01-27 | [5 empty] | 2025-02-05
363 | HVDC-ADOPT-SIM-0036-B | E04-1 | 2024-11-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC-PS026 GIS CB Bay, connection module, Accessories Surge Arrester, Voltage Transformer, Monitor |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 93 | 0 | 19 | - |  |  |  | 68085 | 357.23 | 357.23 | 2024-12-15 | 2024-12-15 | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-01-27 | [5 empty] | 2025-02-05
364 | HVDC-ADOPT-SIM-0037-A | E04-1 | 2024-11-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC-PS027 GIS CB Bay, connection module, Accessories Surge Arrester, Voltage Transformer, Monitor |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 46 | 2 | 9 | - |  |  |  | 58806.4 | 388.82 | 388.82 | 2024-12-15 | 2024-12-15 | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-01-27 | [5 empty] | 2025-02-05
365 | HVDC-ADOPT-SIM-0037-B | E04-1 | 2024-11-14 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC - PS027 GIS CB Bay, connection module, Accessories Surge Arrester, Voltage Transformer, Monitor |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 2 | 0 | 1 | - |  |  |  | 9742 | 66.06 | 66.06 | 2024-12-15 | 2024-12-15 | 2025-01-24 | 2025-01-24 |  | 2025-01-24 | 2025-01-27 | [5 empty] | 2025-02-05
366 | HVDC-ADOPT-SEI-0019 | E03 | 2024-12-11 | Sumitomo | Elec | 400kV HVDC Cable System | Bonding Cable & Concentric Cable |  |  |  |  | CIF | Indonesia | Jakarta | Khalifa port |  |  | C | 3 | 1 | 0 | - |  |  |  | 1518 | 3.74 | 3.74 | 2024-12-15 | 2024-12-15 | 2025-01-24 | 2025-01-24 |  | 2025-01-30 | 2025-02-03 | [7 empty] | 2025-02-08
367 | HVDC-ADOPT-SCT-0046 | E08 | 2025-01-25 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O |  |  |  | FOB | Shanghai | China | Abu Dhabi Airport |  | Deugro | A | 4 | 0 | 0 | - |  |  |  | 62 | 0.31 | 0.31 | 2025-01-22 | 2025-01-22 | 2025-01-26 | 2025-01-26 |  | 2025-01-27 | 2025-01-27 | 2025-01-30
368 | HVDC-ADOPT-HE-0238 | E01 | 2024-12-07 | Hitachi | Elec | Main Converter | Cooling System EQ300 |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | B | 18 | 0 | 0 | - |  |  |  | 37994 | 224.8 | 224.8 | 2024-12-07 | 2024-12-07 | 2025-01-27 | 2025-01-27 |  | 2025-01-27 | 2025-01-30 |  |  |  |  | 2025-02-01
369 | HVDC-ADOPT-HE-0239 | E01 | 2024-12-07 | Hitachi | Elec | Main Converter | Cooling System EQ300 |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | B | 18 | 0 | 0 | - |  |  |  | 36724 | 224.7 | 224.7 | 2024-12-07 | 2024-12-07 | 2025-01-27 | 2025-01-27 |  | 2025-01-27 | 2025-01-30 |  | 2025-02-01
370 | HVDC-ADOPT-HE-0243 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | Diverter Switch | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 130 | 0.78 | 0.78 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 | 2025-02-15
371 | HVDC-ADOPT-HE-0253 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | Corona Shield, GSCL1300 |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 9 | 0 | 1 | - |  |  |  | 6910 | 35.58 | 35.58 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 |  | 2025-02-15
372 | HVDC-ADOPT-HE-0254 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | Racks + Capacitors | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 25 | 0 | 2 | - |  |  |  | 20665 | 72.29 | 72.29 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 | 2025-02-15
373 | HVDC-ADOPT-HE-0255 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | Spare Parts DCMKP | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 170 | 0.7 | 0.7 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 | 2025-02-15
374 | HVDC-ADOPT-HE-0256 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | DC Pole Capacitors |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 22 | 0 | 2 | - |  |  |  | 18020 | 63.98 | 63.98 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 |  |  | 2025-05-04 |  |  | 2025-02-06
375 | HVDC-ADOPT-HE-0257 | E01 | 2024-12-19 | Hitachi | Elec | Main Converter | DC Pole Capacitors Spare |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 110 | 0.45 | 0.45 | 2024-12-31 | 2024-12-31 | 2025-01-28 | 2025-01-28 |  | 2025-01-28 | 2025-01-30 | [5 empty] | 2025-02-06
376 | HVDC-ADOPT-SCT-0037 | E08 | 2024-12-21 | LS Cable | Elec | MV, LV & Control Cable | MV,LV & CONTROL CABLE (5th) | O | O | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 46 | 0 | 4 | - |  |  |  | 73346 | 90.68 | 90.68 | 2024-12-21 | 2024-12-21 | 2025-01-29 | 2025-01-29 |  | 2025-01-29 | 2025-01-30 | 2025-02-17 | 2025-02-10 | [7 empty] | 2025-02-10
377 | HVDC-ADOPT-SCT-0029 | M01 | 2024-12-09 | Xinxiang | Mech | Bulk Bag discharger Equipment | Bulk Bag discharger Equipment |  |  |  | O | FOB | CHINA | Shanghai | Khalifa port |  | Deugro | C | 11 | 0 | 1 | - |  |  |  | 3980 | 37.37 | 37.37 | 2024-12-09 | 2024-12-09 | 2025-01-29 | 2025-01-29 |  | 2025-01-30 | 2025-01-31 | [9 empty] | 2025-02-06
378 | HVDC-ADOPT-ZEN-0013 |  | 2025-01-17 | SCHRACK SECONET | Elec |  | Fire Alarm and Aspiration Sytem |  |  |  |  | CIF | Austria | Viena | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 238 | 1.82 | 1.82 | 2025-01-30 | 2025-01-30 | 2025-01-30 | 2025-01-30 |  | 2025-02-03 | 2025-02-03 | [11 empty] | 2025-02-05
379 | HVDC-ADOPT-HE-0290 | E01 | 2025-01-28 | Hitachi | Elec | Main Converter | Fiber Optic Cable | O |  |  |  | DAP | UK | England | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 1 | 0 | 0 | - |  |  |  | 1135 | 1.74 | 1.74 | 2025-02-03 | 2025-02-03 | 2025-02-04 | 2025-02-04 |  | 2025-02-04 | 2025-02-04 | 2025-02-06
380 | HVDC-ADOPT-SEI-0017-03 | E03 | 2025-01-21 | Sumitomo | Elec | 400kV HVDC Cable System | Part for Oil Pressure Tank |  |  |  |  | CIF | JAPAN | Osaka | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 28 | 0.14 | 0.14 | 2025-02-04 | 2025-02-04 | 2025-02-05 | 2025-02-05 |  | 2025-02-05 | 2025-02-05 | [7 empty] | 2025-02-08
381 | HVDC-ADOPT-HE-0233 | E01 | 2024-11-21 | Hitachi | Elec | Main Converter | Cooling Pumps |  |  |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 6 | 0 | 4 | - |  |  |  | 10554 | 130.44 | 130.44 | 2024-11-21 | 2024-11-21 | 2025-01-03 | 2025-01-03 |  | 2025-01-04 | 2025-01-28 |  |  |  | 2025-02-14
382 | HVDC-ADOPT-HE-0236 | E01 | 2024-11-21 | Hitachi | Elec | Main Converter | Earthing & Instrument Kits | O | O | O | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 12 | 0 | 3 | - |  |  |  | 4800 | 34.28 | 34.28 | 2024-11-21 | 2024-11-21 | 2025-01-03 | 2025-01-03 |  | 2025-01-04 | 2025-01-28 |  |  |  |  | 2025-02-14
383 | HVDC-ADOPT-SCT-0048 | E08 | 2025-02-04 | Dong Yang | Elec | Cathodic Protection | Cathodic Protection Systems (3rd) |  | O |  |  | FOB | KOREA | Incheon | Abu Dhabi Airport |  | Deugro | A | 1 | 0 | 0 | - |  |  |  | 912 | 2.03 | 2.03 | 2025-02-04 | 2025-02-04 | 2025-02-06 | 2025-02-06 |  | 2025-02-07 | 2025-02-07 |  |  | 2025-02-17 | [6 empty] | 2025-02-10
384 | HVDC-ADOPT-SEI-0017-01 | E03 | 2024-12-27 | Sumitomo | Elec | 400kV HVDC Cable System | Cable Accessories |  |  |  |  | CIF | JAPAN | Kobe | Khalifa port |  |  | C | 52 | 0 | 0 | - |  |  |  | 11014 | 74.89 | 74.89 | 2024-12-27 | 2024-12-27 | 2025-01-29 | 2025-01-29 |  | 2025-02-10 | 2025-02-10 | [7 empty] | 2025-02-20
385 | HVDC-ADOPT-SCT-0038 | E08 | 2025-01-05 | TaeHwa | Elec | Cable Tray System | Cable Tray System (11th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port |  | Deugro | C | 39 | 1 | 6 | - |  |  |  | 64093 | 194.05 | 194.05 | 2025-01-05 | 2025-01-05 | 2025-02-07 | 2025-02-07 |  | 2025-02-11 | 2025-02-11 | 2025-02-26 | 2025-02-28 | 2025-04-28 | 2025-04-21 | [5 empty] | 2025-03-19
386 | HVDC-ADOPT-ZEN-0006 |  | 2024-09-30 | FIRE EATER |  |  | Fire Extinguishing System |  |  |  |  | CIF | Denmark | Copenhagen | Khalifa port |  |  | C | 40 | 3 | 0 | - |  |  |  | 35796 | 41.52 | 41.52 | 2024-12-07 | 2024-12-07 | 2025-02-09 | 2025-02-09 |  | 2025-02-12 | 2025-02-14 | [11 empty] | 2025-02-15
387 | HVDC-ADOPT-HE-0302 | E01 | 2025-02-11 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Malmoe | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 3 | 0 | 0 | - |  |  |  | 1950 | 15.14 | 15.14 | 2025-02-11 | 2025-02-11 | 2025-02-13 | 2025-02-13 |  | 2025-02-14 | 2025-02-14 | 2025-02-19
388 | HVDC-ADOPT-HE-0307 | E01 | 2025-02-12 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Malmoe | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 4 | 0 | 0 | - |  |  |  | 2600 | 20.19 | 20.19 | 2025-02-12 | 2025-02-12 | 2024-02-14 | 2024-02-14 |  | 2024-02-14 | 2024-02-14 | 2025-02-19
389 | HVDC-ADOPT-SCT-0056 | E08 | 2025-02-11 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O |  |  | FOB | CHINA | Shanghai | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 502 | 1.67 | 1.67 | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-02-14 | 2025-02-14 | 2025-02-21 | [8 empty] | 2025-02-10
390 | HVDC-ADOPT-SCT-0039 | E08 | 2025-01-11 | Sangdong | Elec | Earthing & Lightning Protection Material | Earthing & Lightning Protection Material (2nd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1220 | 3.78 | 3.78 | 2025-01-11 | 2025-01-11 | 2025-02-19 | 2025-02-19 |  | 2025-02-19 | 2025-02-19 | 2025-04-24 | 2025-02-28 | 2025-03-31 | 2025-04-06 | [5 empty] | 2025-03-18
391 | HVDC-ADOPT-HE-0267 | E01 | 2025-02-10 | Hitachi | Elec | Main Converter | External Piping |  | O |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 17320 | 117.2 | 117.2 | 2025-02-14 | 2025-02-14 | 2025-02-18 | 2025-02-18 |  | 2025-02-19 | 2025-02-19 |  |  | 2025-02-21 | [6 empty] | 2025-02-20
392 | HVDC-ADOPT-SCT-0042 | E08 | 2025-01-18 | TaeHwa | Elec | Cable Tray System | Cable Tray System (12th) | O | O | O |  | FOB | KOREA | Busan Port | Khalifa port |  | Deugro | C | 11 | 1 | 2 | - |  |  |  | 18613 | 75.46 | 75.46 | 2025-01-18 | 2025-01-18 | 2025-02-21 | 2025-02-21 |  | 2025-02-24 | 2025-02-24 | 2025-03-03 | 2025-03-03 | 2025-04-28 | [6 empty] | 2025-03-01
393 | HVDC-ADOPT-HE-0245 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 11 | 0 | 2 | - |  |  |  | 14735 | 64.16 | 64.16 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 | 2025-03-19
394 | HVDC-ADOPT-HE-0246 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1088 | 5.32 | 5.32 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 |  |  |  |  | 2025-03-01
395 | HVDC-ADOPT-HE-0247 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | Spare Parts DSC | O |  |  |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 1038 | 5.89 | 5.89 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 |  |  |  |  | 2025-03-01
396 | HVDC-ADOPT-HE-0248 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 15 | 1 | 2 | - |  |  |  | 16690 | 85.65 | 85.65 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 | 2025-03-18
397 | HVDC-ADOPT-HE-0249 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | n° 6 Singlepole DSC STA 145 kV & Insulator |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1045 | 5.32 | 5.32 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 |  |  |  |  | 2025-03-01
398 | HVDC-ADOPT-HE-0250 | E01 | 2024-12-16 | Hitachi | Elec | Main Converter | Spare Parts DSC |  |  | O |  | DAP | Italy | Venezia | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 916 | 5.95 | 5.95 | 2024-12-16 | 2024-12-16 | 2025-02-25 | 2025-02-25 |  | 2025-02-25 | 2025-02-27 |  |  |  |  | 2025-03-01
399 | HVDC-ADOPT-SIM-0042 A | E04-1 | 2024-12-05 | Siemens | Elec | 400kV and 132kV New Converter GIS | 32kV GIB GHDC PS029 |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 27 | 0 | 17 | - |  |  |  | 30518 | 254 | 254 | 2025-01-19 | 2025-01-19 | 2025-02-26 | 2025-02-26 |  | 2025-02-28 | 2025-03-01 | [5 empty] | 2025-03-17
400 | HVDC-ADOPT-SIM-0042 B | E04-1 | 2024-12-06 | Siemens | Elec | 400kV and 132kV New Converter GIS | 32kV GIB GHDC PS029 |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 26 | 1 | 0 | - |  |  |  | 23140 | 170.07 | 170.07 | 2025-01-19 | 2025-01-19 | 2025-02-26 | 2025-02-26 |  | 2025-02-28 | 2025-03-01 | [5 empty] | 2025-03-17
401 | HVDC-ADOPT-SIM-0050 | E04-1 | 2024-12-10 | Siemens | Elec | 400kV and 132kV New Converter GIS | 132 kV GIS DAS Spare Cable Feeder_PS031 |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 10 | 1 | 1 | - |  |  |  | 8261.2 | 47.66 | 47.66 | 2025-01-23 | 2025-01-23 | 2025-02-26 | 2025-02-26 |  | 2025-02-28 | 2025-03-03 |  |  | 2025-04-28 | [6 empty] | 2025-04-09
402 | HVDC-ADOPT-SIM-0053 | E04-1 | 2024-12-13 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kV Shuweihat HV Test Bushing_ GIS-PS034 | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 4 | 1 | 0 | - |  |  |  | 998.5 | 7.97 | 7.97 | 2025-01-20 | 2025-01-20 | 2025-02-26 | 2025-02-26 |  | 2025-02-28 | 2025-03-01 | 2025-04-19
403 | HVDC-ADOPT-SIM-0052 | E04-1 | 2024-12-12 | Siemens | Elec | 400kV and 132kV New Converter GIS | 132 kV GIS AL Ghallan Spare cable feeder PS033 |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 10 | 1 | 1 | - |  |  |  | 6979.5 | 40.07 | 40.07 | 2025-01-19 | 2025-01-19 | 2025-02-26 | 2025-02-26 |  | 2025-02-28 | 2025-03-05
404 | HVDC-ADOPT-HE-0216 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | UMD Batteries | O |  |  |  | DAP | FRANCE | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 2910 | 8.3 | 8.3 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 | 2025-04-20
405 | HVDC-ADOPT-HE-0220 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | Side Shield Brackets | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 100 | 0.26 | 0.26 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 | 2025-04-12
406 | HVDC-ADOPT-HE-0221 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | Side Shield Brackets |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 140 | 0.26 | 0.26 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 |  | 2025-04-11
407 | HVDC-ADOPT-HE-0222 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | Side Shield Brackets |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 250 | 0.52 | 0.52 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 | [5 empty] | 2025-04-09
408 | HVDC-ADOPT-HE-0217 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | UMD Batteries |  |  | O |  | DAP | FRANCE | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 3360 | 6 | 6 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 |  | 2025-04-20
409 | HVDC-ADOPT-HE-0218 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | UMD Batteries |  | O |  |  | DAP | FRANCE | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 2910 | 6 | 6 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 | [9 empty] | 2025-04-25
410 | HVDC-ADOPT-HE-0219 | E01 | 2024-10-10 | Hitachi | Elec | Main Converter | UMD Batteries |  |  |  | O | DAP | FRANCE | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 3660 | 6 | 6 | 2024-10-10 | 2024-10-10 | 2025-03-03 | 2025-03-03 |  | 2025-03-05 | 2025-03-06 | [9 empty] | 2025-04-25
411 | HVDC-ADOPT-HE-0318-1 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 5925 | 44.9 | 44.9 | 2025-03-04 | 2025-03-04 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-06 | 2025-03-11
412 | HVDC-ADOPT-HE-0318-2 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 5830 | 42.77 | 42.77 | 2025-03-04 | 2025-03-04 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-06 | 2025-03-11
413 | HVDC-ADOPT-HE-0318-3 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 6757 | 51.27 | 51.27 | 2025-03-04 | 2025-03-04 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-06 | 2025-03-11
414 | HVDC-ADOPT-SCT-0063 | E08 | 2025-03-06 | TaeHwa | Elec | Cable Tray System | Cable Tray System (14th) | O |  | O |  | FOB | KOREA | Incheon | Abu Dhabi Airport |  | Deugro | A | 2 | 0 | 0 | - |  |  |  | 70 | 0.16 | 0.16 | 2025-03-06 | 2025-03-06 | 2025-03-07 | 2025-03-07 |  | 2025-03-07 | 2025-03-07 | 2025-03-27 | 2025-03-14
415 | HVDC-ADOPT-HE-0318-4 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 5 | 0 | 0 | - |  |  |  | 3380 | 25.64 | 25.64 | 2025-03-04 | 2025-03-04 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-06 | 2025-03-11
416 | HVDC-ADOPT-ZEN-0008 |  | 2024-10-23 | SPP PUMPS |  |  | Fire Pump Set |  |  |  |  | CIF | UK | Felixstowe | Khalifa port |  |  | C | 8 | 0 | 2 | - |  |  |  | 14897 | 58.6 | 58.6 | 2025-01-18 | 2025-01-18 | 2025-02-28 | 2025-02-28 |  | 2025-03-07 | 2025-03-09 | [11 empty] | 2025-03-11
417 | HVDC-ADOPT-SCT-0043 | E08 | 2025-01-27 | Dong-A Bestech | Elec | Cable Gland | Cable Gland 1st | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 4490 | 11.93 | 11.93 | 2025-01-27 | 2025-01-27 | 2025-03-07 | 2025-03-07 |  | 2025-03-10 | 2025-03-11 | 2025-03-18 | 2025-03-18 | 2025-04-01 | 2025-03-31 | [5 empty] | 2025-03-17
418 | HVDC-ADOPT-SCT-0045 | M01 | 2025-01-26 | WILO Pump Korea | Mech | General Seviece Pump | Portable water Pump |  | O | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1140 | 4.75 | 4.75 | 2025-01-27 | 2025-01-27 | 2025-03-07 | 2025-03-07 |  | 2025-03-10 | 2025-03-11 |  | 2025-03-18 | 2025-04-01 | [6 empty] | 2025-03-17
419 | HVDC-ADOPT-SCT-0047 | E08 | 2025-01-30 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O |  |  |  | FOB | CHINA | Shanghai | Khalifa port | HMM | Deugro | C | 6 | 1 | 0 | - |  |  |  | 2402 | 16.59 | 16.59 | 2025-01-30 | 2025-01-30 | 2025-03-07 | 2025-03-07 |  | 2025-03-07 | 2025-03-07 | 2025-03-18
420 | HVDC-ADOPT-HE-0265 | E01 | 2025-01-23 | Hitachi | Elec | Main Converter | Fiber Optic Cables - MULTIMODE |  | O |  |  | DAP | United Kingdom | Felixstowe | Khalifa port | Maersk | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 6619 | 14.9 | 14.9 | 2025-01-28 | 2025-01-28 | 2025-03-07 | 2025-03-07 |  | 2025-03-07 | 2025-03-10 |  |  | 2025-03-27 | [6 empty] | 2025-03-18
421 | HVDC-ADOPT-HE-0266 | E01 | 2025-01-23 | Hitachi | Elec | Main Converter | Fiber Optic Cables - MULTIMODE | O |  |  |  | DAP | United Kingdom | Felixstowe | Khalifa port | Maersk | Scan Global Logistics AB | C | 8 | 0 | 0 | - |  |  |  | 6348 | 14.2 | 14.2 | 2025-01-28 | 2025-01-28 | 2025-03-07 | 2025-03-07 |  | 2025-03-07 | 2025-03-10 | 2025-03-28
422 | HVDC-ADOPT-SEI-0020 | E03 | 2025-02-20 | Sumitomo | Elec | 400kV HVDC Cable System | Omline Monitoring System | O | O |  |  | CIF | GERMANY | Frankfurt | Abu Dhabi Airport |  |  | A | 5 | 0 | 0 | - |  |  |  | 1882 | 10.52 | 10.52 | 2025-02-28 | 2025-02-28 | 2025-03-09 | 2025-03-09 |  | 2025-03-10 | 2025-03-10 | [7 empty] | 2025-03-11
423 | HVDC-ADOPT-HE-0317-1 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 6560 | 51.27 | 51.27 | 2025-03-07 | 2025-03-07 | 2025-03-11 | 2025-03-11 |  | 2025-03-11 | 2025-03-11 | 2025-03-13
424 | HVDC-ADOPT-HE-0317-2 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 6165 | 47.02 | 47.02 | 2025-03-07 | 2025-03-07 | 2025-03-13 | 2025-03-13 |  | 2025-03-13 | 2025-03-13 | 2025-03-14
425 | HVDC-ADOPT-HE-0317-3 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | SWEDEN | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 6655 | 51.27 | 51.27 | 2025-03-07 | 2025-03-07 | 2025-03-14 | 2025-03-14 |  | 2025-03-14 | 2025-03-14 | 2025-03-17
426 | HVDC-ADOPT-ZEN-0006 A |  | 2024-09-30 | FIRE EATER |  |  | Fire Extinguishing System |  |  |  |  | CIF | Denmark | Copenhagen | Khalifa port |  |  | C | 42 | 3 | 0 | - |  |  |  | 73080 | 78.61 | 78.61 | 2024-12-19 | 2024-12-19 | 2025-03-09 | 2025-03-09 |  | 2025-03-13 | 2025-03-13 | [11 empty] | 2025-03-14
427 | HVDC-ADOPT-SIM-0044 | E04-1 | 2024-10-24 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400kv and 132kv GIS - SHDC - PS024 GIB -IMO DG cargo | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port |  | Alpha Maritime | C | 17 | 0 | 2 | - |  |  |  | 4380 | 27.56 | 27.56 | 2025-01-06 | 2025-01-06 | 2025-03-12 | 2025-03-12 |  | 2025-03-12 | 2025-03-14 | 2025-03-28
428 | HVDC-ADOPT-SIM-0057 | E04-1 | 2024-12-20 | Siemens | Elec | 400kV and 132kV New Converter GIS | 19LT-SCT-SE2-TR-00560 : PDMS PO# 4510190879 | O | O | O | O | CIF | Italy | Malpensa | Abu Dhabi Airport |  |  | A | 15 | 0 | 0 | - |  |  |  | 3292 | - | 3.29 | 2025-03-08 | 2025-03-08 | 2025-03-10 | 2025-03-10 |  | 2025-03-17 | 2025-03-17 | 2025-04-21 |  | 2025-04-01 |  | 2025-03-20 |  |  |  |  | 2025-03-20
429 | HVDC-ADOPT-SCT-0069 | E08 | 2025-03-15 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System (Lighting Fixture) | O |  |  |  | FOB | Spain | Barcelona | Abu Dhabi Airport |  |  | A | 4 | 0 | 0 | - |  |  |  | 913 | 5.73 | 5.73 | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-03-15 |  | 2025-03-17 | 2025-03-17 | 2025-04-05
430 | HVDC-ADOPT-HE-0319-1 | E01 | 2025-03-12 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 10 | 0 | 0 | - |  |  |  | 4857 | 37.79 | 37.79 | 2025-03-14 | 2025-03-14 | 2025-03-17 | 2025-03-17 |  | 2025-03-18 | 2025-03-18 | 2025-03-21
431 | HVDC-ADOPT-HE-0319-2 | E01 | 2025-03-12 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 9 | 0 | 0 | - |  |  |  | 4785 | 35.52 | 35.52 | 2025-03-14 | 2025-03-14 | 2025-03-18 | 2025-03-18 |  | 2025-03-19 | 2025-03-19 | 2025-03-21
432 | HVDC-ADOPT-HE-0319-3 | E01 | 2025-03-12 | Hitachi | Elec | Main Converter | CONTROL CUBICLE | O |  |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 8 | 0 | 0 | - |  |  |  | 1086 | 4.9 | 4.9 | 2025-03-14 | 2025-03-14 | 2025-03-17 | 2025-03-17 |  | 2025-03-18 | 2025-03-18 | 2025-03-21
433 | HVDC-ADOPT-SCT-0065 | E08 | 2025-03-11 | JEONO ELECTRIC | Elec | Terminal Lug | Terminal Lug | O | O | O |  | FOB | KOREA | Incheon | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1432 | 3.29 | 3.29 | 2025-03-16 | 2025-03-16 | 2025-03-18 | 2025-03-18 |  | 2025-03-18 | 2025-03-18 | 2025-04-16 | 2025-04-14 |  |  |  | 2025-03-25 |  |  |  | 2025-04-09
434 | HVDC-ADOPT-SCT-0054 | E08 | 2025-02-26 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O | O | O | O | FOB | CHINA | Shekou | Khalifa port | CMA | Deugro | C | 26 | 0 | 2 | - |  |  |  | 10410 | 73.49 | 73.49 | 2025-02-26 | 2025-02-26 | 2025-03-18 | 2025-03-18 |  | 2025-03-24 | 2025-03-24 | 2025-04-09 | 2025-04-08 |  |  |  | 2025-03-29 |  |  |  | 2025-04-09
435 | HVDC-ADOPT-HE-0268 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator Bil 250 |  | O |  | O | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 1 | 0 | - |  |  |  | 600 | 1.42 | 1.42 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 |  |  | 2025-04-14 | 2025-04-21 | [5 empty] | 2025-04-10
436 | HVDC-ADOPT-HE-0269 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator Bil 250 Spare |  | O |  | O | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 110 | 0.26 | 0.26 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 |  |  | 2025-04-14 | 2025-04-21 | [5 empty] | 2025-04-10
437 | HVDC-ADOPT-HE-0270 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator |  |  | O |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 300 | 0.71 | 0.71 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 |  | 2025-04-11
438 | HVDC-ADOPT-HE-0271 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator Spare |  |  | O |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 55 | 0.13 | 0.13 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 |  | 2025-04-11
439 | HVDC-ADOPT-HE-0272 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 300 | 0.71 | 0.71 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 | 2025-04-17
440 | HVDC-ADOPT-HE-0273 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator Spare | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 55 | 0.13 | 0.13 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 | 2025-04-17
441 | HVDC-ADOPT-HE-0274 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 361.5 | 1.02 | 1.02 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 | 2025-04-17
442 | HVDC-ADOPT-HE-0275 | E01 | 2025-02-24 | Hitachi | Elec | Main Converter | Insulator Bil 250 Spare | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 77.5 | 0.19 | 0.19 | 2025-02-24 | 2025-02-24 | 2025-03-22 | 2025-03-22 |  | 2025-03-25 | 2025-03-26 | 2025-04-17
443 | HVDC-ADOPT-HE-0326 | E01 | 2025-03-18 | Hitachi | Elec | Main Converter | CONTROL CUBICLE |  | O |  |  | DAP | Denmark | Billund | Abu Dhabi Airport |  | Scan Global Logistics AB | A | 2 | 0 | 0 | - |  |  |  | 2160 | 14.5 | 14.5 | 2025-03-21 | 2025-03-21 | 2025-03-25 | 2025-03-25 |  | 2025-03-26 | 2025-03-26 | [9 empty] | 2025-03-27
444 | HVDC-ADOPT-HE-0291 | E01 | 2025-02-06 | Hitachi | Elec | Main Converter | Wall Bushings-GSCL1300 |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 1 | - |  |  |  | 1625 | 7.17 | 7.17 | 2025-02-06 | 2025-02-06 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-03-27 |  | 2025-04-11
445 | HVDC-ADOPT-HE-0292 | E01 | 2025-02-13 | Hitachi | Elec | Main Converter | External Pipe Coolers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 8 | 0 | 4 | - |  |  |  | 19210 | 135.42 | 135.42 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-03-27 | 2025-04-15
446 | HVDC-ADOPT-HE-0298 | E01 | 2025-02-13 | Hitachi | Elec | Main Converter | HMD62 RH+T Duct Transmitter |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 30 | 0.3 | 0.3 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-03-27 |  | 2025-04-11 |  |  | 2025-04-12
447 | HVDC-ADOPT-HE-0299 | E01 | 2025-02-13 | Hitachi | Elec | Main Converter | HMD62 RH+T Duct Transmitter | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 31 | 0.3 | 0.3 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-03-27 |  |  |  |  | 2025-04-12
448 | HVDC-ADOPT-HE-0300 | E01 | 2025-02-13 | Hitachi | Elec | Main Converter | HMD62 RH+T Duct Transmitter |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | Maersk | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 52 | 0.4 | 0.4 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-03-27 |  |  |  |  | 2025-04-10
449 | HVDC-ADOPT-SCT-0055 | E08 | 2025-02-18 | TaeHwa | Elec | Cable Tray System | Cable Tray System (13th) | O | O | O |  | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 60 | 1 | 9 | - |  |  |  | 113708 | 326.32 | 326.32 | 2025-02-18 | 2025-02-18 | 2025-03-28 | 2025-03-29 |  | 2025-03-26 | 2025-03-27 | 2025-04-11 | 2025-04-14 | 2025-04-16 | [6 empty] | 2025-04-08
450 | HVDC-ADOPT-SCT-0052 | E08 | 2025-02-18 | Dong-A Bestech | Elec | Cable Gland | Cable Gland 2nd | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 0 | 1 | - |  |  |  | 8605 | 24.56 | 24.56 | 2025-02-18 | 2025-02-18 | 2025-03-28 | 2025-03-28 |  | 2025-03-26 | 2025-03-28 | 2025-04-09 | 2025-04-14 |  | 2025-04-21 |  | 2025-04-09 |  |  |  | 2025-04-09
451 | HVDC-ADOPT-SCT-0051 | E08 | 2025-02-18 | Dong Yang | Elec | Cathodic Protection | Cathodic Protection Systems (4th) | O |  | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 3 | 1 | 0 | - |  |  |  | 1724 | 4.27 | 4.27 | 2025-02-18 | 2025-02-18 | 2025-03-28 | 2025-03-29 |  | 2025-03-26 | 2025-03-29 | 2025-04-11 | 2025-04-14 | [7 empty] | 2025-05-12
452 | HVDC-ADOPT-SCT-0050 | E08 | 2025-02-18 | Sangdong | Elec | Earthing & Lightning Protection Material | Earthing & Lightning Protection Material (3rd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 6 | 1 | 0 | - |  |  |  | 3980 | 9.68 | 9.68 | 2025-02-18 | 2025-02-18 | 2025-03-28 | 2025-03-29 |  | 2025-03-26 | 2025-03-27 | 2025-04-09 | 2025-04-14 |  | 2025-04-21 | [5 empty] | 2025-04-09
453 | HVDC-ADOPT-HE-0301-1 | E01 | 2025-02-26 | Hitachi | Elec | Main Converter | Insulators / Hings |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 996 | 1.6 | 1.6 | 2025-02-26 | 2025-02-26 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-02 | [5 empty] | 2025-04-05
454 | HVDC-ADOPT-HE-0311-1 | E01 | 2025-02-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 51 | 0 | 3 | - |  |  |  | 8794 | 48.1 | 48.1 | 2025-02-26 | 2025-02-26 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-02 |  |  |  |  | 2025-04-05
455 | HVDC-ADOPT-HE-0308 | E01 | 2025-02-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 250x6mm |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 24 | 0 | 0 | - |  |  |  | 6273 | 45.4 | 45.4 | 2025-02-26 | 2025-02-26 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-02 |  |  |  |  | 2025-04-05
456 | HVDC-ADOPT-HE-0309-1 | E01 | 2025-02-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 19 | 0 | 0 | - |  |  |  | 3751 | 20.9 | 20.9 | 2025-02-26 | 2025-02-26 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-02 |  |  |  |  | 2025-04-05
457 | HVDC-ADOPT-HE-0310-1 | E01 | 2025-02-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 26 | 0 | 0 | - |  |  |  | 4099 | 21.5 | 21.5 | 2025-02-26 | 2025-02-26 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-02 |  |  |  |  | 2025-04-05
458 | HVDC-ADOPT-SCT-0053 | E08 | 2025-01-23 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O | O | O | O | FOB | Spain | Barcelona | Khalifa port | MSC | Deugro | C | 37 | 0 | 1 | - |  |  |  | 5302 | 48.26 | 48.26 | 2025-02-27 | 2025-02-27 | 2025-04-01 | 2025-04-01 |  | 2025-04-03 | 2025-04-04 | 2025-04-21 | 2025-04-22 | [7 empty] | 2025-04-21
459 | HVDC-ADOPT-SCT-0061 | E08 | 2025-03-31 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting Fixture | O | O | O | O | FOB | Spain | Vitoria-Gasteiz | Abu Dhabi Airport |  | Deugro | A | 4 | 0 | 0 | - |  |  |  | 406 | 3.42 | 3.42 | 2025-03-28 | 2025-03-28 | 2025-04-04 | 2025-04-04 |  | 2025-04-04 | 2025-04-04 | 2025-05-01 | 2025-04-29 | [7 empty] | 2025-04-17
460 | HVDC-ADOPT-SIM-0066 | E04-1 | 2025-01-23 | Siemens | Elec | 400kV and 132kV New Converter GIS | Statron Battery | O |  | O |  | CIF | India | Visakhapatnam | Khalifa port | MSC |  | C | 32 | 1 | 0 | - |  |  |  | 5028 | 6.58 | 6.58 | 2025-02-26 | 2025-02-26 | 2025-03-31 | 2025-03-31 |  | 2025-04-02 | 2025-04-07 | 2025-04-19 | 2025-04-19
461 | HVDC-ADOPT-SCT-0079 | E08 | 2025-03-27 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O | O | O | O | FOB | Spain | Vitoria-Gasteiz | Abu Dhabi Airport |  | Deugro | A | 4 | 0 | 0 | - |  |  |  | 257.4 | 2.54 | 2.54 | 2025-03-27 | 2025-03-27 | 2025-04-01 | 2025-04-01 |  | 2025-04-07 | 2025-04-07 |  | 2025-04-29 | 2025-04-13 | [6 empty] | 2025-04-08
462 | HVDC-ADOPT-SIM-0056 | E04-1 | 2024-12-30 | Siemens | Elec | 400kV and 132kV New Converter GIS | SHDC - GIS Spares -PS037 GIS spares | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 44 | 1 | 8 | - |  |  |  | 39666.8 | 311.11 | 311.11 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-04-07 | 2025-04-24
463 | HVDC-ADOPT-SIM-0061 | E04-1 | 2025-01-09 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRDC Spares PS041 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 40 | 1 | 8 | - |  |  |  | 39693.5 | 315.21 | 315.21 | 2025-02-13 | 2025-02-13 | 2025-03-23 | 2025-03-23 |  | 2025-03-25 | 2025-04-07 | [5 empty] | 2025-04-14
464 | HVDC-ADOPT-HE-0334 | E01 | 2025-02-25 | Hitachi | Elec | Main Converter | NYTRO 10XN Transformer Oil | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port |  | DANMAR LINES | C | 8 | 8 | 0 | - |  |  |  | 172180 | 306.37 | 306.37 | 2025-02-22 | 2025-02-22 | 2025-04-01 | 2025-04-01 |  | 2025-04-02 | 2024-04-08 | 2025-04-18
465 | HVDC-ADOPT-SIM-0062 | E04-1 | 2025-01-03 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC - GIBs - PS042 |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 1 | 1 | 0 | - |  |  |  | 815 | 3.5 | 3.5 | 2025-02-20 | 2025-02-20 | 2025-03-28 | 2025-03-28 |  | 2025-04-08 | 2025-04-09
466 | HVDC-ADOPT-PPL-0016 | E02 | 2025-03-18 | Prysmian | Elec | 320kV HVDC Cable System | MINISUB FOC Subsea Fibre Optic Cable (up to 96 fibres) FO Accessories |  |  |  |  | CIF | GERMANY | Frankfurt | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 210 | 0.73 | 0.73 | 2025-04-04 | 2025-04-04 | 2025-04-05 | 2025-04-05 |  | 2025-04-10 | 2025-04-10 | [7 empty] | 2025-04-15
467 | HVDC-ADOPT-SCT-0090 | E08 | 2025-04-05 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System |  |  |  | O | FOB | CHINA | Zhenzhen | Abu Dhabi Airport |  | Deugro | A | 20 | 0 | 0 | - |  |  |  | 86 | 0.56 | 0.56 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-04-06 |  | 2025-04-08 | 2025-04-08 |  |  |  | 2025-04-12 | [5 empty] | 2025-04-09
468 | HVDC-ADOPT-HE-0301-2 | E01 | 2025-03-10 | Hitachi | Elec | Main Converter | Insulators / Hings |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 901 | 2.2 | 2.2 | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 |  | 2025-04-07 | 2025-04-09 | [5 empty] | 2025-04-12
469 | HVDC-ADOPT-HE-0311-2 | E01 | 2025-03-10 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 0 | - |  |  |  | 1234 | 6.8 | 6.8 | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 |  | 2025-04-07 | 2025-04-09 | 2025-04-23
470 | HVDC-ADOPT-HE-0309-2 | E01 | 2025-03-10 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 7 | 0 | 0 | - |  |  |  | 1742 | 9.5 | 9.5 | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 |  | 2025-04-07 | 2025-04-09 |  |  |  |  | 2025-04-23
471 | HVDC-ADOPT-HE-0310-2 | E01 | 2025-03-10 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 9 | 0 | 0 | - |  |  |  | 2053 | 11.6 | 11.6 | 2025-03-10 | 2025-03-10 | 2025-04-07 | 2025-04-07 |  | 2025-04-07 | 2025-04-09 |  |  |  |  | 2025-04-23
472 | HVDC-ADOPT-HE-0314 | E01 | 2025-02-27 | Hitachi | Elec | Main Converter | CONTROL CUBICLE |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 7 | 0 | 1 | - |  |  |  | 4550 | 35.3 | 35.3 | 2025-02-27 | 2025-02-27 | 2025-04-07 | 2025-04-07 |  | 2025-04-07 | 2025-04-17 |  |  |  |  | 2025-04-24
473 | HVDC-ADOPT-SIM-0054 | E04-1 | 2024-12-13 | Siemens | Elec | 400kV and 132kV New Converter GIS | 400 kV Shuweihat HV Test Bushing_PS035_45188766 SHDC DG | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 1 | 0 | 0 | - |  |  |  | 3.1 | 0.02 | 0.02 | 2025-02-20 | 2025-02-20 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-16 | 2025-04-22
474 | HVDC-ADOPT-SIM-0055 | E04-1 | 2024-12-30 | Siemens | Elec | 400kV and 132kV New Converter GIS | GIS Spares - PS036 SHDC-DG | O |  |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 8 | 1 | 0 | - |  |  |  | 171 | 0.51 | 0.51 | 2025-02-20 | 2025-02-20 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | 2025-04-16 | 2025-04-22
475 | HVDC-ADOPT-SIM-0065 | E04-1 | 2025-01-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRDC - Test Bushing -PS039 |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 4 | 1 | 0 | - |  |  |  | 1108.5 | 8.63 | 8.63 | 2025-02-20 | 2025-02-20 | 2025-03-28 | 2025-03-28 |  | 2025-04-08 | 2025-04-10 |  | 2025-05-09
476 | HVDC-ADOPT-HE-0327 | E01 | 2025-03-13 | Hitachi | Elec | Main Converter | UPS SYSTEM BATTERIES | O | O |  |  | DAP | India | Visakhapatnam | Khalifa port | MSC |  | C | 196 | 0 | 8 | - |  |  |  | 172256 | 114.3 | 172.26 | 2025-03-13 | 2025-03-13 | 2025-04-01 | 2025-04-01 |  | 2025-04-02 | 2025-04-04 | [12 empty] | 2025-05-08
477 | HVDC-ADOPT-SCT-0049 | E08 | 2025-03-01 | LS Cable | Elec | MV, LV & Control Cable | MV,LV & CONTROL CABLE (6th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 295 | 14 | 18 | - |  |  |  | 541644 | 682.29 | 682.29 | 2025-03-01 | 2025-03-01 | 2025-04-08 | 2025-04-08 |  | 2025-04-11 | 2025-04-14 | 2025-05-07 | 2025-05-12 | [7 empty] | 2025-05-05
478 | HVDC-ADOPT-SCT-0057 | E08 | 2025-03-03 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O | O | O | FOB | CHINA | Shanghai | Khalifa port | HMM | Deugro | C | 9 | 0 | 1 | - |  |  |  | 4456 | 14.31 | 14.31 | 2025-03-01 | 2025-03-01 | 2025-04-08 | 2025-04-08 |  | 2025-04-11 | 2025-04-14 | 2025-04-23 | 2025-04-19 | [7 empty] | 2025-04-17
479 | HVDC-ADOPT-HE-0335 | E01 | 2025-03-04 | Hitachi | Elec | Main Converter | NYTRO 10XN Transformer Oil | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port |  | DANMAR LINES | C | 8 | 8 | 0 | - |  |  |  | 173120 | 306.37 | 306.37 | 2025-02-22 | 2025-02-22 | 2025-04-11 | 2025-04-11 |  | 2025-04-11 | 2025-04-18 | 2025-04-24
480 | HVDC-ADOPT-ZEN-0014 |  | 2025-01-20 | FIRE EATER |  |  | Fire Extinguishing System |  |  |  |  | CIF | Denmark | Copenhagen | Khalifa port |  |  | C | 95 | 7 | 0 | - |  |  |  | 121226 | 137.39 | 137.39 | 2025-02-08 | 2025-02-08 | 2025-04-11 | 2025-04-11 |  | 2025-04-18 | 2025-04-18 | [11 empty] | 2025-04-23
481 | HVDC-ADOPT-SCT-0091 | E08 | 2025-04-11 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O | O | O |  | FOB | Spain | Barcelona | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 271 | 2.88 | 2.88 | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-04-17 | 2025-04-17 | 2025-05-01 | 2025-04-29 | [7 empty] | 2025-04-19
482 | HVDC-ADOPT-ZEN-0016 |  | 2025-01-30 | APRECO |  |  | Pressure Relief Dampers |  |  |  |  | CIF | United Kingdom | London | Khalifa port |  |  | C | 9 | 0 | 1 | - |  |  |  | 5211 | 24.8 | 24.8 | 2025-03-13 | 2025-03-13 | 2025-04-12 | 2025-04-12 |  | 2025-04-17 | 2025-04-17 | [11 empty] | 2025-04-18
483 | HVDC-ADOPT-HE-0312 | E01 | 2025-04-13 | Hitachi | Elec | Main Converter | Capacitor Bank | O |  | O |  | DAP | Italy | Milan | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 1327 | 5.13 | 5.13 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-04-13 |  | 2025-04-17 | 2025-04-17 | 2025-04-20 | 2025-04-20
484 | HVDC-ADOPT-HE-0313 | E01 | 2025-04-13 | Hitachi | Elec | Main Converter | Capacitor Bank | O |  | O |  | DAP | Italy | Milan | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 96 | 0.41 | 0.41 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-04-13 |  | 2025-04-17 | 2025-04-17 | 2025-04-20 | 2025-04-20
485 | HVDC-ADOPT-SIM-0064 | E04-1 | 2025-01-08 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRDC-PS038-DG |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 1 | 0 | 0 | - |  |  |  | 3.1 | 0.02 | 0.02 | 2025-03-03 | 2025-03-03 | 2025-04-06 | 2025-04-06 |  | 2025-04-10 | 2025-04-21 |  | 2025-04-24
486 | HVDC-ADOPT-SIM-0040 | E04-1 | 2025-01-07 | Siemens | Elec | 400kV and 132kV New Converter GIS | MRDC-PS040-DG |  |  | O |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 8 | 1 | 0 | - |  |  |  | 211.1 | 0.87 | 0.87 | 2025-03-03 | 2025-03-03 | 2025-04-06 | 2025-04-06 |  | 2025-04-10 | 2025-04-21 |  | 2025-04-24
487 | HVDC-ADOPT-HE-0320 | E01 | 2025-03-14 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 250x12mm |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 44 | 0 | 2 | - |  |  |  | 19265 | 72.3 | 72.3 | 2025-03-14 | 2025-03-14 | 2025-04-12 | 2025-04-12 |  | 2025-04-15 | 2025-04-21 |  |  |  |  | 2025-04-23
488 | HVDC-ADOPT-HE-0293 | E01 | 2025-03-07 | Hitachi | Elec | Main Converter | Alu.lina AAC Solros 910mm² 61-kardeler | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 7 | 0 | 1 | - |  |  |  | 9242 | 17.92 | 17.92 | 2025-03-07 | 2025-03-07 | 2025-04-14 | 2025-04-14 |  | 2025-04-15 | 2025-04-21 | 2025-05-05
489 | HVDC-ADOPT-HE-0294 | E01 | 2025-03-07 | Hitachi | Elec | Main Converter | Alu.lina AAC Solros 910mm² 61-kardeler |  |  | O |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 5 | 0 | 1 | - |  |  |  | 5668 | 12.8 | 12.8 | 2025-03-07 | 2025-03-07 | 2025-04-14 | 2025-04-14 |  | 2025-04-15 | 2025-04-21 | 2025-05-05 | 2025-05-05
490 | HVDC-ADOPT-HE-0295 | E01 | 2025-03-07 | Hitachi | Elec | Main Converter | Alu.lina AAC Solros 910mm² 61-kardeler |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 17 | 0 | 1 | - |  |  |  | 22640 | 43.52 | 43.52 | 2025-03-07 | 2025-03-07 | 2025-04-14 | 2025-04-14 |  | 2025-04-15 | 2025-04-21 |  |  |  |  | 2025-04-23
491 | HVDC-ADOPT-HE-0288 | E01 | 2025-02-06 | Hitachi | Elec | Main Converter | Capacitor Bank |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | CMA | Scan Global Logistics AB | C | 2 | 0 | 1 | - |  |  |  | 1465 | 5.03 | 5.03 | 2025-02-06 | 2025-02-06 | 2025-04-13 | 2025-04-13 |  | 2025-04-22 | 2025-04-23
492 | HVDC-ADOPT-HE-0289 | E01 | 2025-02-06 | Hitachi | Elec | Main Converter | Spare Capacitor |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | CMA | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 87 | 0.41 | 0.41 | 2025-02-06 | 2025-02-06 | 2025-04-13 | 2025-04-13 |  | 2025-04-22 | 2025-04-23
493 | HVDC-ADOPT-HE-0296 | E01 | 2025-02-12 | Hitachi | Elec | Main Converter | Capacitor Bank | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | C | 4 | 0 | 1 | - |  |  |  | 1440 | 4.07 | 4.07 | 2025-02-12 | 2025-02-12 | 2025-04-13 | 2025-04-13 |  | 2025-04-22 | 2025-04-23 | 2025-05-11
494 | HVDC-ADOPT-HE-0297 | E01 | 2025-02-12 | Hitachi | Elec | Main Converter | Spare Capacitor | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port |  | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 197 | 0.21 | 0.21 | 2025-02-12 | 2025-02-12 | 2025-04-13 | 2025-04-13 |  | 2025-04-22 | 2025-04-23 | 2025-05-11
495 | HVDC-ADOPT-ZEN-0018 |  | 2025-03-27 | Fluid Pumps |  |  | Valves, Nozzle & Grooved Fittings |  |  |  |  | CIF | India | Cochin | Khalifa port |  |  | C | 13 | 0 | 1 | - |  |  |  | 6266.53 | 10.96 | 10.96 | 2025-04-03 | 2025-04-03 | 2025-04-14 | 2025-04-14 |  | 2025-04-21 | 2025-04-23 | [11 empty] | 2025-04-25
496 | HVDC-ADOPT-SCT-0077 | E08 | 2025-03-25 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O | O |  | FOB | Sweden | Malmoe | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1516 | 2.74 | 2.74 | 2025-04-10 | 2025-04-10 | 2025-04-17 | 2025-04-17 |  | 2025-04-22 | 2025-04-22 | 2025-05-01 | 2025-04-29 | [7 empty] | 2025-04-25
497 | HVDC-ADOPT-SCT-0080 | E08 | 2025-03-20 | Excellift | Mech | Crane and Hoist | Crane and Hoist (6th) | O |  | O | O | FOB | MALAYSIA | Kuala Lumpur | Abu Dhabi Airport |  |  | A | 1 | 0 | 0 | - |  |  |  | 182 | 0.93 | 0.93 | 2025-04-11 | 2025-04-11 | 2025-04-19 | 2025-04-19 |  | 2025-04-21 | 2025-04-21 | 2025-05-01 | 2025-04-29 | [7 empty] | 2025-04-22
498 | HVDC-ADOPT-SCT-0088 | E08 | 2025-04-16 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O |  |  |  | FOB | Spain | Vitoria-Gasteiz | Abu Dhabi Airport |  |  | A | 1 | 0 | 0 | - |  |  |  | 103 | 0.71 | 0.71 | 2025-04-16 | 2025-04-16 | 2025-04-19 | 2025-04-19 |  | 2025-04-22 | 2025-04-22 | 2025-04-23
499 | HVDC-ADOPT-HE-0321 | E01 | 2025-03-21 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 28 | 0 | 1 | - |  |  |  | 6731 | 36.7 | 36.7 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23
500 | HVDC-ADOPT-HE-0322 | E01 | 2025-03-13 | Hitachi | Elec | Main Converter | Control Cubicle |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 60 | 0 | 7 | - |  |  |  | 38318 | 290.6 | 290.6 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-22 | 2025-04-23
501 | HVDC-ADOPT-HE-0276 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 7 | - |  |  |  | 850 | 7.99 | 7.99 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
502 | HVDC-ADOPT-HE-0277 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors Spare |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 205 | 1.38 | 1.38 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
503 | HVDC-ADOPT-HE-0278 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Insulator for HP 12 AC Filter Resistor |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 960 | 4.13 | 4.13 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
504 | HVDC-ADOPT-HE-0279 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Composite Insulator Spare |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 70 | 0.35 | 0.35 | 2025-03-21 | 2025-03-21 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
505 | HVDC-ADOPT-HE-0280 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 2400 | 21.08 | 21.08 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
506 | HVDC-ADOPT-HE-0281 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors Spare |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 385 | 3.69 | 3.69 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
507 | HVDC-ADOPT-HE-0282 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 8100 | 113.61 | 113.61 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
508 | HVDC-ADOPT-HE-0283 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor Spare |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1335 | 19.11 | 19.11 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
509 | HVDC-ADOPT-HE-0284 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 8100 | 113.61 | 113.61 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
510 | HVDC-ADOPT-HE-0285 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor Spare | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 1335 | 19.11 | 19.11 | 2025-03-22 | 2025-03-22 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
511 | HVDC-ADOPT-HE-0286 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 6 | 0 | 0 | - |  |  |  | 2100 | 18.22 | 18.22 | 2025-03-20 | 2025-03-20 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
512 | HVDC-ADOPT-HE-0287 | E01 | 2025-03-22 | Hitachi | Elec | Main Converter | Auxillary Bus Filter Resistors Spare | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 335 | 3.21 | 3.21 | 2025-03-20 | 2025-03-20 | 2025-04-20 | 2025-04-20 |  | 2025-04-21 | 2025-04-23 |  |  |  |  | 2025-05-05
513 | HVDC-ADOPT-HE-0356 | E01 | 2025-04-20 | Hitachi | Elec | Main Converter | EXTERNAL PIPES VALVE HALL |  |  | O |  | DAP | Denmark | Billund | Abu Dhabi Airport |  |  | A | 4 | 0 | 0 | - |  |  |  | 8770 | 70.66 | 70.66 | 2025-04-20 | 2025-04-20 | 2025-04-25 | 2025-04-25 |  | 2025-04-25 | 2025-04-25 |  | 2025-04-30
514 | HVDC-ADOPT-HE-0355 | E01 | 2025-03-13 | Hitachi | Elec | Main Converter | NYTRO 10XN Transformer Oil | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port |  |  | C | 8 | 8 | 0 | - |  |  |  | 170620 | 306.37 | 306.37 | 2025-03-13 | 2025-03-13 | 2025-04-18 | 2025-04-18 |  | 2025-04-18 | 2025-04-24
515 | HVDC-ADOPT-SCT-0066 | E08 | 2025-03-04 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O | O | O | FOB | CHINA | Shanghai | Khalifa port |  | Deugro | C | 12 | 0 | 1 | - |  |  |  | 7475 | 20.43 | 20.43 | 2025-03-18 | 2025-03-18 | 2025-04-22 | 2025-04-22 |  | 2025-04-24 | 2025-04-25 | 2025-05-01 | 2025-05-01 |  | 2025-05-04 | [5 empty] | 2025-04-30
516 | HVDC-ADOPT-SIM-0072 | E04-1 | 2025-03-28 | Qualitrol | Elec | 400kV and 132kV New Converter GIS | 400kV PQMS System (WBS Element)_DC | O |  | O |  | CIF | United Kingdom | Belfast | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 981 | 5.5 | 5.5 | 2024-03-24 | 2024-03-24 | 2025-04-11 | 2025-04-11 |  | 2025-04-16 | 2025-04-16 | 2025-05-01 | 2025-04-29
517 | HVDC-ADOPT-SIM-0073 | E04-1 | 2025-03-28 | Qualitrol | Elec | 400kV and 132kV New Converter GIS | 400kV PQMS System (WBS Element)_PS | O |  | O |  | CIF | United Kingdom | Belfast | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 1080 | 5.5 | 5.5 | 2024-03-24 | 2024-03-24 | 2025-04-11 | 2025-04-11 |  | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23
518 | HVDC-ADOPT-SEI-0017-02 | E03 | 2025-01-21 | Sumitomo | Elec | 400kV HVDC Cable System | Oil Pressure Tank & Silicone Oil |  |  |  |  | CIF | JAPAN | Kobe | Khalifa port |  |  | C | 7 | 0 | 2 | - |  |  |  | 18673 | 82.6 | 82.6 | 2025-02-10 | 2025-02-10 | 2025-04-08 | 2025-04-08 |  | 2025-04-11 | 2025-04-30
519 | HVDC-ADOPT-SIM-0048 | E04-1 | 2024-12-05 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC-PS028-DG |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 16 | 1 | 0 | - |  |  |  | 3992 | 10.47 | 10.47 | 2025-03-17 | 2025-03-17 | 2025-04-20 | 2025-04-20 |  | 2025-04-23 | 2025-04-27
520 | HVDC-ADOPT-SIM-0049 | E04-1 | 2024-12-11 | Siemens | Elec | 400kV and 132kV New Converter GIS | 132 kV GIS DAS Spare cable feeder"_PS030 DG |  | O |  |  | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 4 | 0 | 0 | - |  |  |  | 18.8 | 0.09 | 0.09 | 2025-03-17 | 2025-03-17 | 2025-04-20 | 2025-04-20 |  | 2025-04-23 | 2025-04-27 | 2025-05-08 | [8 empty] | 2025-05-08
521 | HVDC-ADOPT-SIM-0051 | E04-1 | 2024-12-12 | Siemens | Elec | 400kV and 132kV New Converter GIS | GHDC-PS032-DG |  |  |  | O | CIF | GERMANY | Hamburg | Khalifa port | MAERSK | Alpha Maritime | C | 4 | 0 | 0 | - |  |  |  | 19.3 | 0.09 | 0.09 | 2025-03-17 | 2025-03-17 | 2025-04-20 | 2025-04-20 |  | 2025-04-23 | 2025-04-27
522 | HVDC-ADOPT-SCT-0075 | E08 | 2025-03-11 | El Seswdy | Elec | Radio Tower - Embedded Material | Radio Tower - Embedded Material | O |  | O |  | FOB | Egypt | Kairo | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 930 | 1.8 | 1.8 | 2025-04-08 | 2025-04-08 | 2025-04-11 | 2025-04-11 |  | 2025-04-28 | 2025-04-28 | 2025-04-30 | [8 empty] | 2025-04-30
523 | HVDC-ADOPT-HE-0330 | E01 | 2025-04-02 | Hitachi | Elec | Main Converter | Aluminium wire AAC Blubonnet |  | O |  | O | DAP | CHINA | Shanghai | Khalifa port | CSCL |  | C | 5 | 0 | 1 | - |  |  |  | 12910 | 44.91 | 44.91 | 2025-04-02 | 2025-04-02 | 2025-04-22 | 2025-04-22 |  | 2025-04-28 | 2025-04-28
524 | HVDC-ADOPT-SEI-0021-T | E03 | 2025-03-11 | Sumitomo | Elec | 400kV HVDC Cable System | Cable Cleat 400 kv Subseaa Cables |  |  |  |  | CIF | United Kingdom | Heathrow | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 22 | 0.07 | 0.07 | 2025-04-24 | 2025-04-24 | 2025-04-27 | 2025-04-27 |  | 2025-04-28 | 2025-04-29 | [7 empty] | 2025-05-03
525 | HVDC-ADOPT-SEI-0021-L | E03 | 2025-03-11 | Sumitomo | Elec | 400kV HVDC Cable System | Cable Cleat 400 kv Subseaa Cables |  |  |  |  | CIF | United Kingdom | Heathrow | Abu Dhabi Airport |  |  | A | 1 | 0 | 0 | - |  |  |  | 151 | 0.92 | 0.92 | 2025-04-24 | 2025-04-24 | 2025-04-27 | 2025-04-27 |  | 2025-05-01 | 2025-05-01 | [7 empty] | 2025-05-03
526 | HVDC-ADOPT-HE-0315 | E01 | 2025-03-19 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port |  | Scan Global Logistics AB | B | 12 | 0 | 0 | - |  |  |  | 22200 | 273.78 | 273.78 | 2025-03-19 | 2025-03-19 | 2025-04-29 | 2025-04-29 |  | 2025-04-29 | 2025-04-30 |  |  |  |  | 2025-05-03
527 | HVDC-ADOPT-HE-0316 | E01 | 2025-03-19 | Hitachi | Elec | Main Converter | HP 12 AC Filter Resistor Spare |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port |  | Scan Global Logistics AB | B | 2 | 0 | 0 | - |  |  |  | 3600 | 45.63 | 45.63 | 2025-03-19 | 2025-03-19 | 2025-04-29 | 2025-04-29 |  | 2025-04-29 | 2025-04-30 |  |  |  |  | 2025-05-03
528 | HVDC-ADOPT-SCT-0058 | E08 | 2025-03-19 | Dong Yang | Elec | Cathodic Protection | Cathodic Protection Systems (5th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1312 | 8.37 | 8.37 | 2025-03-19 | 2025-03-19 | 2025-05-01 | 2025-05-01 |  | 2025-04-30 | 2025-04-30 |  | 2025-05-12 | [7 empty] | 2025-05-12
529 | HVDC-ADOPT-SCT-0070 | I01 | 2025-03-19 | SHIN AHN | Inst. | Field Instrument | Field Instrument (1st) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 7 | 0 | 1 | - |  |  |  | 2775 | 27.11 | 27.11 | 2025-03-19 | 2025-03-19 | 2025-05-01 | 2025-05-01 |  | 2025-04-30 | 2025-04-30 |  | 2025-05-12 | [7 empty] | 2025-05-12
530 | HVDC-ADOPT-SCT-0089 | E08 | 2025-03-26 | Roxtec | Elec | Lighting&Small Power System | Mulitiple Cable Transit | O | O | O | O | FOB | CHINA | Shanghai | Khalifa port |  | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1132 | 2.37 | 2.37 | 2025-04-12 | 2025-04-12 | 2025-05-05 | 2025-05-05 |  | 2025-05-09 | 2025-05-09 | [9 empty] | 2025-05-12
531 | HVDC-ADOPT-SIM-0076-A | E04-1 | 2025-04-04 | STATRON | Elec | 400kV and 132kV New Converter GIS | Charger System_MRPS | O |  | O |  | CIF | Switzerland | Geneve | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1500 | 9.22 | 9.22 | 2025-04-30 | 2025-04-30 | 2025-05-06 | 2025-05-06 |  | 2025-05-08 | 2025-05-08
532 | HVDC-ADOPT-SIM-0076-B | E04-1 | 2025-04-04 | STATRON | Elec | 400kV and 132kV New Converter GIS | Charger System_SHPS | O |  | O |  | CIF | Switzerland | Geneve | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1500 | 9.22 | 9.22 | 2025-04-30 | 2025-04-30 | 2025-05-06 | 2025-05-06 |  | 2025-05-08 | 2025-05-08
533 | HVDC-ADOPT-SIM-0076-C | E04-1 | 2025-04-04 | STATRON | Elec | 400kV and 132kV New Converter GIS | Charger System_MRDC | O |  | O |  | CIF | Switzerland | Geneve | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1835 | 9.22 | 9.22 | 2025-04-30 | 2025-04-30 | 2025-05-06 | 2025-05-06 |  | 2025-05-08 | 2025-05-08
534 | HVDC-ADOPT-SIM-0076-D | E04-1 | 2025-04-04 | STATRON | Elec | 400kV and 132kV New Converter GIS | Charger System_SHDC | O |  | O |  | CIF | Switzerland | Geneve | Abu Dhabi Airport |  |  | A | 3 | 0 | 0 | - |  |  |  | 1850 | 9.22 | 9.22 | 2025-04-30 | 2025-04-30 | 2025-05-06 | 2025-05-06 |  | 2025-05-08 | 2025-05-08
535 | HVDC-ADOPT-SCT-0100 | E08 | 2025-05-08 | LS Cable | Elec | MV, LV & Control Cable | 400kv Power Cable Accessories | O |  |  |  | FOB | KOREA | Incheon | Abu Dhabi Airport |  |  | A | 1 | 0 | 0 | - |  |  |  | 392 | 0.97 | 0.97 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 |  | 2025-05-08 | 2025-05-09
536 | HVDC-ADOPT-HE-0340 | E01 | 2025-04-03 | Hitachi | Elec | Main Converter | UPS SYSTEM BATTERIES |  |  | O | O | DAP | India | Visakhapatnam | Khalifa port | MSC |  | C | 196 | 0 | 8 | - |  |  |  | 172256 | 114.28 | 172.26 | 2025-04-07 | 2025-04-07 | 2025-05-04 | 2025-05-04 |  | 2025-05-06 | 2025-05-07
537 | HVDC-ADOPT-SCT-0067 | E08 | 2025-02-18 | Sangdong | Elec | Earthing & Lightning Protection Material | Earthing & Lightning Protection Material (4th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 8 | 0 | 1 | - |  |  |  | 5470 | 21.64 | 21.64 | 2025-03-28 | 2025-03-28 | 2025-05-08 | 2025-05-08 |  | 2025-05-09 | 2025-05-12
538 | HVDC-ADOPT-SCT-0068 | E08 | 2025-04-02 | Bansuk | Elec | Lighting and Small Power Sysytem | Lighting & Small Power System | O | O | O | O | FOB | Spain | Barcelona | Khalifa port | MSC | Deugro | C | 25 | 0 | 0 | - |  |  |  | 6578.5 | 37.09 | 37.09 | 2025-04-02 | 2025-04-02 | 2025-05-10 | 2025-05-10 |  | 2025-05-09 | 2025-05-12
539 | HVDC-ADOPT-HE-0303 | E01 | 2025-03-11 | Hitachi | Elec | Main Converter | Singlepole, Insulator, Corona Rings |  |  | O |  | DAP | Italy | Venice | Khalifa port | MSC | Scan Global Logistics AB | C | 9 | 0 | 3 | - |  |  |  | 11975 | 53.2 | 53.2 | 2025-03-11 | 2025-03-11 | 2025-05-08 | 2025-05-08 |  | 2025-05-10 | 2025-05-12
540 | HVDC-ADOPT-HE-0304 | E01 | 2025-03-11 | Hitachi | Elec | Main Converter | Singlepole, Insulator, Corona Rings |  |  | O |  | DAP | Italy | Venice | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 538 | 2.7 | 2.7 | 2025-03-11 | 2025-03-11 | 2025-05-08 | 2025-05-08 |  | 2025-05-10 | 2025-05-12
541 | HVDC-ADOPT-HE-0305 | E01 | 2025-03-11 | Hitachi | Elec | Main Converter | Singlepole, Insulator, Corona Rings | O |  |  |  | DAP | Italy | Venice | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 538 | 2.7 | 2.7 | 2025-03-11 | 2025-03-11 | 2025-05-08 | 2025-05-08 |  | 2025-05-10 | 2025-05-12
542 | HVDC-ADOPT-HE-0306 | E01 | 2025-03-11 | Hitachi | Elec | Main Converter | Singlepole, Insulator, Corona Rings | O |  |  |  | DAP | Italy | Venice | Khalifa port | MSC | Scan Global Logistics AB | C | 9 | 0 | 0 | - |  |  |  | 12015 | 52.4 | 52.4 | 2025-03-11 | 2025-03-11 | 2025-05-08 | 2025-05-08 |  | 2025-05-10 | 2025-05-12
543 | HVDC-ADOPT-HE-0323 | E01 | 2025-03-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 53 | 0 | 2 | - |  |  |  | 10052 | 54.5 | 54.5 | 2025-03-26 | 2025-03-26 | 2025-05-16
544 | HVDC-ADOPT-HE-0324 | E01 | 2025-03-26 | Hitachi | Elec | Main Converter | Aluminium Busbar Tube 160x6mm |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MAERSK | Scan Global Logistics AB | C | 22 | 0 | 0 | - |  |  |  | 2721 | 14 | 14 | 2025-03-26 | 2025-03-26 | 2025-05-16
545 | HVDC-ADOPT-SCT-0062 | E08 | 2025-02-25 | Sangdong | Elec | Steel Conduit | Steel Conduit (5th) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 29 | 0 | 5 | - |  |  |  | 68850 | 106.28 | 106.28 | 2025-03-28 | 2025-03-28 | 2025-05-06
546 | HVDC-ADOPT-SCT-0060 | E08 | 2025-02-21 | Tyco Electronics | Elec | Cable Termimation Kit | Cable Termimation Kit (1st) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 2760 | 7.03 | 7.03 | 2025-03-28 | 2025-03-28 | 2025-05-06
547 | HVDC-ADOPT-HE-0325-1 | E01 | 2025-03-18 | Hitachi | Elec | Main Converter | CONTROL CUBICLE |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 18 | 0 | 2 | - |  |  |  | 9265 | 71 | 71 | 2025-03-21 | 2025-03-21 | 2025-05-06
548 | HVDC-ADOPT-HE-0325-2 | E01 | 2025-03-18 | Hitachi | Elec | Main Converter | CONTROL CUBICLE |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 9 | 0 | 0 | - |  |  |  | 2637 | 18.2 | 18.2 | 2025-03-21 | 2025-03-21 | 2025-05-06
549 | HVDC-ADOPT-SCT-0076 | E08 | 2025-03-04 | Roxtec | Elec | Lighting&Small Power System | Multiple Cable Transit | O | O | O |  | FOB | Sweden | Helsingborg | Khalifa port | MSC | Deugro | C | 6 | 1 | 0 | - |  |  |  | 1375 | 4.15 | 4.15 | 2025-03-27 | 2025-03-27 | 2025-05-16
550 | HVDC-ADOPT-HE-0331 | E01 | 2025-03-20 | Hitachi | Elec | Main Converter | GSA 73-AA Sp. Wallbushing |  | O |  | O | DAP | SWEDEN | Gothenburg | Khalifa port | MAERSK | Scan Global Logistics AB | C | 8 | 1 | 0 | - |  |  |  | 1880 | 9.59 | 9.59 | 2025-03-20 | 2025-03-20 | 2025-05-16
551 | HVDC-ADOPT-HE-0328 | E01 | 2025-04-02 | Hitachi | Elec | Main Converter | UPS SYSTEM PARTS | O |  |  |  | DAP | MALAYSIA | Port Klang | Khalifa port | CSCL |  | C | 19 | 0 | 2 | - |  |  |  | 23586 | 105 | 105 | 2025-04-07 | 2025-04-07 | 2025-06-22
552 | HVDC-ADOPT-HE-0332 | E01 | 2025-03-27 | Hitachi | Elec | Main Converter | External Pipe Support-Coolers |  | O |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 5 | 0 | 3 | - |  |  |  | 13150 | 82.4 | 82.4 | 2025-03-27 | 2025-03-27 | 2025-05-06
553 | HVDC-ADOPT-HE-0333 | E01 | 2025-03-27 | Hitachi | Elec | Main Converter | External Pipe Support-Coolers | O |  |  |  | DAP | SWEDEN | Gothenburg | Khalifa port | MSC | Scan Global Logistics AB | C | 3 | 0 | 0 | - |  |  |  | 4260 | 11.6 | 11.6 | 2025-03-27 | 2025-03-27 | 2025-05-06
554 | HVDC-ADOPT-HE-0240 | E01 | 2025-04-06 | Hitachi | Elec | Main Converter | Service Platform PB S171-12ES |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port |  |  | B | 3 | 0 | 0 | - |  |  |  | 16950 | 28.32 | 28.32 | 2025-04-06 | 2025-04-06 | 2025-05-11
555 | HVDC-ADOPT-HE-0241 | E01 | 2025-04-06 | Hitachi | Elec | Main Converter | Service Platform PB S171-12ES |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port |  |  | B | 2 | 0 | 0 | - |  |  |  | 11300 | 18.8 | 18.8 | 2025-04-06 | 2025-04-06 | 2025-05-11
556 | HVDC-ADOPT-HE-0242 | E01 | 2025-04-06 | Hitachi | Elec | Main Converter | Service Platform PB S171-12ES | O |  |  |  | DAP | BELGIUM | Antwerp | Khalifa port |  |  | B | 1 | 0 | 0 | - |  |  |  | 5650 | 9.4 | 9.4 | 2025-04-06 | 2025-04-06 | 2025-05-11
557 | HVDC-ADOPT-HE-0337 | E01 | 2025-04-12 | Hitachi | Elec | Main Converter | Al-Conductor |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 1 | 0 | - |  |  |  | 1030 | 2.61 | 2.61 | 2025-04-12 | 2025-04-12 | 2025-05-14
558 | HVDC-ADOPT-HE-0338 | E01 | 2025-04-12 | Hitachi | Elec | Main Converter | Al-Conductor |  | O |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 2 | 0 | 0 | - |  |  |  | 2573 | 5.22 | 5.22 | 2025-04-12 | 2025-04-12 | 2025-05-14
559 | HVDC-ADOPT-HE-0339 | E01 | 2025-04-12 | Hitachi | Elec | Main Converter | Al-Conductor |  | O |  |  | DAP | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 1 | 0 | 0 | - |  |  |  | 1465 | 2.61 | 2.61 | 2025-04-12 | 2025-04-12 | 2025-05-14
560 | HVDC-ADOPT-HE-0350 | E01 | 2025-04-17 | Hitachi | Elec | Main Converter | Fiber Optic Cables |  | O |  | O | DAP | United Kingdom | LONDON GATEWAY | Khalifa port | MSC | Scan Global Logistics AB | C | 8 | 0 | 1 | - |  |  |  | 5146 | 13.4 | 13.4 | 2025-04-12 | 2025-04-12 | 2025-05-14
561 | HVDC-ADOPT-HE-0351 | E01 | 2025-04-17 | Hitachi | Elec | Main Converter | Fiber Optic Cables |  |  | O |  | DAP | United Kingdom | LONDON GATEWAY | Khalifa port | MSC | Scan Global Logistics AB | C | 7 | 0 | 0 | - |  |  |  | 4828 | 11.05 | 11.05 | 2025-04-12 | 2025-04-12 | 2025-05-14
562 | HVDC-ADOPT-HE-0343 | E01 | 1141486 | Hitachi | Elec | Main Converter | ODF Cubibles - coupled |  |  |  | O | DAP | Bulgaria | Varna | Khalifa port | MSC | Scan Global Logistics AB | C | 6 | 0 | 1 | - |  |  |  | 3900 | 30.6 | 30.6 | 2025-04-12 | 2025-04-12 | 2025-05-26
563 | HVDC-ADOPT-HE-0342 | E01 | 1141486 | Hitachi | Elec | Main Converter | ODF Cubibles - coupled |  |  | O |  | DAP | Bulgaria | Varna | Khalifa port | MSC | Scan Global Logistics AB | C | 6 | 1 | 0 | - |  |  |  | 3900 | 30.6 | 30.6 | 2025-04-12 | 2025-04-12 | 2025-05-26
564 | HVDC-ADOPT-SCT-0074 | E08 | 2025-04-02 | TaeHwa | Elec | Cable Tray System | Cable Tray System (15th) |  | O |  | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 7 | 1 | 1 | - |  |  |  | 4356 | 29.97 | 29.97 | 2025-04-02 | 2025-04-02 | 2025-05-10
565 | HVDC-ADOPT-SCT-0081 | I01 | 2025-03-20 | SHIN AHN | Inst. | Field Instrument | Field Instrument (2nd) | O | O | O | O | FOB | KOREA | Busan Port | Khalifa port | HMM | Deugro | C | 4 | 1 | 0 | - |  |  |  | 1800 | 11.2 | 11.2 | 2025-04-02 | 2025-04-02 | 2025-05-10
566 | HVDC-ADOPT-HE-0354 | E01 | 2025-04-13 | Hitachi | Elec | Main Converter | UPS SYSTEM PARTS |  | O |  |  | DAP | MALAYSIA | Port Klang | Khalifa port |  |  | C | 19 | 0 | 2 | - |  |  |  | 23257 | 105 | 105 | 2025-04-13 | 2025-04-13 | 2025-05-04
567 | HVDC-ADOPT-HE-0357 | E01 | 2025-04-21 | Hitachi | Elec | Main Converter | UPS SYSTEM Accessories |  |  |  | O | DAP | MALAYSIA | Port Klang | Khalifa port |  |  | C | 19 | 0 | 2 | - |  |  |  | 23521 | 105 | 105 | 2025-04-24 | 2025-04-24 | 2025-05-12
568 | HVDC-ADOPT-HE-0358 | E01 | 2025-04-21 | Hitachi | Elec | Main Converter | UPS SYSTEM Accessories |  |  | O |  | DAP | MALAYSIA | Port Klang | Khalifa port |  |  | C | 19 | 0 | 2 | - |  |  |  | 23528 | 105 | 105 | 2025-04-24 | 2025-04-24 | 2025-05-12
569 | HVDC-ADOPT-HE-0360 | E01 | 2025-05-07 | Hitachi | Elec | Main Converter | External System Pipe Support VH |  |  | O |  | DAP | Denmark | Billund | Abu Dhabi Airport |  |  | A | 2 | 0 | 0 | - |  |  |  | 3010 | 8.77 | 8.77 | 2025-05-12 | 2025-05-12 | 2025-05-12
570 | HVDC-ADOPT-HE-0329 | E01 | 2025-04-12 | Hitachi | Elec | Main Converter | Dry Capacitors and Accessories |  |  | O |  | DAP | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 23 | 1 | 2 | - |  |  |  | 21440 | 96.2 | 96.2 | 2025-04-26 | 2025-04-26 | 2025-05-30
571 | HVDC-ADOPT-HE-0336 | E01 | 2025-04-12 | Hitachi | Elec | Main Converter | Dry Capacitors and Accessories |  |  |  | O | DAP | BELGIUM | Antwerp | Khalifa port | MSC | Scan Global Logistics AB | C | 18 | 1 | 2 | - |  |  |  | 17635 | 91.2 | 91.2 | 2025-04-26 | 2025-04-26 | 2025-05-30
572 | HVDC-ADOPT-HE-0344 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 25 | 0 | 3 | - |  |  |  | 25840 | 28.47 | 28.47 | 2025-04-15 | 2025-04-15 | 2025-05-12
573 | HVDC-ADOPT-HE-0345 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators Spare | O |  |  |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 563 | 0.63 | 0.63 | 2025-04-15 | 2025-04-15 | 2025-05-12
574 | HVDC-ADOPT-HE-0346 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators |  |  | O |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 30 | 0 | 0 | - |  |  |  | 29090 | 32.2 | 32.2 | 2025-04-15 | 2025-04-15 | 2025-05-12
575 | HVDC-ADOPT-HE-0347 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators Spare |  |  | O |  | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 4 | 0 | 0 | - |  |  |  | 563 | 0.63 | 0.63 | 2025-04-15 | 2025-04-15 | 2025-05-12
576 | HVDC-ADOPT-HE-0348 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators |  | O |  | O | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 17 | 0 | 0 | - |  |  |  | 15884 | 20.66 | 20.66 | 2025-04-15 | 2025-04-15 | 2025-05-12
577 | HVDC-ADOPT-HE-0349 | E01 | 2025-04-15 | Hitachi | Elec | Main Converter | Insulators Spare |  | O |  | O | DAP | CHINA | Shanghai | Khalifa port | MSC | Scan Global Logistics AB | C | 8 | 0 | 0 | - |  |  |  | 466 | 0.55 | 0.55 | 2025-04-15 | 2025-04-15 | 2025-05-12